## Sheet1
2 Card Varient
Defect no | Date | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-06-03 | Desktop | Edge | md | top cards are displayed in front of the circle, while in the design they appear partially behind it to create a depth effect. | https://i.ibb.co/5g6QFFKq/2155290114ee.png | https://i.ibb.co/pjLT574r/6816e6f88e69.png | P3 |  | Open |  |  | Failed | 2026-06-03 | Issue reproduced; card layering does not match the design.
2 | 2026-06-17 | Desktop | Edge | md | Partner cards are not clearly visible because they blend with the light background. but in design they are clearly visible | https://www.loom.com/share/7aace88df79f4fc18529578c0b1dce18 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; partner cards have low visibility and need better contrast or shadow effect.
3 | 2026-06-03 | Desktop | Edge | md | Card container shadow effect is missing on the website compared to the design. | https://i.ibb.co/783FDLy/54548a640ddd.png | https://i.ibb.co/bj0gcTTR/b247e3605922.png | P3 |  | Open |  |  | Failed | 2026-06-03 | Issue reproduced; card shadow effect does not match the design.
4 | 2026-06-03 | Desktop | Edge | md | should add shadow effect for starting top 2 Cards like above issue | https://www.loom.com/i/431d4303d1ed490e88dcc2f5386d8401 |  | P3 |  | Open |  |  | Failed | 2026-06-03 | Issue reproduced; card shadow effect does not match the design.
5 | 2026-06-17 | Desktop | Edge | md | Card container loses its rounded corners at 200% zoom. Rounded corners are visible at lower zoom levels but not at 200%. | https://www.loom.com/share/0e9e9d3e46a745dbb62116b315ef9733 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; card border radius is not maintained at 200% zoom.
6 | 2026-06-17 | Desktop | Edge | md | Image elements are missing alt attributes. | https://ibb.co/TBXhsgw8 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; 6 images do not have alt text.
7 | 2026-06-17 | Desktop | Edge | md | Invalid role attribute is used on a section element. | https://ibb.co/TBXhsgw8 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; invalid ARIA role detected by Nu HTML Checker.
8 | 2026-06-17 | Desktop | Edge | md | Joining fee amount is displayed on the same line as the label. It should appear on the next line as shown in the design. on left should has space for cards looks proffesional | https://www.loom.com/share/43b522095fa541caa3d73ec45d8661f1 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; joining fee text layout does not match the design.
9 | 2026-06-17 | Mobile | Chrome | md | Page performance score is 66, which needs improvement. | https://i.ibb.co/qLgYkfpV/136b266909a7.png |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; Lighthouse performance score is below the recommended threshold.
3 Card Varient (same issues from 2 card varient)
1 | 2026-06-17 | Desktop | Edge | md | Section heading bar colors do not match the design. | https://ibb.co/V0wV7wB5 | https://ibb.co/VpgKdn2r | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; heading bar color differs from the design.
1 | 2026-06-03 | Desktop | Edge | md | top cards are displayed in front of the circle, while in the design they appear partially behind it to create a depth effect. | https://i.ibb.co/5g6QFFKq/2155290114ee.png | https://i.ibb.co/pjLT574r/6816e6f88e69.png | P3 |  | Open |  |  | Failed | 2026-06-03 | Issue reproduced; card layering does not match the design.
2 | 2026-06-17 | Desktop | Edge | md | Partner cards are not clearly visible because they blend with the light background. but in design they are clearly visible | https://www.loom.com/share/7aace88df79f4fc18529578c0b1dce18 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; partner cards have low visibility and need better contrast or shadow effect.
3 | 2026-06-03 | Desktop | Edge | md | Card container shadow effect is missing on the website compared to the design. | https://i.ibb.co/783FDLy/54548a640ddd.png | https://i.ibb.co/bj0gcTTR/b247e3605922.png | P3 |  | Open |  |  | Failed | 2026-06-03 | Issue reproduced; card shadow effect does not match the design.

## Sampreets findings
Defect no | Date | Browsers | Font Size | Device | Priority | Type | Section | Title | Description | Steps to Reproduce | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Assigned To | Dev Status | Last Fixed On | Dev Remark | Status | Last Tested On | QA Remark
PF_001 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Entire Page | Nu HTML Validator highlights errors | If not everything including warnings, info, at least errors that get highlighted in the nu html validator needs to be addressed - https://validator.unl.edu/ | Nu HTML Validator --> Validate all the product family pages | https://loom.com/i/fd0cec2d597a4307b046ad4909d8be18 | - | Satyam
PF_002 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Aria role Table is not allowed for the pf-kb-wrapper | Either need to remove the aria role attribute or have an appropriate role for the container | Accessibility Checker for web --> Run Fast Check on the website | https://www.loom.com/i/4b3d25e53fb548e59dd9ddfd5bb5a9db | - | Satyam
PF_003 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Credit Card titles fail colour contrast | The credit card titles need to have #0077AF instead of #0094D9 in case of light mode | Key Benefits --> Credit card titles --> colour contrast ratio | https://www.loom.com/i/e2148365527b499c904250347d8c408a | - | Satyam | Fixed | 2026-06-19 | Fixed the contrast issue
PF_004 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Features & Benefits | Feature icon images are missing their alt text | Accessibility checker for web throws error for icons are they are images and according to it all images must have an alt text | Accessibility Checker for web --> Run Fast Check on the website | https://www.loom.com/i/faabc9aca2374444ac7a567a5960ace7 | - | Satyam | Fixed | 2026-06-19 | Added the alt tags to all the images icon
PF_005 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Each Key Benefit's heading fails the colour contrast | The Key Benefits headings need to have #0077AF instead of #0094D9 in case of light mode | Browser Tools CSS Overview --> Run the overview for the webpage | https://www.loom.com/i/3fc4bd160c4c44e18abab429e93e4e09 | - | Satyam | Fixed | 2026-06-19 | Fixed the contrast issue
PF_006 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Entire Page | Fallback font not assigned to some font occurrances | Fallback font neccessary in all font-family properties as it helps the browser to fallback to an acceptable font family instead of random one. | Browser Tools CSS Overview --> Run the overview --> Font Occurrances | https://www.loom.com/i/274cc1f019e1437582f3d80922f124c1 | - | Satyam | Fixed | 2026-06-19 | Attached the proper fallback fonts to all the texts
PF_007 | 2026-06-17 | All Browsers | - | All Devices | P3 | Bug | Entire Page | Browser console highlights one JS error | If possible, we can handle and avoid any JS error that appears in the browser console. We can ignore if the error is not impacting any UI or functionality. | Browser Tools --> Console --> JS error | https://loom.com/i/d0cc9fac82f5447183f9b959e690147b | - | Satyam | Need Discussion | 2026-06-19 | This issue is in the main.js file therfore will need to discuss and diagnose exactly what to do with the issue
PF_008 | 2026-06-17 | All Browsers | - | Desktops | P3 | Bug | Key Benefits | Apply Now button's arrow icon missing animation on hover | Like other CTA buttons that have arrow icon, the "Apply Now" button's arrow is missing animation effect when hovered on it. | Key Benefits --> Apply Now button --> Hover on the button to check if the arrow icon has the animated hover effect. | https://www.loom.com/i/aec0dcacf8ed47c18283aea676cc7ac8 | - | Satyam
PF_009 | 2026-06-17 | All Browsers | - | All Devices | P2 | Design/Asset | Entire Page | Dummy names on the card face images | Card Faces in the hero section & the 10% discount wrapper have dummy names in the image that need to be removed | Hero section, 10% discount banner --> Card Face --> Dummy Names | https://www.loom.com/i/237ad6c33ef9493bacb954c279fe6c71 | - | Phulvinder
PF_010 | 2026-06-17 | All Browsers | Large | Desktops | P2 | Bug | Features & Benefits | Feature Cards overlap each other when font increased | As per the current dummy content, when font size is increased, the feature cards start to overlap each other for desktops staring 1351px width. | Desktops (1351px & above) --> Features & Benefits --> Feature Cards --> Increase font size --> Notice how they overlap with each other. | https://www.loom.com/i/915a8ba6fc2841229600496b6129f25b | - | Satyam
PF_011 | 2026-06-17 | All Browsers | - | Desktops | P3 | Suggestion | Features & Benefits | Absolute postion feature cards not strong to hold length content | Not in favour of feature cards having absolute position instead of fixed layout in case of desktops as it possesses a high risk of their position shifting or breaking the UI in case slightly lengthy content needs to authored in them instead of short lines. | Desktops --> Features & Benefits --> Feature Cards --> Increase the content and notice their position shifiting and in some cases overlapping on each other. | https://loom.com/i/9df37d9e78d442e59272963911dbfe77 | - | Arun
PF_012 | 2026-06-17 | All Browsers | Large | Desktops | P2 | Bug | Features & Benefits | Top Feature cards get too close to the section heading | As per the current dummy content, when font size is increased, the top features cards go too close to the section heading for desktops having 1351px width and above | Desktops (1351px & above) --> Features & Benefits --> Feature Cards --> Increase font size --> Notice how the top feature cards go too close to the section heading | https://www.loom.com/i/ef30445198d94eb68b6ddcaae35ba17c | - | Satyam
PF_013 | 2026-06-17 | All Browsers | - | Tablets, Desktops | P2 | Bug | 10% Discount Banner | T&C Apply font doesn't adjust its size when font increased or decreased | For devices starting 768px and above, the font size of the T&C apply doesn't adjust as user increases or decreases it from the accessibility bar | Tablets & Desktops --> 10% Discount Banner --> T&C Apply --> Increase / Decrease font size --> Notice how the font size doesn't adjust | https://www.loom.com/i/6165e2ed87114267800bda4e04cf7405 | - | Satyam | Fixed | 2026-06-19 | Removed the static px and inserted the rem prop.
PF_014 | 2026-06-17 | All Browsers | - | All Devices | P3 | Need Confirmation | Header | Limited Period Offer UI broken for tablets & mobile phones | Limited offer wrap was discard and replaced with marquee, do we need to have it in the product family page? If yes, its UI is broken for mobile & tablet devices. It's height is too narrow, left & right gap appears for devices starting 640px - 768px, its content goes to next line starting 768px. If this wrapper is not needed then needs to be removed/replaced with marquee | Tablets & Mobile Phones --> Header --> Limited Period Offer Wrapper --> Notice how the wrapper gets gap from left & right & | Mobile Phones - https://www.loom.com/i/5b10e26f2fb54eeeb41bad9be680cf2a Mobile Phones (640px - 786px) - https://www.loom.com/i/d164954cafab41c3a82eba7f5674efc3 Tablets - https://www.loom.com/i/c0d0e13103f242e3b5d46de5616c5742 | https://loom.com/i/a3878703f374431cb510d4c53784f47c | Arun
PF_015 | 2026-06-17 | All Browsers | Lg & Default | Desktops | P2 | Bug | Hero Section | Less or no gap between Card Stack image & the card price right above | The gap between the card stack image & the card pricing text right above needs to be the same as it is between the banner headings above. But for desktop, it gets reduced in case of default font size or close to zero in case of large font. | Desktops --> Hero Section --> Notice the gap above the card stack image when font size increased or in default mode | https://www.loom.com/i/cad078f4312d4865945e16d826eea872 | https://www.loom.com/i/84990a4fb1ff4a919d763104a0bcddbe | Satyam | Fixed | 2026-06-19 | Added the gap between the elements
PF_016 | 2026-06-17 | All Browsers | - | Mobile Phones | P3 | Suggestion | SBI Card Presents | Selected card tab should only show the respective card | Respective card tab should only show the card whose tab is selected. Or instead we could have used the slider in the Discover our cards section on the home page instead of having tabs | Mobile Phones --> SBI Card Presents Section | https://www.loom.com/i/69d082e4b8ff4cfdae66f0ce6b3e210c | https://loom.com/i/640f4f168d8b42a6a315be0b1b0bad5b | Arun
PF_017 | 2026-06-17 | All Browsers | - | Mobile Phones | P2 | Bug | SBI Card Presents | Family cards wrapper doesn't cover the entire available space | In case of mobile phones with larger widths (landscape modes or foldable devices) the wrapper's width remains the same as it is in case of smaller screens and doesn't adjust size or layout according to the avaiable space | Mobile Phones --> SBI Card Presents Section --> Notice the empty spaces on the left & right side in case of larger width mobile phones | https://www.loom.com/i/a0581c1b999c400ea97312d75b4eab6e | - | Satyam
PF_018 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | SBI Card Presents | Card CTA buttons get wrapped to next line breaking the UI | Client doesn't prefer the CTA labels going to the next line and increasing the height in turn | Tablets --> SBI Card Presents Section --> CTA Buttons | https://www.loom.com/i/630d2e78f71040928106555573da6176 | - | Satyam
PF_019 | 2026-06-17 | All Browsers | - | Tablets | P3 | Suggestion | SBI Card Presents | 3 card wrapper gets congested within the available space | As followed on the home page, for tablet devices, we can set the wrapper to show 2 cards in a single slide and add slider to swipe and show the remaining card/s | Tablets --> SBI Card Presents Section --> Notice how the card containers get congested | https://www.loom.com/i/55ec45d2d51c4e8b80c8f0f57e32a62d | https://www.loom.com/i/f13c00dfafa44564a9304bcca978527a | Arun
PF_020 | 2026-06-17 | All Browsers | - | Mobile Phones | P2 | Bug | Features & Benefits | Features container doesn't cover the entire available space | In case of mobile phones with larger widths (landscape modes or foldable devices) the features container width remains the same as it is in case of smaller screens and doesn't adjust size or layout according to the avaiable space | Mobile Phones --> Features & Benefits --> Notice the empty spaces on the left & right side in case of larger width mobile phones | https://www.loom.com/i/53905605cc444b61a343b5627af3f8ed | - | Satyam
PF_021 | 2026-06-17 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | All section do not follow the page left-right page margin that header & footer follow | Need confirmation whether we again need to ignore the left-right page margin not being followed by the sections. | All Devices --> Left right page margin for each section in accordance with the header & footer | https://www.loom.com/i/1122dcfeffec4d739be3b6c33529e7e0 | - | Arun
PF_022 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | Key Benefits | Card's Apply Now button get wrapped to next line breaking the UI | Client doesn't prefer the CTA labels going to the next line and increasing the height in turn | Tablets --> Key Benefits Section --> Apply Now Button | https://www.loom.com/i/3ea6aa6a03a349feab3a4c9362aadad7 | - | Satyam
PF_023 | 2026-06-17 | All Browsers |  | Tablets | P2 | Suggestion | Key Benefits | Card header container gets congested in tablet layout | For small & medium size tablets, not much width available for the contents of the card header container, therefore they get too close together, card title gets wrapped into multiple lines breaking the card names readability flow. | Tablets --> Key Benefits Section --> Card Container header layout. | https://www.loom.com/i/c66e65a075e94bff89eafd3fc3292add | - | Arun
PF_024 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | Key Benefits | Card header container UI breaks in case of lengthy card title | For small & medium size tablets, length card title in the column header container has a chance of breaking its UI | Tablets --> Key Benefits Section --> Enter a lengthy card title in the container --> Notice how the UI breaks. | https://www.loom.com/i/564bc203b7d2452e92a14ee9753b4f7e | - | Satyam
PF_025 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Section background image shifts, breaks UI & inconsistent behaviour while scrolling | Compare the background image behaviour while scrolling with the other section backgrounds - i.) It appears as if instead of normally scrolling up or down, it is going underneath the next section. ii.) It shifts its position on real devices when page is scrolled up or down. iii.) It breaks the section's UI when scrolling down the page slowing from all the way to the top in one go. | All Devices --> SBI Card Presents Section --> Background Image --> Notice its behaviour while scrolling | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQCJQNJgAIXcQZMwY7BIoQzXAT-ZZjl7J_FsnutNDXILfaY?e=aBUavy | - | Sachin
PF_026 | 2026-06-17 | All Browsers | - | All Devices | P3 | Need Confirmation | Our Exclusive Partners | The Parner logo swiper should or shouldn't auto scroll? | Need confirmation whether the partner logo swiper should have auto-scroll behaviour or not. Currently it remains stationary | All Devices --> Our Exclusive Partners slider | https://www.loom.com/i/c70462df57584ff3b7e12df2f1ab5831 | - | Arun
PF_027 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | Our Exclusive Partners | The logo swiper doesn't slide using touch gesture | In case of mobile devices, the swiper slides through swipe gesture but not in case of tablet devices | Tablets --> Out Exclusive Partners Slider --> Try sliding the swiper using touch gesture | https://www.loom.com/i/7a3b36fb57df47ae9e494202cac7f235 | - | Satyam | Fixed | 2026-06-19 | Working on all deviced as expected. Fixed the tab size.
PF_028 | 2026-06-17 | All Browsers | - | Mobile Phones | P2 | Bug | Key Benefits | Gap between the column header container & Welcome benefits container | In case of mobile devices, a gap is observed between the column header container & Welcome Benefits container which doesn't match with the design | Mobile Phones --> Key Benefits --> Gap below the column header container | https://www.loom.com/i/6e651cbf75e74da09a07b219300f89b6 | https://www.loom.com/i/ca42f1f9fa484540a3a62484a13d9829 | Satyam | Fixed | 2026-06-19 | Gap removed between the header and content
PF_029 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Entire Page | Skip to main content not functional | Clicking on skip to main content button doesn't skip to the main section of the page | Skip to main content --> Click --> Notice if the page skips to the main section | https://www.loom.com/i/da7e688f0e484f99a53bfadf254cba5b | - | Satyam | Fixed | 2026-06-19 | Fixed the behaviour
PF_030 | 2026-06-17 | All Browsers | - | All Devices | P1 | Bug | Entire Page | Breadcrumb is missing for the page | Breadcrumb was decided to be present on all pages. But is missing on product family pages | Check if the breadcrumb is present below the header | https://www.loom.com/i/16a0bbc06d3046a68ccc041100de03ae | - | Satyam
PF_031 | 2026-06-17 | All Browsers | - | Desktops | P2 | Bug | SBI Card Presents | Key Benefit bullet point icons do not stay vertically center aligned with the sentence | If a solution possible that ensures the icons used as bullet points always appear vertically center aligned for all devices, it should be implemented. Currently the vertical alignment with the sentence if off in case of desktops and especially in case of large font | SBI Card Presents --> Bullet points icons --> Notice their vertical alignment with their sentence | https://www.loom.com/i/f101631a6fbb41b3b4cf85bbd49a8c1d | - | Satyam
PF_032 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | SBI Card Presents | Card Container UI breaks in case of lengthy content | The card container width doesn't get distributed equally in case the card names or bullet points get lengthy or have length variations between them which results in UI breaking | Tablets --> SBI Card Presents --> Enter lengthy & short credit card names --> Notice how the UI behaves. | https://www.loom.com/i/c595b8f833be4cd39a91e4ca08ee3950 | - | Satyam
PF_033 | 2026-06-17 | All Browsers | - | Desktops | P2 | Bug | SBI Card Presents | Card Container height & position breaks in case of lengthy content | The card container's height & position doesn't remain consistent when length content gets entered as card title or bullet point | Desktops --> SBI Card Presents --> Enter lengthy & short credit card names --> Notice the card container heights & positions | https://www.loom.com/i/cd7aad1f4a1641f28f0d6d70665c3378 | - | Satyam | Fixed | 2026-06-19 | Fixed the layout such that now the height of all the cards will consistently grow with the growing content
PF_034 | 2026-06-17 | All Browsers | - | Tablets | P3 | Bug | Hero Section | Banner sub heading has a chance to overlap the QR code | In case a lengthier sub heading is authored, it has a chance to get overlapped by the QR code on the left | Tablets --> Hero Section --> Banner sub heading --> Author lengthy content | https://www.loom.com/i/e02cc8a751b5490fb6d6bbc8bf9902e2 | - | Satyam
PF_035 | 2026-06-17 | All Browsers | - | All Devices | P3 | Bug | Hero Section | Banner heading - subheading has a chance to overlap with the card stack image | For all devices, in case lengthier content is authored, the heading & sub-heading has a chance to go beneath the card stack due to the absolute position of the card stack instead of having a fixed layout. | Hero Section --> Add lengthier banner heading & sub heading | https://www.loom.com/i/846c81da2dba49e8961251c2372a2709 | - | Satyam
PF_036 | 2026-06-17 | All Browsers | - | Desktops | P3 | Need Confirmation | SBI Card Presents | The Earn heading & description supposed to have less width? | Need confirmation whether the Earn Heading & Description present on top of the SBI Card Presents section is supposed to have lesser width | SBI Card Presents --> Earn Heading & Description | https://www.loom.com/i/6229b3efcc87486ab7b23f787c67993b | - | Satyam
PF_037 | 2026-06-17 | All Browsers | - | All Devices | P3 | Bug | Key Benefits | The card container UI breaks in case Joining Fee setence goes lengthy | For all devices, enter a lengthier Joining Fee sentence and notice how the card container content starts to break the UI | Key Benefits --> Enter lengthier card Joining Fees sentence --> Notice how the UI breaks. | https://www.loom.com/i/b6a8954f7b614254bb40cb00230e97e8 | - | Satyam
PF_038 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P3 | Need Confirmation | Hero Section | QR code container won't fit in case it's content increased. | Need confirmation whether the static content currently put up in the QR code container would be the max that is to be authored in it as it has a chance to go out of the container in case content increased any further | Hero Section --> QR Code --> Increase the heading & disclaimer content in the QR container --> Notice if it goes out of its parent container UI. | https://www.loom.com/i/9f76d267902641468bb1638ee171862f | - | Arun
PF_039 | 2026-06-18 | All Browsers | - | Desktops | P3 | Need Confirmation | Features & Benefits | Increased length of T&C has a chance to overlap above the image above | Need confirmation whether the Features & Benefits T&C is not going to be lengthier that it currently is. If gets twice or thrice it currently is, it has a chance to overlap the image above and if not, will surely start to cover the gap given between itself and the image. | Features & Benefits --> T&C --> Enter a lengthier T&C and notice if it starts to overlap the image above or cover the gap between itself & the image. | https://www.loom.com/i/43bfc2767cde45f8a37d5448f6812495 | - | Arun | /
PF_040 | 2026-06-18 | All Browsers | - | Desktops | P3 | Need Confirmation | Features & Benefits | Increased length of T&C would lead to increased number of lines | Need confirmation whether the Features & Benefits T&C is supposed to have shorter width the the available space in case of mobile phones as it may lead to more lines that required in case T&C gets lengthier. | Mobile Phones --> Features & Benefits --> Enter a lengthier T&C statement. | https://www.loom.com/i/350a306e47cf410a8ef0dbc83f5adf9b | - | Arun | /
PF_041 | 2026-06-18 | All Browsers | - | Mobile Phones | P3 | Need Confirmation | Assistance Made Simple | Vertical position mis-alignment between each title's descriptions | Need confirmation whether it is okay for the description below each title to not be vertically aligned just due to the length difference of the titles. Because, this is the same way it is on the catalogue page | Mobile Phones --> Assistance Made Simple --> Notice the vertical position consistency of the description under each title. | https://www.loom.com/i/87185e0ee8494296b38fffe7d6d97f46 | - | Arun | /
PF_042 | 2026-06-18 | All Browsers | - | Mobile Phones | P3 | Need Confirmation | Hero Section | Hero section Banner title font size less than section heading | Need confirmation whether it is okay for the Hero section banner title being <h1> of the page to be slightly lesser in size in comparison to normal section headings | Mobile Phones --> Hero section --> Compare the size of the Banner title with the section headings | https://www.loom.com/i/363d2b88d90440a3bbb163e646142b2d | - | Arun | /
PF_043 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | Page has not main content & sectional landmarks declared | Need confirmation whether this page needs main content & sectional landmarks for better accessibility of sections through D shortcut for blind users or it should again be ignored just like the rest of the pages | Entire Page --> Screen Readers --> The page has not main content & section landmarks | - | - | Arun | /
PF_044 | 2026-06-18 | All Browsers | - | All Devices | P2 | Need Confirmation | Entire Page | Inconsistent left & right padding for each section | Need confirmation if it is okay for the sections to not have same left & right padding. Currently they have different left & right paddings like - 20px, 18px, 16px & 12px | Entire Page --> Inspect the left & right padding of each section | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAcWlkLD_SGRJ7Z8ckJlom2ARdEfT_X9fIYMPjDzQe6oew?e=eqcTKD | - | Arun | /
PF_045 | 2026-06-18 | All Browsers | - | Mobile Phones | P2 | Bug | SBI Card Presents | Current state of the tab button doesn't get announced. | In case of mobile phones, the card tabs present are annouced as buttons but the state of each button - whether it is selected/active or not is not annouced when focused on it | SBI Card Presents --> Card Tab buttons --> Check if their current state is annouced when in focus | https://www.loom.com/i/e549aedf45b249108adf9deec9d27e4b | - | Satyam | /
PF_046 | 2026-06-18 | All Browsers | - | Desktops | P3 | Need Confirmation | Hero Section | QR code container would disappear when screen zoomed till 200-400% no desktop | Need confirmation whether the QR code is an essential content or just an alternate content. Because, it is not present in mobile layouts and when desktop users zoom in, mobile layout gets followed due to which QR code disappears. If it is an essential content that should be available for all desktop users then it would be considered loss of information | Desktops --> Hero Section --> Zoom in till 200% --> Notice the QR code disappearing | https://loom.com/i/d28c2b8dde4a4fec8bcd72a908426d7c | - | Arun | /
PF_047 | 2026-06-18 | All Browsers | - | All Devices | P3 | Suggestion | Entire Page | Levels of the bullet points get annouced even when they are not nested | For all the bullet points on the entire page, if they are not going to have nesting within them, they do not need have their level announced. It's not a failure but it adds to audio noise and gives the user impression that there is a nested hierarchy of bullet points even when there isn't one | Entire Page --> Screen Readers --> All bullet points --> Notice how their level is annouced even when they are not nested | - | - | Satyam | /
PF_048 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Features & Benefits | Screen readers do not follow the visual order while scanning feature cards | In case of desktops, when narrator scans and annouces the feature cards, it doesn't follow the visual order in which the feature cards appear on the desktop layout. Instead, it follows the same visual order that the feature cards follow in case of mobile layout. If this is the case then the feature card visual sequence should be the same as it is in mobile layout. | Desktops --> Screen Readers --> Feature Cards --> Notice the sequence of the feature cards followed while narrating them. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQA2Ftnsh9OmRKEp51ulbB_MAYmmBw8KXJE0jVznvlNxPig?e=eDkVe1 | - | Satyam | /
PF_049 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | While focus on Apply Now CTA, it annouces info apart from the focus CTA | When focus lands on any of the Apply Now CTA in the key benefits container, instead of only annoucing the role, label & context of the particular CTA, it starts to annouce extra information not exactly related to the element in focus. | Desktops --> Screen Readers --> Apply Now CTA --> Notice the annoucement when Apply Now CTA in focus | - | - | Satyam | /
PF_050 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Same info annouced multiple times when focus on Table column header | When focus lands on any of the column header and notice how the same information is getting annouced multiple times. | Desktops --> Screen Readers --> Get the focus on column header | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQChWF3zbPSKRaS3w8K0j_nQAVHiTZzi5DTqVx0SXg3hTx0?e=ZMbCFn | - | Satyam | /
PF_051 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Blind user doesn't get the column (card name) & row (Benefit) context on cell focus | When screen reader focuses on each cell using ctrl + alt + arrow keys, the context of it doesn't get announced - for which card this cell is about & which benefit category does it come under. Due to this, user only gets to hear the benefits but doesn't get to know they are related to which card and which benefit category. | Desktops --> Screen Readers --> Focus on the table --> Get focus on each cell using ctrl + alt + arrow keys | https://www.loom.com/i/d503d99d6459490fa272d85e544cd6c6 | - | Satyam | /
PF_052 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Contrainsts while trying to move up & down the table cells | In a table, usually user is able to move up & down the rows using ctrl + alt + up or down arrow key but in this case, user can only move up and down the rows when focus is on the very first cell of each row | Desktops --> Screen Readers --> Keep the focus on any row cell apart from the 1st one --> Try moving up & down the row using ctrl + alt + up / down button | https://loom.com/i/5068493943364a68a610a5cb4a95409f | - | Satyam | /
PF_053 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Unable to traverse through table cells using NVDA screen reader | Case when NVDA screen reader is being used, even when focus is on the table, user remains unable to navigate through table cells using ctrl + alt + up or down arrow key | Desktops --> NVDA screen reader --> Focus on the table --> Try to focus table cells using ctrl + alt + up or down arrow key | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAQ5r21FUoNQJXvWFOyEx2zAY-IIUhi9Zht8lcxxvUojYk?e=yqoJFl | - | Satyam | Fixed | 2026-06-19 | I have added shadow to the complete outer container of the component. Although other than variant with 1 card it might appear a bit different because the first row will have bottom shadow overlapped on the next row if applied on individual rows.
PF_054 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Entire column header content annouced while scanning each table cell | In NVDA Scan Mode, navigating table through up & down arrow keys, the screen reader announces the entire column header rather than the relevant card name and benefit type for each cell | Desktops --> NVDA screen reader --> Scan through the table --> Notice the annoucement when each cell is changed. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQDZj3QKqBx9T7s43Gm6lZl5AQ--6zTSRrMgkJGY_o08toQ?e=sohywJ | - | Satyam
PF_055 | 2026-06-18 | All Browsers | - | All Devices | P2 | Need Confirmation | Entire Page | T&C apply can be hyperlinks instead of normal text? | Need confirmation whether any of the T&C apply. text present across the page needs to be hyperlink instead of normal text. If yes, need at least one of them as hyperlink to demonstrate how it is going to be | Entire Page --> Any section that has T&C apply text | https://www.loom.com/i/45abc345837e46abb399a02e30590a5a | - | Arun | /
PF_056 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Hero Section | Inconsistent font weight of the banner title | In the design, 800 font weight is given for the hero section banner title in case of mobile layout but 700 font weight given in case of desktop layout. Need confirmation which font weight needs to be followed. Currently 800 is being followed for all layouts | Hero Section --> Banner Title --> Font weight | https://www.loom.com/i/78eb56307c76439d8c7ec8398c54ac3c | https://www.loom.com/i/d551dd2c9de8483dbe708b2ab601950f | Satyam | /
PF_057 | 2026-06-18 | All Browsers | - | All Devices | P3 | Bug | Hero Section | Price text font weight needs to be increased to match with design | In the design, the price text font weight is 500 but on the webpage, 400 is used | Hero Section --> Price Text --> Font weight | https://www.loom.com/i/b7f7e035daaf469aa8c76cf1d6a17127 | https://www.loom.com/i/3c58f7bc22bb4a95aac958c4120e4a6e | Satyam
PF_058 | 2026-06-18 | All Browsers | - | All Devices | P3 | Bug | Hero Section | QR code TnC text font family mis-match | In the design, Roboto is used as font family for QR Code TnC text instead of Roboto Condensed | Hero Section --> QR Code --> TnC --> Font Family | https://www.loom.com/i/7e81b21be3cd41379cd1c8fa2525ebe4 | https://www.loom.com/i/544562af1cbf4e2180f1e4dbce4d0825 | Satyam
PF_059 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | Formats other then .webp used for images all across the page | As per the latest communication, it was decided all image assets to be used on the page would be in .webp format instead of .jpg or .png format but almost all the images are still not in .webp format. Need confirmation whether it is alright or needs to be addressed | Entire Page --> Image Assets --> Image format | - | - | Arun
PF_060 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P2 | Bug | SBI Card Presents | "Earn upto" heading takes more than one line | As per the design, the "Earn upto" heading takes a single line only but on the webpage its width is reduced in order for it to take more than 1 line | Desktop --> SBI Card Presents --> Earn Upto Heading --> Notice how it takes more than 1 line | https://www.loom.com/i/d6b7b7c75861456daad4925f6562ae29 | https://www.loom.com/i/0d81f6b322ca475fa812d388d196bfcc | Satyam | Fixed | 2026-06-19 | Adjusted the width of the heading, now coming in a single line as provided in the design
PF_061 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P3 | Bug | SBI Card Presents | Less gap between "Earn upto" heading & its description | While observing the design for desktop layout, the "Earn upto" title & description appear to be having sufficient gap between them but when reviewing the same on the webpage, the appear slightly more close to each other | Desktop --> SBI Card Presents --> Notice the gap between Earn upto heading & its description | https://www.loom.com/i/5b96dd8953c54d1fa7ee31898b9cecb6 | https://www.loom.com/i/a9296565728b4ce98c04de7d91a3c61a | Satyam
PF_062 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | "Earn upto" heading's description font properties do not match the design | The design has #000000 as font colour. It also has 1.5 line height ratio for the description. On the web, #222222 colour is used and 1.1 line height is given. It also as 16px size but on the web it has 2rem size which amounts to 18px it can be reduced to 1.8 rem to amount to 16px. Also, on the webpage, a &nbsp space character is present due to which the 2nd line appears to be again starting from the left even though the sentence is actually center aligned | SBI Card Presents --> "Earn Upto" description --> Match the font properties with the design | https://www.loom.com/i/d4761538f0594a2aa9c9cfda51c6fff3 | https://www.loom.com/i/f24fbbb3453d41e5bf29d920944deb2c | Satyam | Fixed | 2026-06-19 | Color of the text changed to #000000, alignment is fixed, lineheight is fixed to 1.5. About font-size its already discussed basis issue (73,74).
PF_063 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | SBI Card Presents | "Earn upto" heading & the amount span font size inconsistent | Need confirmation about that standard font size needs to be followed for "Earn upto" heading as well as the amount <span> inside it. In case of desktop, on the webpage it is - 25.2px that is 2.8rem, 36px for amount span that is 4rem but the design has - 20px & 28px for amount span. Whereas, for mobile phones, webpage has - 22.5px that is 3rem, 30px that is 4rem for amount and the design has 24px & 33px for amount. The design itself is not consistent as it uses increased font size for smaller layout and decreased size for larger layouts | SBI Card Presents --> "Earn Upto" description --> Match the font size properties with the design | https://www.loom.com/i/7ca55b4eb597448e9c7cc9954a7fb2d3 | https://loom.com/i/5be14458aee04813804591c74dc3a3af | Arun
PF_064 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Hero Section | Gap & Position mismatch between banner title, sub-title & card price | Need a confirmation on the exact gap that should be maintained between title, sub-title & the card price text because the way design is made, unable to determine what exact gap should be maintained | Hero Section --> Notice gaps between banner title, sub title & card price text | https://www.loom.com/i/53209b4972e94c2cb66164a9cdfa469c | https://www.loom.com/i/c7600968531a4f5ab0b49e73c2487900 | Arun
PF_065 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Less gap between "Earn upto" description & SBI Card Present heading | Compare to design, the gap between "Earn upto" description & the SBI Card Presents heading is less | SBI Card Presents --> Gap between "Earn upto" description & the "SBI Card Presents" heading | https://www.loom.com/i/14da81340e3344ceb93562810ab05074 | https://www.loom.com/i/618d606182794efab20a5c7f0b936f9c | Satyam | Fixed | 2026-06-19 | I have added the gap to be 40px. In the design it was 35px but was not making any significant difference in appearance hence increased it to 40px.
PF_066 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Card Face shadow effect missing | As shown in the design, the card face shadow effect is missing behind the card face images | SBI Card Presents --> Notice how the card face shadow effect is missing. | https://www.loom.com/i/acfe1a1e36ba44d584eec632afff753d | https://www.loom.com/i/f28f655cc87946e89462e8e25c02385b | Satyam | Fixed | 2026-06-19 | Added the shadow
PF_067 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Card Face shadow effect missing | Even if the card face shadow effect is not present for this section in the design, it is required to prevent white & black card faces to merge with light or dark backgrounds. | SBI Card Presents --> Notice how the card face shadow effect is missing. | https://www.loom.com/i/aa93dcf6e96c4a22addc5d4a7b045daf | - | Satyam | Fixed | 2026-06-19 | Added the shadow
PF_068 | 2026-06-18 | All Browsers | - | All Devices | P2 | Design/Asset | Our Exclusive Partners | Brand logos not having the same size | Each brand's logo should appear in the same size as others | Our Exclusive Partners --> Notice the brand logo size differences | https://www.loom.com/i/e9f440a0b23b4a8ca505dc8ced208d04 | - | Phulvinder
PF_069 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Key Benefits | Font weight of the Key Benefits Bullet points inconsistent | Need confirmation what font weight should be used for the bullet points in the key benefits table as in the design it is 400 in case of mobile layout & 500 in case of desktop layout and on the webpage it is 400 for all layouts | Key Benefits --> Bullet points --> Notice the font weight & compare with the design | https://www.loom.com/i/7a0194180f6647aea6896d145f877536 | https://loom.com/i/2fe5a291f09845ed84335d6c8db9e243 | Arun
PF_070 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Benefits Heading gradience do not match with the design | The gradience used on the current version differs from the one used in the design. Also, we need to inform if the same gradience is not possible on all varients. | Key Benefits --> Benefits Heading --> Notice the gradience effect and compare with the design | https://www.loom.com/i/2a484ee4254e44469b58e79e52a4818e | https://www.loom.com/i/5ec80e6f1ab5492ab09be13bd4e809a4 | Satyam | Fixed | 2026-06-19 | Gradient property fixed along with opacity and required shadows and borders
PF_071 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P2 | Bug | Features & Benefits | Foreground image missing blur and has incorrect layering | The foreground image circumference instead of going beneath the feature cards, should be on top of it and should have the blur effect as shown in the design. | Features & Benefits --> Foreground Image z-index & blur effect (match it with the design) | https://www.loom.com/i/379ab7bbbfb44afcab5cd1f47be67620 | https://www.loom.com/i/4322e9ced8074ddaaee7a85d7e607c76 | Satyam | Need Discussion | 2026-06-19 | This is actually an image along with the content within to be used directly in the context. So a matching asset will be required from the design team for the same.
PF_072 | 2026-06-18 | All Browsers | - | All Devices | P3 | Bug | Key Benefits | Joining Fee font weight mis-match with the design | The design has 500 font weight where as webpage has 600 font weight | Key Benefits --> Joining Fee --> Font weight | https://www.loom.com/i/9944cf5bb2174c4a8314cd5d6e4e7f64 | https://www.loom.com/i/5ada8057e90342d1b190c98fffc896cd | Satyam
PF_073 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Card Name font size mis-match with the design | In the design the card name font size is 24px but on the webpage it comes around 27.5px | SBI Card Presents --> Card Name Font --> Check the font size | https://www.loom.com/i/43d5074ded9e4caaa32a037e68775248 | https://www.loom.com/i/9d9009f298f84936822702273679ca98 | Satyam | Not a Bug | 2026-06-19 | Discussed with Sampreet and Sachin; this is not a bug but the standard behavior followed across the project. Font sizes are defined in rem and scale based on the configured root font size (8px for Desktop: 1025–1350px and Mobile: 381–767px), allowing them to adjust according to device width.
PF_074 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | Features & Benefits | Feature Card Heading & description font size mis-match | In the design, for feature title font size is 16px for all layouts & 12px for description but on the webpage it is around 18px & 15px | Features & Benefits --> Feature Card --> Title & description font size | https://www.loom.com/i/faa9b998714c4855a18c2704ec869ac4 | https://www.loom.com/i/976aa0fb056545dfaf2524640fb877f5 | Satyam | Not a Bug | 2026-06-19 | Discussed with Sampreet and Sachin; this is not a bug but the standard behavior followed across the project. Font sizes are defined in rem and scale based on the configured root font size (8px for Desktop: 1025–1350px and Mobile: 381–767px), allowing them to adjust according to device width.
PF_075 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Key Benefits container is missing shadow effect | The design has a shadow effect on the whole key benefits container. The same is missing on the webpage | Key Benefits --> Container's shadow effect | https://www.loom.com/i/8c69e53b4406477f8c09606e5753abd8 | https://www.loom.com/i/0d471821115847de8d06e25745f30a36 | Satyam | Fixed | 2026-06-19 | Fixed: refer to issue 53 it is the same thing.
PF_076 | 2026-06-19 | All Browsers | - | All Devices | P3 | Bug | Features & Benefits | Feature card container border radius mis-match | The border radius in the design is 6px but on the webpage it is 12px | Features & Benefits --> Feature Card --> Notice & compare the border radius with the design | https://www.loom.com/i/8799cdcd7b6c41f4ac2c5f217969312b | https://www.loom.com/i/0240d8ae699c41c7866672b2365ae25c | Satyam
PF_077 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Slightly less gap between card title, joining fee & CTA | When comparing the design & webpage, side by side, the card name, joining fee & CTA appear too close together in comparison to the design because there it seems they are slightly more apart | Key Benefits --> Card Name, Joining Fee & CTA --> | https://www.loom.com/i/cfae2932dead46959ce1d6799ac7d271 | https://www.loom.com/i/6efecd0a56764a13b1e997db34f100c2 | Satyam
PF_078 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Benefits list items font colour mis-match | The font colour in the design is #222222 but the one used on the webpage is #333 | Key Benefits --> Bullet points --> Notice the font colour & match it with the design | https://www.loom.com/i/6a9bf243f84f427dbdcdfe26cc30a9c0 | https://www.loom.com/i/5b4de51602474968afcbf740b2bf5f31 | Satyam
PF_079 | 2026-06-19 | All Browsers | - | All Devices | P2 | Design/Asset | Assistance Made Simple | 2 White patches observed in the background image used | Around the left & right side of the heading "Assistance Made Simple", white patches can be observed that is part of the background image used | Assistance made simple --> Section background image --> observe the white patches within the background image | https://www.loom.com/i/bf8b009880654f589775fb17ce932cc0 | https://loom.com/i/256c2515c6d0491c8b940d590b04887d | Phulvinder
PF_080 | 2026-06-19 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | Dedicated background images for all 3 breakpoints | Need confirmation whether we need dedicated sectional background images for mobile, tablets & desktop for the following sections - Hero Section (tablet), Features & Benefits (tablet), SBI Card Presents, Key Benefits, Discount Banner (tablet), Discount Assistance Section. Because, same resolution image gets cropped according to the available space and doesn't exactly give the look our design has | Entire Page --> All Sections --> Notice the sectional background image for each break-points and determine whether their essence is lost in different breakpoints | - | - | Arun
PF_081 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | The entire container including column header - background colour mis-match | In the design, #FAFDFF colour is used as the background fill but on the webpage - white color is used | Key Benefits --> Table container's background color --> Notice the difference between the design & web | https://www.loom.com/i/b28ce01355594702b3e6aff091b186e0 | https://www.loom.com/i/90cdf9692ec24e0b8b6d31ed8d6cbb87 | Satyam