## Simplifier Pages Open bugs
Defect no | Date | Browsers | Font Size | Device | Priority | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Assigned To | Dev Status | Dev Remark | Status | Last Tested On | QA Remark | QA Remark | fixed or not | Reason for fixed or not
SP_016 | 2026-01-07 | All Browsers | - | All Devices | P2 | Here are 4 Recommended Cards for you --> "Our Pick" tag label --> The label font weight needs to be 400 instead of 800 as per the design | https://www.loom.com/i/47097144117042398cba09d0dcdbbfed | https://www.loom.com/i/d29a3495c6174d67a3ff276bf508444f | Bharat | Need Discussion | 01/06/2026 - As discussed with Phulvindar You Can close it 12/5/2026 - It's same as in mobile in design you can see it's bold in mobile view | Need Discussion | 2026-05-13 | 13/05/2026 - 700 weight is even more than the card titles & sub titles 30/04/2026 - 700 weight is even more than the card titles & sub titles 19/02/2026 - 700 weight is even more than the card titles & sub titles | Our Pick tag label font weight needs to be 400 instead of 800. | Fixed | Client approved closure on 01/06/2026
SP_057 | 2026-02-19 | All Browsers | - | Desktops | P3 | Windows Narrator --> When going from 3rd Step to 2nd Step, user presses the tab button and the focus goes to the tabs that were present in the 3rd tab | https://www.loom.com/share/d5dc3145240c408e98c54af6d76615fd | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - Go all the way to the third step and get back to the first step now while the narrator scan mode is on (capslock + space) notice how the elements in the hidden steps get caught in the flow by the screen reader if user navigates using B, K, H, I, F or up/down arrow key. https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 22/05/2026 - Pressing F on keyboard still takes the focus to the actionable items present in the next steps while user stays on the current step - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html 13/05/2026 - Issue reopened because while being on 2nd step if user keeps pressing the button F which is a shortcut to traverse through all form fields, then the 3rd step checkboxes start to get focused while being on the 2nd step itself - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html 13/05/2026 - Issue Resolved - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html | Windows Narrator – Hidden step elements are still accessible when navigating between steps. | Not Fixed | Issue reopened on 02/06/2026; screen reader can still access hidden step elements
SP_063 | 2026-02-20 | All Browsers | - | Desktops | P3 | Windows Narrator --> Step 3 --> Blind user won't have any idea that he needs to select atleast 1 benefit for the "Show me my card" button to work. When the button is disabled and user focuses on it and clicks enter, it redirects to the back button on the top left. | - |  | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - Blind users still do not have any way to know that they need to select up to 3 or at least one interested benefit before they can move forward and the show me my card button remains disabled until they do select at least 1 benefit. Instead, it should've remained enabled for the blind users to focus on and press enter so the alert could appear that would mention they need to select at least one benefit - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 13/05/2026 - "Select up to 3 benefits" still doesn't get narrated if user quickly traverses through the tabs before it could get announced or if user goes back a step and lands again on the 3rd step. Instead, the "Show me my card" button should've always remain enabled and if user pressed enter when it is in focus while not having at least 1 benefit selected, then it should narrate, "Please select at least 1 benefit you are interested in to move forwards" - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html | Blind users are not informed that at least 1 benefit must be selected before proceeding. | Not Fixed | Issue reopened on 02/06/2026; guidance is still not announced to screen reader users
SP_065 | 2026-02-23 | All Browsers | - | All Devices | P3 | Step 1 --> Bar Tick Labels --> In case the text is changed for each bar ticks and it's character length is more or less than the current bar ticks, there is no guarantee whether the bar tick labels will be center aligned with the bar ticks | https://loom.com/i/776ce7dbdbc54832b037c1db11576a84 https://loom.com/i/c78d6330e3eb4ecea605bd783dc88d97 |  | Bharat | Fixed | There are no proper solution for this because labels are on absolute position and they are independent from bar | Need Discussion | 2026-06-02 | 02/06/2026 - Need confirmation from client whether the currently used content for the bar axis labels is the final one. | Bar tick labels may not stay center-aligned if label text length changes. | Not Fixed | Client confirmation pending on final label content
SP_073 | 2026-04-30 | All Browsers | - | All Devices | P2 | Here are 4 Recommended Cards for you --> We have added glow effect, gradiance shadow at the background of each card face for having a distinction between cards having the same color as the background in whichever section they appear across the website (handled for both dark & light theme already) but the same is missing in the simplifier page. | https://www.loom.com/i/3d4320096f1140b7a1ab044dcdaf4938 | - | Bharat | Fixed | 1/5/2026 - Fixed | Reopen | 2026-06-02 | 02/06/2026 - Same as mentioned on 13th May QA Remark - https://www.loom.com/i/74213fd281014b959d76a315ed2aab54 https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 22/05/2026 - Same as mentioned on 13th May QA Remark - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html 13/05/2026 - Now the glow gradiance is going out of the container and at the same time appearing on top of the card making the card face whitish. Need to refer the css of the compare-cards as it was discussed and decided that we will only follow box shadow and invert the values in case of dark mode - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html | Recommended cards glow/shadow effect is not matching the approved implementation. | Not Fixed | Issue reopened on 02/06/2026; glow effect still appears outside the container and over the card
SP_077 | 2026-04-30 | All Browsers | - | All Devices | P3 | Here are 4 Recommended Cards for you --> Shadow image below card faces. Extra gap present between the card face and the shadow image when compared with the design and other pages like compare cards etc. | https://www.loom.com/i/c7cdfffcbc774a6f856574debc72a530 | - | Bharat | Fixed | 13/5/2026 - Please check now | Reopen | 2026-06-02 | 02/06/2026 - The card face bottom shadow still doesn't match exactly with the compare cards shadow for any of the breakpoints - https://www.loom.com/i/64b77d1a912248a3bbbac2e1750ca2d6 https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 22/05/2026 - The card face images still overlap with the shadow image at the bottom the shadow image doesn't match with shadow image used below the card faces in compare cards - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html https://www.loom.com/i/65664ad075be418bb8d4b13a81a41ca9 13/05/2026 - Now the card face image overlaps with the shadow image at the bottom - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html https://www.loom.com/i/65664ad075be418bb8d4b13a81a41ca9 | Card face shadow image does not match the compare cards design. | Not Fixed | Issue reopened on 02/06/2026; shadow spacing and alignment still differ from compare cards
SP_078 | 2026-04-30 | All Browsers | - | All Devices | P3 | Dark Mode --> 3 Card stack image with the Section Title. In case of white mode, the image has grey shadow effect & gradiance effect at the edges but the same is missing in the dark mode. In case of dark mode, we have have white low shadow & glowing effect | https://www.loom.com/i/0a48c3fdba3c4222a023920d4fb606f9 | - | Bharat | Need Discussion | 11/5/2026 - The shadow is embedded within the image itself. If we need to modify the shadow for dark mode, we would have to use a separate image specifically for dark mode, which would unnecessarily require maintaining two image assets. Since the current appearance is acceptable, we can consider leaving this as is. | Need Discussion | 2026-05-13 | 13/05/2026 - Need to discuss the Dev Remark with Arun sir and keep the bug on hold as discussed with Bharat. | Dark mode card stack image is missing the expected glow/shadow effect. | Not Fixed | Client/Design discussion pending
SP_088 | 2026-04-30 | All Browsers | - | All Devices | P2 | 2nd/3rd Step --> Click on back button --> Notice the animation of how the previous slide appears --> Click on the Next button --> Notice how the next slide appears. The animation for previous slide and the next slide is not the same. | https://www.loom.com/share/789614a012be4c15ab2448fc5951ecc0 | - | Bharat | Need Discussion | 12/5/2026 - The slide animation cannot be the same in both directions because the card visibility state is different during each transition. When the Next button is clicked, the upcoming slide is already partially visible behind the current slide as part of the card stack. But when the Back button is clicked, the previous slide is completely hidden and needs to re-enter from outside the stack. | Need Discussion | 2026-05-13 | 13/05/2026 - Need to discuss the Dev Remark with Arun sir and keep the bug on hold. | Previous and next slide animations are inconsistent. | Not Fixed | Pending discussion; current behavior considered technically expected by development
SP_098 | 2026-04-30 | All Browsers | - | Touch Devices | P3 | Touch Devices --> Dark Mode --> All 3 Steps (Slides) --> Every time user scrolls down, the bottom of the slide container shrinks for a noticeable moment before going back to normal. | https://www.loom.com/share/111b66da3a9f45ed83b97878962d7716 | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - The issue mentioned in the description is still observable on real devices - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 13/05/2026 - The issue mentioned in the description is still observable on real devices - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html# | Slide container briefly shrinks while scrolling in dark mode on touch devices. | Not Fixed | Issue reopened on 02/06/2026; still reproducible on real devices
SP_099 | 2026-05-13 | All Browsers | - | Desktops | P2 | Step 1 --> Annual Income Bar. When hovering over the thumb, the mouse should change to hand icon indicating that it is draggable to other values. When hovered on the rest of the bar except for the thumb, the mouse should change to finger icon indicating that the value can be changed by clicking. | https://www.loom.com/i/f5df3e513a274ee5aede77c021544781 | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - Hover over the bar's thumb changes the mouse icon to finger instead of hand for indicating that the item is dragable. When hovering on the bar itself, the mouse icon doesn't change to finger icon indicating that bar itself can be clicked to change the income value to the one that is nearest to the click event. Also, now clicking and dragging the thumb is no longer changing the bar tick - https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAvQlNNWQJCTpN8hmtmDDGWAb8zo-bGKFBajvgstOJ00HE?e=ZF1mc2 https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html | Annual income bar cursor behavior and drag functionality are incorrect. | Not Fixed | Issue reopened on 02/06/2026; cursor icons and drag functionality are not working as expected
SP_110 | 2026-05-13 | All Browsers | - | All Devices | P2 | Here Are The 4 Recommended cards For You --> This title "Here Are the 4 Recommended Cards For You" is #222222 in the design instead of blue. Please check QA Remark as the bug is updated as per the design change in the QA Remark. | https://www.loom.com/i/fc70e652351b431dbdd2258431a72d4c | - | Bharat | Need Discussion | 1/6/2026 - Once backgound image is final I will update color accordingly | Unresolved | 2026-05-22 | 22/05/2026 - As per the new design, the Heading - "Here Are 4 Recommended Cards For You" font colour should be #302B6C | Recommended cards heading color does not match the latest design. | Not Fixed | Awaiting final background image/design confirmation
SP_111 | 2026-05-13 | All Browsers | - | All Devices | P2 | All Steps --> Next & Show Me My Cards Button. The Button label goes uppercase by default. Need to remove the uppercase class from both the buttom element. | https://www.loom.com/i/b560212601694e728c6180f510cc207d https://www.loom.com/i/0335bd08d7c44ad1873daf5e546498d4 | - | Bharat | Need Discussion | 26/5/2026 - As discussed with Namita in internal call we are not removing uppercase class from button on all the pages all buttons should have in uppercase only | Unresolved | 2026-05-22 |  | Next and Show My Cards button labels are displayed in uppercase. | Fixed | Requirement changed; approved to keep all button labels uppercase
SP_112 | 2026-05-13 | All Browsers | - | All Devices | P2 | All Steps --> Next Button & Show Me My Cards Button. To much gap between the button label & the arrow icon. Button width can be reduced in order to have a normal gap between the too. | https://www.loom.com/i/59fe0b751b7949d99eeaa7b789ad1462 https://www.loom.com/i/220ddc08c36a44bf81d8abd0e8a1e0db | - | Bharat | Fixed | 3/6/2026 - It's according to design | Reopen | 2026-06-02 | 02/06/2026 - The issue is the same as mentioned in the description - latest build- https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# https://loom.com/i/b43e0c1346dd4d48a2defb28f8ba8085 https://loom.com/i/a16a451d39324ed2b4f178f1abfd7183 | Excessive gap between button label and arrow icon. | Not Fixed | Issue reopened on 02/06/2026; gap still does not match expected design
SP_113 | 2026-05-13 | All Browsers | - | All Devices | P3 | Layout breaks at 1201px - https://loom.com/i/5c2299e6bd094288b44098702ee1da7e at 767px - https://loom.com/i/c637fdafa15944f39bb71e9b24a9d4b2 and at 1023px in case of small or large font - https://loom.com/i/ccf51071a1a94f0b968cb60af1fcc1ae | - | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - The issue is the same as mentioned in the description - latest build- https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# https://loom.com/i/f378546d90774750a102438fd57d398c https://loom.com/i/a41d37930c3b42bc9c85ff1be27327f3 | Layout breaks at specific breakpoints and font sizes. | Not Fixed | Issue reopened on 02/06/2026; layout issues are still present in the latest build | d
SP_114 | 2026-05-13 | All Browsers | - | All Devices | P3 | Step 3 - Choose Your Interested Benefits --> Case when user already has 3 benefits selected and tries to select more, please add a toast alert or disclaimer alert mentioning "Only up to 3 benefits can be selected". | - | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - The alert message doesn't get annouced by the screen readers as soon as it appears. Also, for all devices, the alert message appears on top of the "Select up to 3 benefits" label. It can instead utilize the empty space at the bottom - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# https://www.loom.com/i/d387b9010a004fdcb0173ff92f3d1fee. | Benefit selection limit alert is not fully accessible and positioned incorrectly. | Not Fixed | Issue reopened on 02/06/2026; alert is not announced by screen readers and overlaps content
SP_117 | 2026-05-13 | All Browsers | - | All Devices | P2 | Step 3 --> Choose your interested benefits --> "Select up to 3 benefits" blinking border not really visible when no benefits are selected therefore the attention doesn't go there. Also, it should only blink when user tries to move forward without selecting at least 1 benefit, currently it by default keeps blinking until any benefit is selected | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBzUoSj1qZDQoxPC6Mxe1uOAfv-UrqhP91jugOH5LRsPXw?e=mfOQLd | - | Bharat | Need Discussion | 26/5/2026 - Button is in disable state and button is not allowing any cursor action when there is no benefits selected than how user will try to move forword | Unresolved | 2026-05-22 |  | Select up to 3 benefits blinking indicator behavior does not match the requirement. | Not Fixed | Requirement is unresolved and pending discussion
SP_121 | 2026-05-27 | All Browsers | - | All Devices | P2 | Step 2 (Where Do You Spend The Most) --> When input box is checked, the background fill colour should be #e0f3f7 as per the design instead of #ebffff | https://www.loom.com/i/1a94cd0b045f4ff4a903e5125d3b105e | https://www.loom.com/i/38489c457ebc43c3b118f5eb73344cff | Bharat | Need Discussion | 28/5/2026 - it's because design color was giving error in accessbilty extension |  |  |  | Selected input box background color differs from the design. | Fixed | Accessibility requirement overrides the design color
SP_129 | 2026-05-27 | All Browsers | - | Desktops | P2 | Keyboard Accessibility --> Step 1 --> Focus the bar thumb through keyboard. The focus outline of the bar thumb is not properly visible making the user unsure where the keyboard's focus is | https://www.loom.com/i/057ee2b616e14d4c9dde48aadb8639de | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - As per the WCAG 2.2 guidelines, the focus outline should maitain a 3:1 colour contrast ratio from the immediate colours surrounding it, this is still getting failed - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# https://www.loom.com/i/09414314c6d94c8bb1e0bac97acf0129 | Focus outline of the bar thumb is not sufficiently visible. | Not Fixed | Issue reopened on 02/06/2026; focus indicator still fails WCAG 2.2 contrast requirements
SP_132 | 2026-05-27 | All Browsers | - | All Devices | P2 | Dark Mode --> Step 1 --> Annual Income Bar --> The Bar's gradiance, Rs. icons and other details still remain bright themed when in dark mode. | https://www.loom.com/i/b45dafa37383412aa108ad5bebcbccbb | - | Bharat | Need Discussion | 1/6/2026 - We don't have design regardig this and as discussed with Phulvindar it's not required |  |  |  | Annual income bar elements remain bright-themed in dark mode. | Fixed | Requirement not needed as per discussion with stakeholders
SP_136 | 2026-05-27 | All Browsers | - | Desktops | P3 | Step 2 (Where Do You Spend The Most) --> In this new changed layout, in case when the Checkbox heading is lengthier, it has a chance of breaking the UI in case of mobile phones & tablets | https://www.loom.com/i/8060920167ac46d7ab333e89448a53e9 https://www.loom.com/i/6b887632daad4e8ca47d786e06cceacb | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - The issue is still the same as mentioned in the bug description and shown in the screenshots.
SP_137 | 2026-05-27 | All Browsers | - | All Devices | P3 | Step 2 (Where Do You Spend The Most) --> The check box's size and the tick mark when checked doesn't exactly match with the design | https://www.loom.com/i/894758d9381544c7a98645ca98191879 | - | Bharat | Need Discussion | 28/5/2026 - Checbox size is reduced to maintain in one fold
SP_138 | 2026-05-27 | All Browsers | - | Desktops | P1 | All 3 Steps --> For Desktops, the entire section has been scaled down to 75% in order to fit it in the viewport of all desktop screens but due to this, the readability of the content & icons in the steps have gotten affected, their unsual scaled down view looks odd and inconsistent with the final result - "Here are 4 Recommended Cards for You" | https://loom.com/i/a3367075f36043a3846b21777706e9e1 | - | Bharat | Need Discussion
SP_139 | 2026-05-28 | All Browsers | - | Desktops | P2 | Here Are 4 Recommended Cards for You --> The gap between the card containers is less than required when compared with the design. Also, the grid container has more than neccessary left & right margin from the design. Due to this, the card container shadow effects are overlapping on top of each other. Please check the actual vs expected result to fix the issue. | https://www.loom.com/i/e34e0438735d4a32b033827442611bec | https://loom.com/i/bc71c64d717e4194bd458c534a7985ba | Bharat | Need Discussion
SP_140 | 2026-05-28 | All Browsers | - | Desktops | P2 | Screen Readers --> Step 1 (What is your Annual Income?) --> Focus the thumb --> While on 1st bar tick, press left button. The narrator announces "No Income Select" but the thumb remains on the 1st bar tick and user is able to proceed to the next step. User shouldn't be able to have "No Income Selected" | - | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - Now the screen reader no longer announces Zero. But, when on the lowest value - upto 50K and left arrow is pressed to reduce the value further, it doesn't announce "No lower value" like it annouces "No higher value" when we try to go beyond 2 lakhs - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html#
SP_142 | 2026-05-28 | All Browsers | - | Desktops | P1 | Systems between 1201px - 1280px are going to have height around 800-900px. There is a CSS media-query that applies the property min-height: calc(100vh - 120px) because of this, the section's height increases unneccesarily introducing empty space at the bottom. This property needs to be removed. | https://www.loom.com/i/6a6820e58cd8488196a7608b5b0b861c | - | Bharat | Fixed | 29/5/2026 - This property can't be removed because there are systems available where the approximate height is around 700px, so height-based media queries can't be reliably written. Now the section has been vertically center aligned, so this issue should no longer occur. | Need Discussion | 2026-06-02 | 02/06/2026 - Need confirmation from client whether they are okay with how the section appears on systems having the width mentioned in the bug.
SP_143 | 2026-05-28 | All Browsers | Small | Desktops | P2 | Step 1 (What is Your Annual Income?) --> Small font --> Notice how the step's container doesn't have any padding at the bottom as a result, either UI breaks or no gap is visible at the bottom breaking the visual balance | https://www.loom.com/i/674a94a759014859bba53bc915f1e5e4 | - | Bharat | Fixed |  | Reopen | 2026-06-02 | 02/06/2026 - The issue is still the same. The padding on the top & bottom should be consistent but in case of small font the bottom gap goes close to 0 in case of desktops and the UI even breaks as labels go out of the container for screen sizes between 1280px - 1350px - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# https://www.loom.com/i/d47357255835469194c9cf5a4c56ab7a
SP_144 | 2026-05-28 | All Browsers | Default / Large | Tablets / iPads | P2 | For Tablets & iPads, extra gap/empty space observed in case of default & large font for each of the 3 steps on Tablets & iPads. Step 1 - https://www.loom.com/i/105a9893db374f85b4f97f9611ac7b66 Step 2 - https://www.loom.com/i/4511fc684d6b441e99c3fa1b0190078c Step 3 - https://www.loom.com/i/4a7c97941db84c4fa7f5b3e19ec8b8d6 | Step 1 - https://www.loom.com/i/105a9893db374f85b4f97f9611ac7b66 Step 2 - https://www.loom.com/i/4511fc684d6b441e99c3fa1b0190078c Step 3 - https://www.loom.com/i/4a7c97941db84c4fa7f5b3e19ec8b8d6 | - | Bharat | Need Discussion
SP_145 | 2026-05-28 | All Browsers | Default / Small | Mobile Phones | P2 | For Mobile Phones, extra gap/empty space observed in case of default & small font size for each of the 3 steps. Step 1 - https://www.loom.com/i/6b04d7799d2e4efcb413428f70aaa17f Step 2 - https://www.loom.com/i/c1e54d9a42504b2e8a1294c465bbbae2 Step 3 - https://www.loom.com/i/a0f12dba2d5143acb55d91dfcd12c22f | Step 1 - https://www.loom.com/i/6b04d7799d2e4efcb413428f70aaa17f Step 2 - https://www.loom.com/i/c1e54d9a42504b2e8a1294c465bbbae2 Step 3 - https://www.loom.com/i/a0f12dba2d5143acb55d91dfcd12c22f | - | Bharat | Need Discussion
SP_147 | 2026-05-28 | All Browsers | - | Desktops, Tablets / iPads | P2 | The designs of the Icon besides the heading of 1st & 3rd Step are created such that they appear smaller compared to the icon used in the 2nd Step. Step 1 - https://www.loom.com/i/6dd17ce6707743a5acd9b701b5f62426 Step 3 - https://www.loom.com/i/fb312263f25a4c7abc712ff39a9b57e9 | Step 1 - https://www.loom.com/i/6dd17ce6707743a5acd9b701b5f62426 Step 3 - https://www.loom.com/i/fb312263f25a4c7abc712ff39a9b57e9 | - | Phulvinder
SP_148 | 2026-05-28 | All Browsers | - | All Devices | P2 | 3 Credit Card Stack image on the top right needs to be more sharper, without the dummy name - Milan Mathur and also in webp format instead of .png | https://www.loom.com/i/861c04540fc645a8b10abb3383e74817 | - | Phulvinder
SP_150 | 2026-05-28 | Firefox | - | Touch Devices | P3 | FireFox --> Here Are 4 Recommended Cards for You --> The Restart button container at the bottom stutters or jumps in its position when user scrolls up & down the page in case of touch devices on firefox. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQDO_IEy9NJYTaHAYr-oumu5AcmydZn3xdrkodHiU25jNAA?e=MfTSe3 | - | Bharat | Need Discussion | 1/6/2026 - I think It's a browser behaviour and this is coming in alomost all sites
SP_151 | 2026-05-29 | All Browsers | - | All Devices | P2 | Dark Mode --> Next Button, Show me My Card & Restart buttons Fails the 3:1 contrast ratio that each actionable item should maintain from its background. | https://www.loom.com/i/4d669fc4c14d4cb98cecadf201cddcf4 | - | Bharat | Need Discussion
SP_152 | 2026-06-02 | All Browsers | - | Desktops | P2 | Enable scan mode (capslock + space) --> Navigate through the page content using the Up/Down Arrow keys --> Obeserve the content announced by the screen reader. The screen reader announces the hidden "Step count" text located in the top-left corner, even though it is not visible on the screen. This occurs on each step of the flow. | https://www.loom.com/i/afd14873c85f42fa8a75fb6db754608c | - | Bharat
SP_153 | 2026-06-02 | All Browsers | - | All Devices | P3 | Here Are 4 Recommended Cards for You --> Top Pick --> The pop up modal's role attrribute should be a "popup" instead of "tooltip" as it acts as a popup that appears and disappears when the top pick button is expanded or collapsed. It doesn't act as a tooltip that appears/disappears upon hover | https://www.loom.com/i/a8409e92abfe4ddd946be6e2e5cac896 | - | Bharat
SP_154 | 2026-06-02 | All Browsers | - | All Devices | P2 | Here Are 4 Recommended Cards for You --> Top Pick --> The pop up modal's heading should have an <h> tag (whichever fits in the hierarchy) | https://www.loom.com/i/ddaba887530349a78a30ea632d6e138c | - | Bharat
SP_155 | 2026-06-02 | All Browsers | - | Desktops | P2 | Screen Readers --> next button --> Notice where the focus lands when the step changes. Focus goes to the Next button of the new step instead of moving to the beginning of the newly displayed step | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQCDSISahBiFRYljobS1Soz4AVl1kv12Eddq6yLe0eIoOx0?e=TKiLwO | - | Bharat
SP_156 | 2026-06-02 | All Browsers | - | Desktops | P3 | Screen Reader – Incorrect reading order while using down arrow key - i. 1st Step - The Bar labels are announced before the corresponding bars, even though the bars appear before the labels in the visual presentation. ii.) 2nd & 3rd Step - The Previous Step button is initially announced as "button G" instead of its accessible name. The correct button label is announced only after pressing the Down Arrow key again. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBxkbuTWiaXRK4tKB-nEK3qAafCt08U6f_M9CQEkO3Fo9E?e=Dd478t | - | Bharat
SP_157 | 2026-06-02 | Firefox | - | Touch Devices | P3 | Touch Devices --> 2nd & 3rd Step --> Scroll down to get the step almost out of the view port --> Check/Uncheck any input box on the step. Notice how performing an action on the step while it is mostly out of the viewport leads to the page scrolling up. But, when this happens, in firefox, header containers do not appear back and because of this a gap gets observered above the find you perfect card section | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQDTn75jMwi1TY4eAASpbyEwAZQNHDHNW9tXu825QWxuy8Q?e=nv1Fg2 | - | Bharat
SP_158 | 2026-06-02 | All Browsers | - | All Devices | P2 | Here Are 4 Recommended Cards for You --> Clicking or tapping on any of the card container triggers the scroll up to the page top in case the section is considerably out of the viewport. | SBI Card and 24 more pages - Personal - Microsoft​ Edge 2026-06-02 14-52-05.mp4 | - | Bharat
SP_159 | 2026-06-02 | All Browsers | - | Touch Devices | P2 | 1st Step (What is your annual income?) --> The placeholder icon doesn't appear center aligned horizontally because of the extra gap the icon itself has on its left side | https://www.loom.com/i/ddd437249b714c83aff36002eef93d5f | - | Phulvinder
SP_160 | 2026-06-02 | All Browsers | - | All Devices | P2 | 1st Step (What is your annual income?) --> The bar label - " 0 " is not vertically center aligned with the other bar labels for all breakpoints and font sizes (small / md / large) | https://www.loom.com/i/46367e7fda0d4196abba412b65e955f8 | - | Bharat
SP_161 | 2026-06-02 | All Browsers | - | All Devices | P3 | Here Are 4 Recommended Cards for You --> Dark Mode --> Top Pick button --> The focus border outline fails the 3:1 colour contrast ratio with its immediate surrounding colours | https://www.loom.com/i/57b7c840301349da8bb756fa1eace4ac | - | Bharat
SP_162 | 2026-06-02 | All Browsers | - | Tablets / iPads | P2 | Here Are 4 Recommended Cards for You --> The Card Containers are missing their box shadow effect for screen sizes between 767px - 1199px | https://www.loom.com/i/b89e9c796b77476e88e2b13653e6b6ea | - | Bharat
SP_163 | 2026-06-02 | All Browsers | - | All Devices | P2 | Here Are 4 Recommended Cards for You --> The Card Title's font colour have started to fail the expected colour contrast ratio which is 4.5:1 | https://www.loom.com/i/4df06235ecdc469db99326cb9b8f8f85 | - | Bharat
SP_164 | 2026-06-02 | All Browsers | - | Touch Devices | P2 | 1st Step (What is your annual income?) --> Touch Device --> Now if user starts the drag gesture right on top of the bar's thumb, it doesn't shift its position to the direction where it gets dragged. | MicrosoftTeams-video (8).mp4 | - | Bharat

## Sheet1
Defect no | Date | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-06-02 | Desktop | Edge | md | Duplicate "2 Lakh" labels are displayed on the income slider, causing confusion in income range selection. | https://www.loom.com/i/c1b57d9a60494772a7fdb9b70e300ab4 |  | P2 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; "2 Lakh" appears twice on the income slider.
2 | 2026-06-02 | Desktop | Edge | md | Main <h1> heading is visually hidden/invisible on the result page, affecting accessibility and heading hierarchy navigation | https://www.loom.com/share/369bab6683b848bd9a33562a1638e7d1 |  | P2 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; primary H1 heading is not properly visible/accessibly rendered on the result page
3 | 2026-06-02 | Tablet/Mobile Landscape | Edge | md | Menu text and options appear too large in landscape mode after opening the hamburger menu | https://www.loom.com/share/73cf4f3e98d3440291386aa1d3bd1144 |  | P3 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; hamburger menu content appears oversized in landscape view
4 | 2026-06-02 | Tablet/Mobile Landscape | Edge | md | Excessive spacing is visible between "Personal", "Corporate", and "About SBI Card" tabs in the hamburger menu | https://www.loom.com/i/80f7d03e1f7945218a1e10df26eaeed5 |  | P3 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; large gaps between menu tabs affect layout consistency and space utilization
5 | 2026-06-02 | Desktop | Edge | md | Extra spacing/gap is visible between the "NEXT" button text and right arrow icon, causing alignment inconsistency | https://www.loom.com/i/5ffdeb190df04dc1ba488abfbfe0438a |  | P3 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; button text and arrow icon spacing appears uneven
6 | 2026-06-02 | Desktop | Edge | md | NEXT button allows navigation even when no option/category is selected | https://www.loom.com/share/f0a57eed143449cab5b35c1ba5dc412f |  | P2 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; form validation is missing and user can proceed without selecting any option
7 | 2026-06-02 | Desktop | Edge | md | User can proceed to the next page after selecting only one benefit option; minimum required selection count is not enforced | https://www.loom.com/share/ed7cfe46fe2e4e608b6bf85a4ba453df |  | P2 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; flow allows navigation without completing the required number of selections
8 | 2026-06-02 | Desktop | Edge | md | SHOW ME MY CARDS button becomes visible after selecting only one option; button should appear only after selecting the required 3 benefits/options | https://www.loom.com/share/ed7cfe46fe2e4e608b6bf85a4ba453df |  | P2 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; minimum selection validation is not enforced before enabling CTA button
9 | 2026-06-02 | Desktop | Edge | md | Non-selectable "0" value is displayed on the annual income slider. Users cannot select "0", and the first selectable option starts from "Less than 50k", causing confusion and misleading UI behavior. | https://www.loom.com/i/ffa42f924bbb491683f9fca35b434ec6 |  | P3 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; static "0" value is visible on the slider but is not selectable by users.
10 | 2026-06-02 | Desktop | Edge | md | Excessive spacing is visible between the "SHOW ME MY CARDS" button text and the right arrow icon, causing alignment inconsistency and affecting the visual appearance of the CTA button. | https://www.loom.com/i/daa8fc35813342f09dfa3426bfb25453 |  | P3 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; noticeable gap exists between the CTA text and arrow icon within the button.
11 | 2026-06-02 | Desktop | Edge | md | RESTART button contains excessive left and right padding, making the button wider than necessary. The button width does not fit its text content, resulting in inefficient space utilization and visual imbalance. | https://www.loom.com/i/31fedf0b4471430c8f0a06a9aff1829d |  | P3 |  | Open |  |  | Failed | 2026-06-02 | Issue reproduced; RESTART button has excessive horizontal spacing and should be resized to fit the text content more appropriately.