## Sheet1
Defect no | 2026-06-22 | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-06-22 | Desktop | Edge | md | Narrator announces "Partner 1" continously on exclusive parters section | https://www.loom.com/share/97f01709774c493eb8b72e720bbc8814 |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; partner logos do not have unique accessible names, causing Narrator to announce the same label repeatedly.
2 | 2026-06-22 | Desktop | Edge | md | Invalid ARIA role "table" is used on the .pf-kb-wrapper section element. | https://ibb.co/93CQScZM |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; Accessibility Insights reports role="table" is not allowed on the section element.
3 | 2026-06-22 | Desktop | Edge | md | Exclusive Partners carousel is not keyboard accessible because the scrollable region cannot receive keyboard focus. | https://ibb.co/k2LtPssC |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; scrollable carousel is not focusable and cannot be accessed using the keyboard.
4 | 2026-06-22 | Desktop | Edge | md | Multiple text elements have insufficient color contrast and do not meet WCAG AA requirements. | https://ibb.co/1Jw4MFF8 |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; text contrast ratio is 3.36:1, which is below the required 4.5:1 WCAG AA standard.
5 | 2026-06-22 | Desktop | Edge | md | Multiple text elements have insufficient color contrast against the background. | https://ibb.co/CN2td64 |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; text contrast ratio is 3.36:1, which is below the required 4.5:1 WCAG AA standard.
6 | 2026-06-22 | Desktop | Edge | md | Partner carousel cannot be dragged using the mouse. Users can navigate only through the arrow buttons. | https://www.loom.com/share/2ba2515edef546078502f152748ae937 |  | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; carousel does not support mouse drag interaction.
7 | 2026-06-22 | Desktop | Edge | md | Background image appears blurry and low quality compared to the design. | https://www.loom.com/share/347a53bbe23f4ddaa085207963a2867b |  | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; background image quality does not match the design.
8 | 2026-06-22 | Desktop | Edge | md | Top cards appear behind the circle and the depth effect does not match the design. | https://i.ibb.co/5g6QFFKq/2155290114ee.png | https://i.ibb.co/pjLT574r/6816e6f88e69.png | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; card layering and depth effect are inconsistent with the design.
9 | 2026-06-22 | Desktop | Edge | md | T&C Apply text is should be below the "CHOOSE CARDS" button. | https://www.loom.com/i/82042d4ac4bc4ef5b706a93587140ec8 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; T&C Apply text alignment does not match the button alignment.
10 | 2026-06-22 | Mobile | Chrome | md | Page performance score is low (42) and needs improvement. | https://pagespeed.web.dev/analysis/https-navajowhite-crow-447925-hostingersite-com-pf-v1-1-product-family-html/n8ewde52aq?hl=en-US&form_factor=mobile |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; Lighthouse performance score is below the recommended threshold.
11 | 2026-06-22 | Desktop | Edge | md | Narrator announces "Apply Now" for the "Choose Cards" button. | https://www.loom.com/share/def1ce1f635f45d3975edfa4439fa995 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; accessible name announced by Narrator does not match the visible button text.
Product Family – 1 Card Variation:
1 | 2026-06-22 | Desktop | Edge | md | Card corner overlaps into the adjacent content section at 125% browser zoom. | https://www.loom.com/share/dc43e43501994286b97ef0678f0c3f23 |  | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; card border radius overlaps the neighboring section at 125% zoom.
2 | 2026-06-22 | Desktop | Edge | md | Rounded corners of the comparison card are not maintained at 150% zoom. | https://www.loom.com/share/f6e44c1cff88461b975c2ba7ad05e441 |  | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; card border radius disappears at 150% zoom, resulting in sharp corners.
3 | 2026-06-22 | Desktop | Edge | md | Nu HTML Checker reports HTML validation errors on the page. | https://ibb.co/RkFXpXtq |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; Nu HTML Checker identified missing alt attributes on image elements and an invalid ARIA role ("table") applied to a section element.
4 | 2026-06-22 | Desktop | Edge | md | Multiple text elements have insufficient color contrast and do not meet WCAG AA requirements. | https://ibb.co/ynGtK5wT |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; text contrast ratio is 3.36:1, which is below the required 4.5:1 WCAG AA standard.
5 | 2026-06-22 | Desktop | Edge | md | Multiple text elements have insufficient color contrast and do not meet WCAG AA requirements. | https://ibb.co/C3PgvP7H |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; text contrast ratio is 3.36:1, which is below the required 4.5:1 WCAG AA standard.
6 | 2026-06-22 | Mobile | Edge | md | Credit card images are oversized and overlap the banner text on mobile view. | https://ibb.co/cz8cprY |  | P2 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; card images overlap banner content, reducing readability and causing layout inconsistency on mobile devices.
7 | 2026-06-22 | Mobile | Edge | md | QR code image appears blurry and low quality on mobile view. | https://ibb.co/JjrknYCj |  | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; QR code image is not clear and may affect scanability on mobile devices.
8 | 2026-06-22 | Mobile | Edge | md | Excessive empty space is displayed between the card title and joining fee section on mobile view. | https://ibb.co/YBX5Sg2T |  | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; unnecessary whitespace is present between the card title and joining fee information, causing inefficient use of screen space.
9 | 2026-06-22 | Mobile | Edge | md | Exclusive Partners section does not display left and right navigation arrows on mobile view. | https://ibb.co/Pswp2Q8G |  | P3 |  | Open |  |  | Failed | 2026-06-22 | Issue reproduced; carousel navigation arrows are not visible, making partner navigation less discoverable for users.

## Sampreets Findings
Defect no | Date | Browsers | Font Size | Device | Priority | Type | Section | Title | Description | Steps to Reproduce | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Assigned To | Dev Status | Last Fixed On | Dev Remark | Status | Last Tested On | QA Remark
| 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Entire Page | Nu HTML Validator highlights errors | If not everything including warnings, info, at least errors that get highlighted in the nu html validator needs to be addressed - https://validator.unl.edu/ | Nu HTML Validator --> Validate all the product family pages | https://loom.com/i/fd0cec2d597a4307b046ad4909d8be18 | - | Satyam
| 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Aria role Table is not allowed for the pf-kb-wrapper | Either need to remove the aria role attribute or have an appropriate role for the container | Accessibility Checker for web --> Run Fast Check on the website | https://www.loom.com/i/4b3d25e53fb548e59dd9ddfd5bb5a9db | - | Satyam
| 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Credit Card titles fail colour contrast | The credit card titles need to have #0077AF instead of #0094D9 in case of light mode | Key Benefits --> Credit card titles --> colour contrast ratio | https://www.loom.com/i/e2148365527b499c904250347d8c408a | - | Satyam | Fixed | 2026-06-19 | Fixed the contrast issue | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://loom.com/i/18d303e8c7834e4a9777efb99ca4ecde
PF_004 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Features & Benefits | Feature icon images are missing their alt text | Accessibility checker for web throws error for icons are they are images and according to it all images must have an alt text | Accessibility Checker for web --> Run Fast Check on the website | https://www.loom.com/i/faabc9aca2374444ac7a567a5960ace7 | - | Satyam | Fixed | 2026-06-19 | Added the alt tags to all the images icon | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_005 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Each Key Benefit's heading fails the colour contrast | The Key Benefits headings need to have #0077AF instead of #0094D9 in case of light mode | Browser Tools CSS Overview --> Run the overview for the webpage | https://www.loom.com/i/3fc4bd160c4c44e18abab429e93e4e09 | - | Satyam | Fixed | 2026-06-19 | Fixed the contrast issue | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_006 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Entire Page | Fallback font not assigned to some font occurrances | Fallback font neccessary in all font-family properties as it helps the browser to fallback to an acceptable font family instead of random one. | Browser Tools CSS Overview --> Run the overview --> Font Occurrances | https://www.loom.com/i/274cc1f019e1437582f3d80922f124c1 | - | Satyam | Fixed | 2026-06-19 | Attached the proper fallback fonts to all the texts | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_007 | 2026-06-17 | All Browsers | - | All Devices | P3 | Bug | Entire Page | Browser console highlights one JS error | If possible, we can handle and avoid any JS error that appears in the browser console. We can ignore if the error is not impacting any UI or functionality. | Browser Tools --> Console --> JS error | https://loom.com/i/d0cc9fac82f5447183f9b959e690147b | - | Satyam | Fixed | 2026-06-22 | The issue was coming due the loader component, now fixed on every variant. | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_008 | 2026-06-17 | All Browsers | - | Desktops | P3 | Bug | Key Benefits | Apply Now button's arrow icon missing animation on hover | Like other CTA buttons that have arrow icon, the "Apply Now" button's arrow is missing animation effect when hovered on it. | Key Benefits --> Apply Now button --> Hover on the button to check if the arrow icon has the animated hover effect. | https://www.loom.com/i/aec0dcacf8ed47c18283aea676cc7ac8 | - | Satyam | Fixed | 2026-06-22 | Applied the hover effect on the apply now button of the | Unresolved | 2026-06-23 | 23/06/2026 - The hover effect still not present on the Apply Now button in the build - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_009 | 2026-06-17 | All Browsers | - | All Devices | P2 | Design/Asset | Entire Page | Dummy names on the card face images | Card Faces in the hero section & the 10% discount wrapper have dummy names in the image that need to be removed | Hero section, 10% discount banner --> Card Face --> Dummy Names | https://www.loom.com/i/237ad6c33ef9493bacb954c279fe6c71 | - | Phulvinder
PF_010 | 2026-06-17 | All Browsers | Large | Desktops | P2 | Bug | Features & Benefits | Feature Cards overlap each other when font increased | As per the current dummy content, when font size is increased, the feature cards start to overlap each other for desktops staring 1351px width. | Desktops (1351px & above) --> Features & Benefits --> Feature Cards --> Increase font size --> Notice how they overlap with each other. | https://www.loom.com/i/915a8ba6fc2841229600496b6129f25b | - | Satyam
PF_011 | 2026-06-17 | All Browsers | - | Desktops | P3 | Suggestion | Features & Benefits | Absolute postion feature cards not strong to hold length content | Not in favour of feature cards having absolute position instead of fixed layout in case of desktops as it possesses a high risk of their position shifting or breaking the UI in case slightly lengthy content needs to authored in them instead of short lines. | Desktops --> Features & Benefits --> Feature Cards --> Increase the content and notice their position shifiting and in some cases overlapping on each other. | https://loom.com/i/9df37d9e78d442e59272963911dbfe77 | - | Arun
PF_012 | 2026-06-17 | All Browsers | Large | Desktops | P2 | Bug | Features & Benefits | Top Feature cards get too close to the section heading | As per the current dummy content, when font size is increased, the top features cards go too close to the section heading for desktops having 1351px width and above | Desktops (1351px & above) --> Features & Benefits --> Feature Cards --> Increase font size --> Notice how the top feature cards go too close to the section heading | https://www.loom.com/i/ef30445198d94eb68b6ddcaae35ba17c | - | Satyam
PF_013 | 2026-06-17 | All Browsers | - | Tablets, Desktops | P2 | Bug | 10% Discount Banner | T&C Apply font doesn't adjust its size when font increased or decreased | For devices starting 768px and above, the font size of the T&C apply doesn't adjust as user increases or decreases it from the accessibility bar | Tablets & Desktops --> 10% Discount Banner --> T&C Apply --> Increase / Decrease font size --> Notice how the font size doesn't adjust | https://www.loom.com/i/6165e2ed87114267800bda4e04cf7405 | - | Satyam | Fixed | 2026-06-19 | Removed the static px and inserted the rem prop. | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_014 | 2026-06-17 | All Browsers | - | All Devices | P3 | Need Confirmation | Header | Limited Period Offer UI broken for tablets & mobile phones | Limited offer wrap was discard and replaced with marquee, do we need to have it in the product family page? If yes, its UI is broken for mobile & tablet devices. It's height is too narrow, left & right gap appears for devices starting 640px - 768px, its content goes to next line starting 768px. If this wrapper is not needed then needs to be removed/replaced with marquee | Tablets & Mobile Phones --> Header --> Limited Period Offer Wrapper --> Notice how the wrapper gets gap from left & right & | Mobile Phones - https://www.loom.com/i/5b10e26f2fb54eeeb41bad9be680cf2a Mobile Phones (640px - 786px) - https://www.loom.com/i/d164954cafab41c3a82eba7f5674efc3 Tablets - https://www.loom.com/i/c0d0e13103f242e3b5d46de5616c5742 | https://loom.com/i/a3878703f374431cb510d4c53784f47c | Arun
PF_015 | 2026-06-17 | All Browsers | Lg & Default | Desktops | P2 | Bug | Hero Section | Less or no gap between Card Stack image & the card price right above | The gap between the card stack image & the card pricing text right above needs to be the same as it is between the banner headings above. But for desktop, it gets reduced in case of default font size or close to zero in case of large font. | Desktops --> Hero Section --> Notice the gap above the card stack image when font size increased or in default mode | https://www.loom.com/i/cad078f4312d4865945e16d826eea872 | https://www.loom.com/i/84990a4fb1ff4a919d763104a0bcddbe | Satyam | Fixed | 2026-06-19 | Added the gap between the elements | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://www.loom.com/i/a0c2b09923b64b25b2dc83da0a57e3f3
PF_016 | 2026-06-17 | All Browsers | - | Mobile Phones | P3 | Suggestion | SBI Card Presents | Selected card tab should only show the respective card | Respective card tab should only show the card whose tab is selected. Or instead we could have used the slider in the Discover our cards section on the home page instead of having tabs | Mobile Phones --> SBI Card Presents Section | https://www.loom.com/i/69d082e4b8ff4cfdae66f0ce6b3e210c | https://loom.com/i/640f4f168d8b42a6a315be0b1b0bad5b | Arun
PF_017 | 2026-06-17 | All Browsers | - | Mobile Phones | P2 | Need Confirmation | SBI Card Presents | Family cards wrapper doesn't cover the entire available space | In case of mobile phones with larger widths (landscape modes or foldable devices) the wrapper's width remains the same as it is in case of smaller screens and doesn't adjust size or layout according to the avaiable space | Mobile Phones --> SBI Card Presents Section --> Notice the empty spaces on the left & right side in case of larger width mobile phones | https://www.loom.com/i/a0581c1b999c400ea97312d75b4eab6e | - | Arun
PF_018 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | SBI Card Presents | Card CTA buttons get wrapped to next line breaking the UI | Client doesn't prefer the CTA labels going to the next line and increasing the height in turn | Tablets --> SBI Card Presents Section --> CTA Buttons | https://www.loom.com/i/630d2e78f71040928106555573da6176 | - | Satyam | Fixed | 2026-06-22 | Fixed the issue now the button lables are not getting shofted to next line.
PF_019 | 2026-06-17 | All Browsers | - | Tablets | P3 | Suggestion | SBI Card Presents | 3 card wrapper gets congested within the available space | As followed on the home page, for tablet devices, we can set the wrapper to show 2 cards in a single slide and add slider to swipe and show the remaining card/s | Tablets --> SBI Card Presents Section --> Notice how the card containers get congested | https://www.loom.com/i/55ec45d2d51c4e8b80c8f0f57e32a62d | https://www.loom.com/i/f13c00dfafa44564a9304bcca978527a | Arun
PF_020 | 2026-06-17 | All Browsers | - | Mobile Phones | P2 | Bug | Features & Benefits | Features container doesn't cover the entire available space | In case of mobile phones with larger widths (landscape modes or foldable devices) the features container width remains the same as it is in case of smaller screens and doesn't adjust size or layout according to the avaiable space | Mobile Phones --> Features & Benefits --> Notice the empty spaces on the left & right side in case of larger width mobile phones | https://www.loom.com/i/53905605cc444b61a343b5627af3f8ed | - | Satyam
PF_021 | 2026-06-17 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | All section do not follow the page left-right page margin that header & footer follow | Need confirmation whether we again need to ignore the left-right page margin not being followed by the sections. | All Devices --> Left right page margin for each section in accordance with the header & footer | https://www.loom.com/i/1122dcfeffec4d739be3b6c33529e7e0 | - | Arun
PF_022 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | Key Benefits | Card's Apply Now button get wrapped to next line breaking the UI | Client doesn't prefer the CTA labels going to the next line and increasing the height in turn | Tablets --> Key Benefits Section --> Apply Now Button | https://www.loom.com/i/3ea6aa6a03a349feab3a4c9362aadad7 | - | Satyam | Fixed | 2026-06-22 | Fixed the issue now the button lables are not getting shofted to next line.
PF_023 | 2026-06-17 | All Browsers |  | Tablets | P2 | Suggestion | Key Benefits | Card header container gets congested in tablet layout | For small & medium size tablets, not much width available for the contents of the card header container, therefore they get too close together, card title gets wrapped into multiple lines breaking the card names readability flow. | Tablets --> Key Benefits Section --> Card Container header layout. | https://www.loom.com/i/c66e65a075e94bff89eafd3fc3292add | - | Arun
PF_024 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | Key Benefits | Card header container UI breaks in case of lengthy card title | For small & medium size tablets, length card title in the column header container has a chance of breaking its UI | Tablets --> Key Benefits Section --> Enter a lengthy card title in the container --> Notice how the UI breaks. | https://www.loom.com/i/564bc203b7d2452e92a14ee9753b4f7e | - | Satyam | Fixed | 2026-06-22 | Issue fixed, now if the title is lengthy, it will automatically go to next line
PF_025 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Section background image shifts, breaks UI & inconsistent behaviour while scrolling | Compare the background image behaviour while scrolling with the other section backgrounds - i.) It appears as if instead of normally scrolling up or down, it is going underneath the next section. ii.) It shifts its position on real devices when page is scrolled up or down. iii.) It breaks the section's UI when scrolling down the page slowing from all the way to the top in one go. | All Devices --> SBI Card Presents Section --> Background Image --> Notice its behaviour while scrolling | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQCJQNJgAIXcQZMwY7BIoQzXAT-ZZjl7J_FsnutNDXILfaY?e=aBUavy | - | Satyam | Fixed | 2026-06-23 | Image behaviour is fixed now
PF_026 | 2026-06-17 | All Browsers | - | All Devices | P3 | Need Confirmation | Our Exclusive Partners | The Parner logo swiper should or shouldn't auto scroll? | Need confirmation whether the partner logo swiper should have auto-scroll behaviour or not. Currently it remains stationary | All Devices --> Our Exclusive Partners slider | https://www.loom.com/i/c70462df57584ff3b7e12df2f1ab5831 | - | Arun
PF_027 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | Our Exclusive Partners | The logo swiper doesn't slide using touch gesture | In case of mobile devices, the swiper slides through swipe gesture but not in case of tablet devices | Tablets --> Out Exclusive Partners Slider --> Try sliding the swiper using touch gesture | https://www.loom.com/i/7a3b36fb57df47ae9e494202cac7f235 | - | Satyam | Fixed | 2026-06-19 | Working on all deviced as expected. Fixed the tab size. | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_028 | 2026-06-17 | All Browsers | - | Mobile Phones | P2 | Bug | Key Benefits | Gap between the column header container & Welcome benefits container | In case of mobile devices, a gap is observed between the column header container & Welcome Benefits container which doesn't match with the design | Mobile Phones --> Key Benefits --> Gap below the column header container | https://www.loom.com/i/6e651cbf75e74da09a07b219300f89b6 | https://www.loom.com/i/ca42f1f9fa484540a3a62484a13d9829 | Satyam | Fixed | 2026-06-19 | Gap removed between the header and content | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://loom.com/i/7730cf77afc642b88f204b7b9fd50f7d
PF_029 | 2026-06-17 | All Browsers | - | All Devices | P2 | Bug | Entire Page | Skip to main content not functional | Clicking on skip to main content button doesn't skip to the main section of the page | Skip to main content --> Click --> Notice if the page skips to the main section | https://www.loom.com/i/da7e688f0e484f99a53bfadf254cba5b | - | Satyam | Fixed | 2026-06-19 | Fixed the behaviour | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_030 | 2026-06-17 | All Browsers | - | All Devices | P1 | Bug | Entire Page | Breadcrumb is missing for the page | Breadcrumb was decided to be present on all pages. But is missing on product family pages | Check if the breadcrumb is present below the header | https://www.loom.com/i/16a0bbc06d3046a68ccc041100de03ae | - | Satyam | Fixed | 2026-06-22 | Added the breadcrumb on every variant | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_031 | 2026-06-17 | All Browsers | - | Desktops | P2 | Bug | SBI Card Presents | Key Benefit bullet point icons do not stay vertically center aligned with the sentence | If a solution possible that ensures the icons used as bullet points always appear vertically center aligned for all devices, it should be implemented. Currently the vertical alignment with the sentence if off in case of desktops and especially in case of large font | SBI Card Presents --> Bullet points icons --> Notice their vertical alignment with their sentence | https://www.loom.com/i/f101631a6fbb41b3b4cf85bbd49a8c1d | - | Sachin
PF_032 | 2026-06-17 | All Browsers | - | Tablets | P2 | Bug | SBI Card Presents | Card Container UI breaks in case of lengthy content | The card container width doesn't get distributed equally in case the card names or bullet points get lengthy or have length variations between them which results in UI breaking | Tablets --> SBI Card Presents --> Enter lengthy & short credit card names --> Notice how the UI behaves. | https://www.loom.com/i/c595b8f833be4cd39a91e4ca08ee3950 | - | Satyam | Fixed | 2026-06-22 | Issue is fixed the content fits in well even with th increased lenth and also the height remains consistenet for all cards making sure the UI does not breaks
PF_033 | 2026-06-17 | All Browsers | - | Desktops | P2 | Bug | SBI Card Presents | Card Container height & position breaks in case of lengthy content | The card container's height & position doesn't remain consistent when length content gets entered as card title or bullet point | Desktops --> SBI Card Presents --> Enter lengthy & short credit card names --> Notice the card container heights & positions | https://www.loom.com/i/cd7aad1f4a1641f28f0d6d70665c3378 | - | Satyam | Fixed | 2026-06-19 | Fixed the layout such that now the height of all the cards will consistently grow with the growing content | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://loom.com/i/2626359e740b4dd2bdd23659ae34e25f
PF_034 | 2026-06-17 | All Browsers | - | Tablets | P3 | Bug | Hero Section | Banner sub heading has a chance to overlap the QR code | In case a lengthier sub heading is authored, it has a chance to get overlapped by the QR code on the left | Tablets --> Hero Section --> Banner sub heading --> Author lengthy content | https://www.loom.com/i/e02cc8a751b5490fb6d6bbc8bf9902e2 | - | Satyam | Fixed | 2026-06-22 | Issue is fixed and now the content is not overlapping the qr.
PF_035 | 2026-06-17 | All Browsers | - | All Devices | P3 | Bug | Hero Section | Banner heading - subheading has a chance to overlap with the card stack image | For all devices, in case lengthier content is authored, the heading & sub-heading has a chance to go beneath the card stack due to the absolute position of the card stack instead of having a fixed layout. | Hero Section --> Add lengthier banner heading & sub heading | https://www.loom.com/i/846c81da2dba49e8961251c2372a2709 | - | Satyam | Need Discussion | 2026-06-23 | In the design the image is statically placed at the middle and does not chnages the position dynamically this will have to a fixed length and everything else will be adjusted accordingly.
PF_036 | 2026-06-17 | All Browsers | - | Desktops | P3 | Need Confirmation | SBI Card Presents | The Earn heading & description supposed to have less width? | Need confirmation whether the Earn Heading & Description present on top of the SBI Card Presents section is supposed to have lesser width | SBI Card Presents --> Earn Heading & Description | https://www.loom.com/i/6229b3efcc87486ab7b23f787c67993b | - | Satyam
PF_037 | 2026-06-17 | All Browsers | - | All Devices | P3 | Bug | Key Benefits | The card container UI breaks in case Joining Fee setence goes lengthy | For all devices, enter a lengthier Joining Fee sentence and notice how the card container content starts to break the UI | Key Benefits --> Enter lengthier card Joining Fees sentence --> Notice how the UI breaks. | https://www.loom.com/i/b6a8954f7b614254bb40cb00230e97e8 | - | Satyam | Fixed | 2026-06-22 | Layout is fixed now such that it can expand and contarcat according to the length of the sentence.
PF_038 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P3 | Need Confirmation | Hero Section | QR code container won't fit in case it's content increased. | Need confirmation whether the static content currently put up in the QR code container would be the max that is to be authored in it as it has a chance to go out of the container in case content increased any further | Hero Section --> QR Code --> Increase the heading & disclaimer content in the QR container --> Notice if it goes out of its parent container UI. | https://www.loom.com/i/9f76d267902641468bb1638ee171862f | - | Arun
PF_039 | 2026-06-18 | All Browsers | - | Desktops | P3 | Need Confirmation | Features & Benefits | Increased length of T&C has a chance to overlap above the image above | Need confirmation whether the Features & Benefits T&C is not going to be lengthier that it currently is. If gets twice or thrice it currently is, it has a chance to overlap the image above and if not, will surely start to cover the gap given between itself and the image. | Features & Benefits --> T&C --> Enter a lengthier T&C and notice if it starts to overlap the image above or cover the gap between itself & the image. | https://www.loom.com/i/43bfc2767cde45f8a37d5448f6812495 | - | Arun
PF_040 | 2026-06-18 | All Browsers | - | Desktops | P3 | Need Confirmation | Features & Benefits | Increased length of T&C would lead to increased number of lines | Need confirmation whether the Features & Benefits T&C is supposed to have shorter width the the available space in case of mobile phones as it may lead to more lines that required in case T&C gets lengthier. | Mobile Phones --> Features & Benefits --> Enter a lengthier T&C statement. | https://www.loom.com/i/350a306e47cf410a8ef0dbc83f5adf9b | - | Arun
PF_041 | 2026-06-18 | All Browsers | - | Mobile Phones | P3 | Need Confirmation | Assistance Made Simple | Vertical position mis-alignment between each title's descriptions | Need confirmation whether it is okay for the description below each title to not be vertically aligned just due to the length difference of the titles. Because, this is the same way it is on the catalogue page | Mobile Phones --> Assistance Made Simple --> Notice the vertical position consistency of the description under each title. | https://www.loom.com/i/87185e0ee8494296b38fffe7d6d97f46 | - | Arun
PF_042 | 2026-06-18 | All Browsers | - | Mobile Phones | P3 | Need Confirmation | Hero Section | Hero section Banner title font size less than section heading | Need confirmation whether it is okay for the Hero section banner title being <h1> of the page to be slightly lesser in size in comparison to normal section headings | Mobile Phones --> Hero section --> Compare the size of the Banner title with the section headings | https://www.loom.com/i/363d2b88d90440a3bbb163e646142b2d | - | Arun
PF_043 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | Page has not main content & sectional landmarks declared | Need confirmation whether this page needs main content & sectional landmarks for better accessibility of sections through D shortcut for blind users or it should again be ignored just like the rest of the pages | Entire Page --> Screen Readers --> The page has not main content & section landmarks | - | - | Arun
PF_044 | 2026-06-18 | All Browsers | - | All Devices | P2 | Need Confirmation | Entire Page | Inconsistent left & right padding for each section | Need confirmation if it is okay for the sections to not have same left & right padding. Currently they have different left & right paddings like - 20px, 18px, 16px & 12px | Entire Page --> Inspect the left & right padding of each section | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAcWlkLD_SGRJ7Z8ckJlom2ARdEfT_X9fIYMPjDzQe6oew?e=eqcTKD | - | Arun
PF_045 | 2026-06-18 | All Browsers | - | Mobile Phones | P2 | Bug | SBI Card Presents | Current state of the tab button doesn't get announced. | In case of mobile phones, the card tabs present are annouced as buttons but the state of each button - whether it is selected/active or not is not annouced when focused on it | SBI Card Presents --> Card Tab buttons --> Check if their current state is annouced when in focus | https://www.loom.com/i/e549aedf45b249108adf9deec9d27e4b | - | Sachin
PF_046 | 2026-06-18 | All Browsers | - | Desktops | P3 | Need Confirmation | Hero Section | QR code container would disappear when screen zoomed till 200-400% no desktop | Need confirmation whether the QR code is an essential content or just an alternate content. Because, it is not present in mobile layouts and when desktop users zoom in, mobile layout gets followed due to which QR code disappears. If it is an essential content that should be available for all desktop users then it would be considered loss of information | Desktops --> Hero Section --> Zoom in till 200% --> Notice the QR code disappearing | https://loom.com/i/d28c2b8dde4a4fec8bcd72a908426d7c | - | Arun
PF_047 | 2026-06-18 | All Browsers | - | All Devices | P3 | Suggestion | Entire Page | Levels of the bullet points get annouced even when they are not nested | For all the bullet points on the entire page, if they are not going to have nesting within them, they do not need have their level announced. It's not a failure but it adds to audio noise and gives the user impression that there is a nested hierarchy of bullet points even when there isn't one | Entire Page --> Screen Readers --> All bullet points --> Notice how their level is annouced even when they are not nested | - | - | Satyam
PF_048 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Features & Benefits | Screen readers do not follow the visual order while scanning feature cards | In case of desktops, when narrator scans and annouces the feature cards, it doesn't follow the visual order in which the feature cards appear on the desktop layout. Instead, it follows the same visual order that the feature cards follow in case of mobile layout. If this is the case then the feature card visual sequence should be the same as it is in mobile layout. | Desktops --> Screen Readers --> Feature Cards --> Notice the sequence of the feature cards followed while narrating them. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQA2Ftnsh9OmRKEp51ulbB_MAYmmBw8KXJE0jVznvlNxPig?e=eDkVe1 | - | Sachin
PF_049 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | While focus on Apply Now CTA, it annouces info apart from the focus CTA | When focus lands on any of the Apply Now CTA in the key benefits container, instead of only annoucing the role, label & context of the particular CTA, it starts to annouce extra information not exactly related to the element in focus. | Desktops --> Screen Readers --> Apply Now CTA --> Notice the annoucement when Apply Now CTA in focus | - | - | Satyam
PF_050 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Same info annouced multiple times when focus on Table column header | When focus lands on any of the column header and notice how the same information is getting annouced multiple times. | Desktops --> Screen Readers --> Get the focus on column header | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQChWF3zbPSKRaS3w8K0j_nQAVHiTZzi5DTqVx0SXg3hTx0?e=ZMbCFn | - | Satyam
PF_051 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Blind user doesn't get the column (card name) & row (Benefit) context on cell focus | When screen reader focuses on each cell using ctrl + alt + arrow keys, the context of it doesn't get announced - for which card this cell is about & which benefit category does it come under. Due to this, user only gets to hear the benefits but doesn't get to know they are related to which card and which benefit category. | Desktops --> Screen Readers --> Focus on the table --> Get focus on each cell using ctrl + alt + arrow keys | https://www.loom.com/i/d503d99d6459490fa272d85e544cd6c6 | - | Satyam
PF_052 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Contraints while trying to move up & down the table cells | In a table, usually user is able to move up & down the rows using ctrl + alt + up or down arrow key but in this case, user can only move up and down the rows when focus is on the very first cell of each row | Desktops --> Screen Readers --> Keep the focus on any row cell apart from the 1st one --> Try moving up & down the row using ctrl + alt + up / down button | https://loom.com/i/5068493943364a68a610a5cb4a95409f | - | Satyam
PF_053 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Unable to traverse through table cells using NVDA screen reader | Case when NVDA screen reader is being used, even when focus is on the table, user remains unable to navigate through table cells using ctrl + alt + up or down arrow key | Desktops --> NVDA screen reader --> Focus on the table --> Try to focus table cells using ctrl + alt + up or down arrow key | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAQ5r21FUoNQJXvWFOyEx2zAY-IIUhi9Zht8lcxxvUojYk?e=yqoJFl | - | Satyam | Fixed | 2026-06-19 | I have added shadow to the complete outer container of the component. Although other than variant with 1 card it might appear a bit different because the first row will have bottom shadow overlapped on the next row if applied on individual rows. | Unresolved | 2026-06-23 | 23/06/2026 - Issue is related to NVDA screen reader not being able to traverse through the table but the dev remark mentions container shadow effect.
PF_054 | 2026-06-18 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Entire column header content annouced while scanning each table cell | In NVDA Scan Mode, navigating table through up & down arrow keys, the screen reader announces the entire column header rather than the relevant card name and benefit type for each cell | Desktops --> NVDA screen reader --> Scan through the table --> Notice the annoucement when each cell is changed. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQDZj3QKqBx9T7s43Gm6lZl5AQ--6zTSRrMgkJGY_o08toQ?e=sohywJ | - | Satyam
PF_055 | 2026-06-18 | All Browsers | - | All Devices | P2 | Need Confirmation | Entire Page | T&C apply can be hyperlinks instead of normal text? | Need confirmation whether any of the T&C apply. text present across the page needs to be hyperlink instead of normal text. If yes, need at least one of them as hyperlink to demonstrate how it is going to be | Entire Page --> Any section that has T&C apply text | https://www.loom.com/i/45abc345837e46abb399a02e30590a5a | - | Arun
PF_056 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Hero Section | Inconsistent font weight of the banner title | In the design, 800 font weight is given for the hero section banner title in case of mobile layout but 700 font weight given in case of desktop layout. Need confirmation which font weight needs to be followed. Currently 800 is being followed for all layouts | Hero Section --> Banner Title --> Font weight | https://www.loom.com/i/78eb56307c76439d8c7ec8398c54ac3c | https://www.loom.com/i/d551dd2c9de8483dbe708b2ab601950f | Satyam
PF_057 | 2026-06-18 | All Browsers | - | All Devices | P3 | Bug | Hero Section | Price text font weight needs to be increased to match with design | In the design, the price text font weight is 500 but on the webpage, 400 is used | Hero Section --> Price Text --> Font weight | https://www.loom.com/i/b7f7e035daaf469aa8c76cf1d6a17127 | https://www.loom.com/i/3c58f7bc22bb4a95aac958c4120e4a6e | Satyam | Fixed | 2026-06-23 | Added the correct font weight
PF_058 | 2026-06-18 | All Browsers | - | All Devices | P3 | Bug | Hero Section | QR code TnC text font family mis-match | In the design, Roboto is used as font family for QR Code TnC text instead of Roboto Condensed | Hero Section --> QR Code --> TnC --> Font Family | https://www.loom.com/i/7e81b21be3cd41379cd1c8fa2525ebe4 | https://www.loom.com/i/544562af1cbf4e2180f1e4dbce4d0825 | Satyam | Fixed | 2026-06-23 | Added the correct font family
PF_059 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | Formats other then .webp used for images all across the page | As per the latest communication, it was decided all image assets to be used on the page would be in .webp format instead of .jpg or .png format but almost all the images are still not in .webp format. Need confirmation whether it is alright or needs to be addressed | Entire Page --> Image Assets --> Image format | - | - | Arun
PF_060 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P2 | Bug | SBI Card Presents | "Earn upto" heading takes more than one line | As per the design, the "Earn upto" heading takes a single line only but on the webpage its width is reduced in order for it to take more than 1 line | Desktop --> SBI Card Presents --> Earn Upto Heading --> Notice how it takes more than 1 line | https://www.loom.com/i/d6b7b7c75861456daad4925f6562ae29 | https://www.loom.com/i/0d81f6b322ca475fa812d388d196bfcc | Satyam | Fixed | 2026-06-19 | Adjusted the width of the heading, now coming in a single line as provided in the design | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://loom.com/i/2a403bab6b5446c4adad9a18d0d075ba
PF_061 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P3 | Bug | SBI Card Presents | Less gap between "Earn upto" heading & its description | While observing the design for desktop layout, the "Earn upto" title & description appear to be having sufficient gap between them but when reviewing the same on the webpage, the appear slightly more close to each other | Desktop --> SBI Card Presents --> Notice the gap between Earn upto heading & its description | https://www.loom.com/i/5b96dd8953c54d1fa7ee31898b9cecb6 | https://www.loom.com/i/a9296565728b4ce98c04de7d91a3c61a | Satyam | Fixed | 2026-06-23 | I have introduced a gap of 8px above the subheading .
PF_062 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | "Earn upto" heading's description font properties do not match the design | The design has #000000 as font colour. It also has 1.5 line height ratio for the description. On the web, #222222 colour is used and 1.1 line height is given. It also as 16px size but on the web it has 2rem size which amounts to 18px it can be reduced to 1.8 rem to amount to 16px. Also, on the webpage, a &nbsp space character is present due to which the 2nd line appears to be again starting from the left even though the sentence is actually center aligned | SBI Card Presents --> "Earn Upto" description --> Match the font properties with the design | https://www.loom.com/i/d4761538f0594a2aa9c9cfda51c6fff3 | https://www.loom.com/i/f24fbbb3453d41e5bf29d920944deb2c | Satyam | Fixed | 2026-06-19 | Color of the text changed to #000000, alignment is fixed, lineheight is fixed to 1.5. About font-size its already discussed basis issue (73,74). | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://loom.com/i/2a403bab6b5446c4adad9a18d0d075ba
PF_063 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | SBI Card Presents | "Earn upto" heading & the amount span font size inconsistent | Need confirmation about that standard font size needs to be followed for "Earn upto" heading as well as the amount <span> inside it. In case of desktop, on the webpage it is - 25.2px that is 2.8rem, 36px for amount span that is 4rem but the design has - 20px & 28px for amount span. Whereas, for mobile phones, webpage has - 22.5px that is 3rem, 30px that is 4rem for amount and the design has 24px & 33px for amount. The design itself is not consistent as it uses increased font size for smaller layout and decreased size for larger layouts | SBI Card Presents --> "Earn Upto" description --> Match the font size properties with the design | https://www.loom.com/i/7ca55b4eb597448e9c7cc9954a7fb2d3 | https://loom.com/i/5be14458aee04813804591c74dc3a3af | Arun
PF_064 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Hero Section | Gap & Position mismatch between banner title, sub-title & card price | Need a confirmation on the exact gap that should be maintained between title, sub-title & the card price text because the way design is made, unable to determine what exact gap should be maintained | Hero Section --> Notice gaps between banner title, sub title & card price text | https://www.loom.com/i/53209b4972e94c2cb66164a9cdfa469c | https://www.loom.com/i/c7600968531a4f5ab0b49e73c2487900 | Arun
PF_065 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Less gap between "Earn upto" description & SBI Card Present heading | Compare to design, the gap between "Earn upto" description & the SBI Card Presents heading is less | SBI Card Presents --> Gap between "Earn upto" description & the "SBI Card Presents" heading | https://www.loom.com/i/14da81340e3344ceb93562810ab05074 | https://www.loom.com/i/618d606182794efab20a5c7f0b936f9c | Satyam | Fixed | 2026-06-19 | I have added the gap to be 40px. In the design it was 35px but was not making any significant difference in appearance hence increased it to 40px. | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://loom.com/i/fa700430380d4bf0b08a5dd2a2097e57
PF_066 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Card Face shadow effect missing | As shown in the design, the card face shadow effect is missing behind the card face images | SBI Card Presents --> Notice how the card face shadow effect is missing. | https://www.loom.com/i/acfe1a1e36ba44d584eec632afff753d | https://www.loom.com/i/f28f655cc87946e89462e8e25c02385b | Satyam | Fixed | 2026-06-19 | Added the shadow | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_067 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Card Face shadow effect missing | Even if the card face shadow effect is not present for this section in the design, it is required to prevent white & black card faces to merge with light or dark backgrounds. | SBI Card Presents --> Notice how the card face shadow effect is missing. | https://www.loom.com/i/aa93dcf6e96c4a22addc5d4a7b045daf | - | Satyam | Fixed | 2026-06-19 | Added the shadow | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html
PF_068 | 2026-06-18 | All Browsers | - | All Devices | P2 | Design/Asset | Our Exclusive Partners | Brand logos not having the same size | Each brand's logo should appear in the same size as others | Our Exclusive Partners --> Notice the brand logo size differences | https://www.loom.com/i/e9f440a0b23b4a8ca505dc8ced208d04 | - | Phulvinder
PF_069 | 2026-06-18 | All Browsers | - | All Devices | P3 | Need Confirmation | Key Benefits | Font weight of the Key Benefits Bullet points inconsistent | Need confirmation what font weight should be used for the bullet points in the key benefits table as in the design it is 400 in case of mobile layout & 500 in case of desktop layout and on the webpage it is 400 for all layouts | Key Benefits --> Bullet points --> Notice the font weight & compare with the design | https://www.loom.com/i/7a0194180f6647aea6896d145f877536 | https://loom.com/i/2fe5a291f09845ed84335d6c8db9e243 | Arun
PF_070 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Benefits Heading gradience do not match with the design | The gradience used on the current version differs from the one used in the design. Also, we need to inform if the same gradience is not possible on all varients. | Key Benefits --> Benefits Heading --> Notice the gradience effect and compare with the design | https://www.loom.com/i/2a484ee4254e44469b58e79e52a4818e | https://www.loom.com/i/5ec80e6f1ab5492ab09be13bd4e809a4 | Satyam | Fixed | 2026-06-19 | Gradient property fixed along with opacity and required shadows and borders | Resolved | 2026-06-23 | 23/06/2026 - Issue resolved on - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html https://loom.com/i/c2b061ad62a644e0a63545c0d7eb3473
PF_071 | 2026-06-18 | All Browsers | - | Tablets, Desktops | P2 | Bug | Features & Benefits | Foreground image missing blur and has incorrect layering | The foreground image circumference instead of going beneath the feature cards, should be on top of it and should have the blur effect as shown in the design. | Features & Benefits --> Foreground Image z-index & blur effect (match it with the design) | https://www.loom.com/i/379ab7bbbfb44afcab5cd1f47be67620 | https://www.loom.com/i/4322e9ced8074ddaaee7a85d7e607c76 | Satyam | Need Discussion | 2026-06-19 | This is actually an image along with the content within to be used directly in the context. So a matching asset will be required from the design team for the same.
PF_072 | 2026-06-18 | All Browsers | - | All Devices | P3 | Bug | Key Benefits | Joining Fee font weight mis-match with the design | The design has 500 font weight where as webpage has 600 font weight | Key Benefits --> Joining Fee --> Font weight | https://www.loom.com/i/9944cf5bb2174c4a8314cd5d6e4e7f64 | https://www.loom.com/i/5ada8057e90342d1b190c98fffc896cd | Satyam | Fixed | 2026-06-23 | Font weight corrcted and matched with the design
PF_073 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | SBI Card Presents | Card Name font size mis-match with the design | In the design the card name font size is 24px but on the webpage it comes around 27.5px | SBI Card Presents --> Card Name Font --> Check the font size | https://www.loom.com/i/43d5074ded9e4caaa32a037e68775248 | https://www.loom.com/i/9d9009f298f84936822702273679ca98 | Satyam | Not a Bug | 2026-06-19 | Discussed with Sampreet and Sachin; this is not a bug but the standard behavior followed across the project. Font sizes are defined in rem and scale based on the configured root font size (8px for Desktop: 1025–1350px and Mobile: 381–767px), allowing them to adjust according to device width. | Resolved | 2026-06-23 | 23/06/2026 - As per the dev remark and the discussion held on call (shared with Arun sir on mail) closing this issue.
PF_074 | 2026-06-18 | All Browsers | - | All Devices | P2 | Bug | Features & Benefits | Feature Card Heading & description font size mis-match | In the design, for feature title font size is 16px for all layouts & 12px for description but on the webpage it is around 18px & 15px | Features & Benefits --> Feature Card --> Title & description font size | https://www.loom.com/i/faa9b998714c4855a18c2704ec869ac4 | https://www.loom.com/i/976aa0fb056545dfaf2524640fb877f5 | Satyam | Not a Bug | 2026-06-19 | Discussed with Sampreet and Sachin; this is not a bug but the standard behavior followed across the project. Font sizes are defined in rem and scale based on the configured root font size (8px for Desktop: 1025–1350px and Mobile: 381–767px), allowing them to adjust according to device width. | Resolved | 2026-06-23 | 23/06/2026 - As per the dev remark and the discussion held on call (shared with Arun sir on mail) closing this issue.
PF_075 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Key Benefits container is missing shadow effect | The design has a shadow effect on the whole key benefits container. The same is missing on the webpage | Key Benefits --> Container's shadow effect | https://www.loom.com/i/8c69e53b4406477f8c09606e5753abd8 | https://www.loom.com/i/0d471821115847de8d06e25745f30a36 | Satyam | Fixed | 2026-06-19 | Fixed: refer to issue 53 it is the same thing. | Unresolved | 2026-06-23 | 23/06/2026 - Shadow effect still not found on any variant - https://navajowhite-crow-447925.hostingersite.com/pf-v1.1/product-family-4cards.html Also, in case of desktop layout, instead of having a single shadow for the table, the design has separate shadows for column header container & for the rest of the table container. https://loom.com/i/8fb354f8729343628e1dd8006cb4686b
PF_076 | 2026-06-19 | All Browsers | - | All Devices | P3 | Bug | Features & Benefits | Feature card container border radius mis-match | The border radius in the design is 6px but on the webpage it is 12px | Features & Benefits --> Feature Card --> Notice & compare the border radius with the design | https://www.loom.com/i/8799cdcd7b6c41f4ac2c5f217969312b | https://www.loom.com/i/0240d8ae699c41c7866672b2365ae25c | Satyam | Fixed | 2026-06-23 | Border radius changed to 6px as per design
PF_077 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Slightly less gap between card title, joining fee & CTA | When comparing the design & webpage, side by side, the card name, joining fee & CTA appear too close together in comparison to the design because there it seems they are slightly more apart | Key Benefits --> Card Name, Joining Fee & CTA --> | https://www.loom.com/i/cfae2932dead46959ce1d6799ac7d271 | https://www.loom.com/i/6efecd0a56764a13b1e997db34f100c2 | Satyam | Fixed | 2026-06-23 | Increased the gap from 10px -> 16px
PF_078 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Benefits list items font colour mis-match | The font colour in the design is #222222 but the one used on the webpage is #333 | Key Benefits --> Bullet points --> Notice the font colour & match it with the design | https://www.loom.com/i/6a9bf243f84f427dbdcdfe26cc30a9c0 | https://www.loom.com/i/5b4de51602474968afcbf740b2bf5f31 | Satyam | Fixed | 2026-06-23 | color is changed to #222222
PF_079 | 2026-06-19 | All Browsers | - | All Devices | P2 | Design/Asset | Assistance Made Simple | 2 White patches observed in the background image used | Around the left & right side of the heading "Assistance Made Simple", white patches can be observed that is part of the background image used | Assistance made simple --> Section background image --> observe the white patches within the background image | https://www.loom.com/i/bf8b009880654f589775fb17ce932cc0 | https://loom.com/i/256c2515c6d0491c8b940d590b04887d | Phulvinder
PF_080 | 2026-06-19 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | Dedicated background images for all 3 breakpoints | Need confirmation whether we need dedicated sectional background images for mobile, tablets & desktop for the following sections - Hero Section (tablet), Features & Benefits (tablet), SBI Card Presents, Key Benefits, Discount Banner (tablet), Discount Assistance Section. Because, same resolution image gets cropped according to the available space and doesn't exactly give the look our design has | Entire Page --> All Sections --> Notice the sectional background image for each break-points and determine whether their essence is lost in different breakpoints | - | - | Arun
PF_081 | 2026-06-19 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | The entire container including column header - background colour mis-match | In the design, #FAFDFF colour is used as the background fill but on the webpage - white color is used | Key Benefits --> Table container's background color --> Notice the difference between the design & web | https://www.loom.com/i/b28ce01355594702b3e6aff091b186e0 | https://www.loom.com/i/90cdf9692ec24e0b8b6d31ed8d6cbb87 | Satyam | Fixed | 2026-06-23 | color of the bg is changed to #FAFDFF
PF_082 | 2026-06-22 | All Browsers | - | All Devices | P3 | Need Confirmation | Key Benefits | The column border color & opacity mis-match from the design | The border colour is #DDD with 100% opacity on the webpage for all layouts but in the design it is #D2D2D2 with 100% opacity for desktops & #D2D5DB with 60% opacity in mobile layouts. Need confirmation which border with what opacity to follow for all layouts | Key Benefits --> Notice the colour & opacity of the column borders and compare with the design (Also inconsistent in the design as well) | https://www.loom.com/i/a09495eaa32844ae96e0401d736d5039 | https://www.loom.com/i/1052ace3811b46338ce2c29f152380df | Arun
PF_083 | 2026-06-22 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Benefit Headings are missing border & box-shadow effect | As shown in the design, the benefits heading have #0052A4 and a box shadow effect but the same is missing on the webpage | Key Benefits --> Benefits Heading --> Compare the headings with the design | https://www.loom.com/i/50b540a92e77420d88a506c00ebaf248 | https://www.loom.com/i/d5f496acd81941b794523a160ccbcd4d | Satyam | Fixed | 2026-06-23 | Fixed the UI and matched with the design
PF_084 | 2026-06-22 | All Browsers | - | Mobile Phones | P2 | Bug | Key Benefits | Comparison table in mobile layout breaks with long unbroken words | In case of mobile phones, in order to fit a lengthy word including in the content, the column width increases making the columns uneven in width and unaligned with the column header. Plus, if all 3 of them have lengthy words, the UI has a chance to break | Mobile Phones --> Key Benefits --> Enter lengthy words in the columns as content --> Notice how the column width gets affected and UI breaks | https://www.loom.com/i/a9d7fa035cec4c48b3aa6004969db582 | - | Satyam | Fixed | 2026-06-23 | Corrected the behaviour, now if the words are long then the will get adjusted one below another and height will increase and width will not be affected.
PF_085 | 2026-06-22 | All Browsers | - | All Devices | P3 | Need Confirmation | Features & Benefits | Feature Card background fill mis-match | Need confirmation for the final value of the background fill because in the design it is #F4FDFF with 90% opacity in desktop layout & #F4FDFF with 100% opacity in mobile layout. Currently #F4FDFF with 90% is used for all layouts in the webpage | Features & Benefits --> Feature Card --> Notice different opacities used in the design | https://www.loom.com/i/1f55192b9f0d4f7784008954462f7cbc | https://www.loom.com/i/5372bef316364c9ca4dd0f997349a745 | Arun
PF_086 | 2026-06-22 | All Browsers | - | All Devices | P3 | Bug | SBI Card Presents | Card shadow effect partially hidden by parent container | Compare the card container shadow effect in the webpage & the design. In the design the box shadow spreads 34px from all sides but not on webpage because of their parent container ending before the shadow could spread. This makes it look like the top & bottom side doesn't have any shadow effect. | SBI Card Presents --> Card Container --> Check the shadow effect spread and compare with the design | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQANMONyx7L_QIay9og515yZASZCLoQn2gb2wtqSJYhuH3A?e=OvEzgS | https://www.loom.com/i/b9b027d1887241eda6ca3aa3f3afd68e | Satyam
PF_087 | 2026-06-22 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | Joining Fee content missing a line break | In the design, the joining fee content always has a line break but on the webpage, in case of 2 card variant the line break is missing | 2 Card Variant --> Key Benefits --> Joining Fee --> Compare with the design & notice if line break is missing | https://www.loom.com/i/4eb345deced24a528fe2b0883b104404 | https://www.loom.com/i/50962075d211414daeab5c35c328d9d5 | Satyam
PF_088 | 2026-06-22 | All Browsers | - | All Devices | P3 | Bug | Our Exclusive Partners | Card shadow effect partially hidden by parent container | Compare the logo wrapper shadow effect in the webpage & the design. In the design the box shadow spreads 24px from all sides but not on webpage because of their parent container ending before the shadow could spread. This makes it look like the top & bottom side doesn't have any shadow effect. | Our Exclusive Partners --> Card Container --> Check the shadow effect spread and compare with the design | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAz9dgPmtg0TbVSAvruKga9AVWVrwjBDS5N7QjlFiG-NiI?e=MVQcph | https://www.loom.com/i/57bb4f46efe346909b1f7b565f85b33d | Satyam | Fixed | 2026-06-23 | Made the container such that it accomodates the shadow within
PF_089 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | Hero Section | A slight gap observed above between Hero Section & Header | Notice the slight gapping that now appears right above the hero section in case of desktops | Hero Section --> Check the white gap right above the hero section (between header & the section | https://www.loom.com/i/6690316650254c509bae116643b65340 | - | Satyam
PF_090 | 2026-06-22 | All Browsers | - | All Devices | P2 | Design/Asset | SBI Card Presents | 2 White patches observed in the background image used | Around the left & right side of the heading "SBI Card Presents", white patches can be observed that is part of the background image used. | SBI Card Presents --> Section background image --> observe the white patches within the background image | https://www.loom.com/i/bf8b009880654f589775fb17ce932cc0 | https://loom.com/i/256c2515c6d0491c8b940d590b04887d | Phulvinder
PF_091 | 2026-06-22 | All Browsers | - | Desktops | P3 | Need Confirmation | Key Benefits | Each Benefit heading has its own gradience instead of combined | Need confirmation if this should be addressed - In case of Single Card Variant, the benefits headings have separate gradiance stops instead of combined gradiance stop. | Single Card Variant --> Key Benefits --> Benefit Headings --> Notice the difference between gradience effect on the webpage & the design | https://www.loom.com/i/cb56f1e91ba345ac8f86cc6dac9f0490 | https://www.loom.com/i/b94abb3ce1bb47f582c4411b64a3da4b | Arun
PF_092 | 2026-06-22 | All Browsers | - | All Devices | P2 | Bug | Entire Page | Trust & Safety, Browser Compatility concerns on lighthouse | Lighhouse browser extension highlights 4 trust & safety issues and 1 browser compatibility issue. | All Variants --> Run the lighthouse extention on Chrome/Edge Browser --> Notice the trust & safety + browser compatibility issues under Best Practices section | https://www.loom.com/i/e8ee74cf9fcb4ba8923d55c611a8ef50 | - | Satyam
PF_093 | 2026-06-22 | All Browsers | - | All Devices | P3 | Bug | Key Benefits | Card Face shadow effect radius goes out of the container as well | In the Key Benefits section in case of single varient card, due to the way single variant is designed, the card face shadow effect goes out of the container as well (in all layouts) | Single Card Variant --> Key Benefits --> Card Face --> Shadow effect --> Notice how the shadow effect gets outside the card container too. | https://www.loom.com/i/b93e89b8ac44417483273f305120b79f | - | Satyam | Fixed | 2026-06-23 | Adjusted the box shadow
PF_094 | 2026-06-22 | All Browsers | - | All Devices | P2 | Bug | Key Benefits | For single card variant - column separtor line required or not? | Need confirmation for the Key Benefits section's column separator gridline in case of single variant. Whether it is required or not because in the design it is skipped and on the webpage it is present | Single Card Variant --> Key Benefits --> Notice how the column separator gridline is not present in the design but visible in the webpage | https://www.loom.com/i/56b50e46d24a48f486000f953e82f52f | https://www.loom.com/i/4f3178ce0eae40f58fedb7f03a964dc1 | Arun
PF_095 | 2026-06-22 | All Browsers | - | All Devices | P2 | Bug | 10% Discount Banner | The Choose Card CTA label font color & font-size mis-match | In the design, the font color for the choose cards CTA is - #302B6C and default desktop font size is 18px and mobile layout is 13px whereas on the webpage - the default desktop size is 12.4px & 11.2px for mobile phones | 10% Discount Banner --> Choose Card label --> Notice the font size & colour of the label | https://www.loom.com/i/4b9b6d4737de4e2eb54ad28393f4e4ce | https://www.loom.com/i/9358f7577732461a9711ff86007a946f | Satyam | Fixed | 2026-06-22 | Font styling matched with the design.
PF_096 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | 10% Discount Banner | Lesser left margin gap within the banner before the content | In the design's desktop layout, we notice quite some margin gap before the start of the content whereas on the webpage that gap is quite less compare to the design | 10% Discount Banner --> Notice the left margin gap within the banner before the content and compare with the design | https://www.loom.com/i/5cff609b659a4da6b7518c8c43af0703 | https://www.loom.com/i/fc7337ca838f4190a8b21abd52ea436c | Satyam | Fixed | 2026-06-22 | The top margin is given to be 30px while on the left and right is 70px
PF_097 | 2026-06-22 | All Browsers | - | Desktops | P2 | Design/Asset | 10% Discount Banner | Card + Trolley image's shadow effect doesn't match the design | In the design, the shadow effect of the card + trolley image is more prominent and noticeable as compared to the image used in the webpage | 10% Discount Banner --> Notice the card + trolley image shadow effect | https://www.loom.com/i/cc862d6528dd4e66bd89512bb242bcfa | https://www.loom.com/i/720fff76bd094cb5b4fbc0f31ec31fa7 | Phulvinder
PF_098 | 2026-06-22 | All Browsers | - | Mobile Phones | P2 | Bug | 10% Discount Banner | Card + Trolley image appears smaller compared to design | In case of mobile phones, the card + trolley image appears larger in the design as compared to the actual webpage | 10% Discount Banner --> Notice the card + trolley image size difference between the design & the webpage | https://www.loom.com/i/52f35ef8bc0049dbacca8f737132d2d0 | https://www.loom.com/i/d66197b9c6d74f03833001b2ce148566 | Satyam
PF_099 | 2026-06-22 | All Browsers | - | Mobile Phones | P2 | Bug | 10% Discount Banner | The Banner title font size mis-match from the design (base mobile screen) | In case of mobile phones, the Banner titile's default font size is 26px but in the design it is 24px. As discussed, only checked the base screensize | Mobile Phones --> 10% Discount Banner --> Banner Title --> Notice the font size difference of the title in the design & the webpage | https://www.loom.com/i/af63bbfc436440cbaf956c5a22a19ee1 | https://www.loom.com/i/4200b66574d04704b1559a1f501bc566 | Satyam | Fixed | 2026-06-22 | Fontsize is fixed
PF_100 | 2026-06-22 | All Browsers | - | All Devices | P3 | Suggestion | 10% Discount Banner | The Banner sub-title should also have 1.2 line height | In case the banner sub-title takes more than 1 line due to lengthy content, it should have 1.2 line height for it to appear more readable and less congested | 10% Discount Banner --> Sub title --> Enter a lengthy sub-title, notice the line height of it | https://www.loom.com/i/c9eced52684b4878bcb9f5a4c5cbfb68 | - | Satyam
PF_101 | 2026-06-22 | All Browsers | - | All Devices | P3 | Suggestion | 10% Discount Banner | Should we have slight more gap between the Title & Sub title? | In case the title & sub-title content that gets finalized is lengthy, they will take more than 1 line. In such case, the gap between the title & sub-title should always be more than the line gap within themselves. | 10% Discount Banner -->Title & Sub-title --> Enter a lengthy sub-title, notice the line height of the content and compare it with the gap between the title & sub - title | https://www.loom.com/i/6d8b15ad714e4c0fb612247c1012e5b7 | - | Satyam
PF_102 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | A lengthy benefit heading breaks bottom gap of the container | In case of Single Card Variant, the column header UI breaks if the title is lengthy as it doesn't fit within the available header height. We have benefits that are as long as "Complimentary Priority Pass Membership". We need to ensure that the benefit container accomodates lengthy benefit titles without breaking the UI | Single Card Variant --> Key Benefits --> Column Header --> Enter a lengthy benefit as heading --> Notice how the lengthy content doesn't fit within the available header height | https://www.loom.com/i/23d335f0ab3a45da8b550f934c89628d | - | Satyam
PF_103 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Benefit headings larger than others create uneven header height | In case of Single Card Variant - Desktops, if by chance one of the Benefit takes more than 1 line, it increases the height of the column header making it uneven with others | Single Card Variant --> Key Benefits --> Increase font size --> Notice how one of the benefit takes the next line --> Increasing the column height making it uneven with others | https://www.loom.com/i/097f9977fb5e4a3e825d3a9cdfc2b840 | - | Satyam
PF_104 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Card column container UI breaks in case of lengthy card name | Enter a real card name like "BANK OF MAHARASHTRA SBI CARD ELITE" and notice how the text goes out of the column and image as well goes out on the right side | Single Card Variant --> Key Benefits --> Lengthy Card Name --> Notice how the content of the cell goes out of the container if lengthy card title is entered | https://www.loom.com/i/7ab11dabd4f643f89d447c6c64f652a2 https://www.loom.com/i/5941cee08335489ab25d8b1a98642c53 | - | Satyam
PF_105 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Card Name & Joining Fee go apart in case of lengthy Key Benefit | In case of Single Card Variant - Desktops, if a key benefit bullet point is lengthy, it increases the height of the container & as a result the card name & joining fee go apart | Single Card Variant --> Key Benefits --> Enter a lengthy key benefit bullet point --> Notice the gap between the card name & the joining fee | https://www.loom.com/i/f4899a457ac7430f9ebf3f2164603f94 | - | Satyam
PF_106 | 2026-06-22 | All Browsers | - | Mobile Phones | P2 | Bug | Hero Section | Card Face Image overlaps on top of the Banner Title & Sub Title | In case of Single Card Variant - Mobile Phones, the card face directly overlaps on top of the hero banner title & sub-title | Single Card Variant --> Mobile Phones --> Hero Section --> Notice how the card face image overlaps above the text content | https://www.loom.com/i/dc01a1d008d5409a9b5884e8524233fb | https://www.loom.com/i/9cf448a5038848e0a5ddddd227b2a15f | Satyam | Fixed | 2026-06-23 | Adjusted the image below the text such that it does not overlaps even if the font size is inceased.
PF_107 | 2026-06-22 | All Browsers | - | Mobile Phones | P2 | Bug | Key Benefits | Card Title/ Joining Fee get overlapped by the card face image | In case of Single Card Variant - Mobile Phones, the text content in the table header container gets overlapped by the card face on the right. Increase the font size in not increase the content to make it happen | Single Card Variant --> Mobile Phones --> Key Benefits --> Notice how when font size is increased or content is increased, the text get overlapped by the card face image | https://www.loom.com/i/dafa0e395d744aa49d0c7579438618b7 | - | Satyam | Fixed | 2026-06-23 | Adjusted the content such that it does not distorts the image
PF_108 | 2026-06-22 | All Browsers | - | Mobile Phones | P3 | Suggestion | Key Benefits | Should card text content & image follow the same left & right margin as bullet points ? | The card name, joining fee & the card face are more towards center having more left & right margin gap in comparison to the left right margin bullet points follow | Single Card Variant --> Mobile Phones --> Key Benefits --> Compare the Card Name, joining fee & card face left right margin gaps with the bullet point margins | https://www.loom.com/i/8302d3a8901b483abe8503834d93b220 | - | Satyam
PF_109 | 2026-06-22 | All Browsers | - | All Devices | P2 | Bug | Hero Section | 4 Card Stack image appears smaller in comparison to other variants | In case of 4 Card Variant - The card stack image appears smaller than other card stacks | 4 Card Variant --> Hero Section --> Compare the size of the 4 cards stack image with other card stacks in the variants | https://www.loom.com/i/89bc888e7895454f8a1d46102011b2f5 | https://loom.com/i/9e4c1f2ed570449daf18de9104105b01 | Satyam | Fixed | 2026-06-23 | Increased the image from 320px -> 400px in deviced above 768px
PF_110 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Table's bottom left border not rounded | For 2, 3 & 4 Card Variants in case of desktop mode, the key benefit table's bottom left border needs to be rounded | Key Benefits --> Table --> Bottom left border --> Notice how the border is pointed instead of rounded | https://www.loom.com/i/1bc8cb101d6a4f2b8a29357cbab46175 | - | Satyam | Fixed | 2026-06-23 | Border aligned with the design
PF_111 | 2026-06-22 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Card Title / Joining Fee content get cropped | In case of 4 Card Variant - Desktops, when card names are lengthy and font size is increased, the left most card content gets cropped from the start | 4 Card Variant --> Desktops --> Key Benefits --> Enter lengthy card names --> Increase font size --> Notice the left most card content getting cropped from the start | https://www.loom.com/i/8b36fe3664c241f598caa5b80bd53328 | - | Satyam | Fixed | 2026-06-23 | Corrcted the issue such that cards content does not overflows on increasing the length of the content
PF_112 | 2026-06-22 | All Browsers | - | Mobile Phones | P2 | Bug | SBI Card Presents | Card tab sticky container position doesn't adjust after closing get app & offer marquee | As the card tab container sticks to the top, if user closes the top 2 header containers - Get App & Offer marquee then the sticky container doesn't adjust its position leave a gap between the header & itself | Mobile Phones --> Scroll down till the SBI Card Present Section --> Close the Get App & Offer containers in the header --> Notice if the sticky container position adjusts | https://www.loom.com/i/097e1ca1efa64c08817da49efe8b45f9 | - | Sachin | Fixed | 2026-06-23 | This is fixed with js logic and recalculated the header height on somethinging changing on header.
PF_113 | 2026-06-22 | All Browsers | - | Mobile Phones | P3 | Need Confirmation | SBI Card Presents | No indication of 4th tab being present in the sticky container | Need confirmation whether we need an indicator of more tabs being present when all cannot be shown within the available width. In case of 4 Card Variant - Mobile Phones, the 3 tabs appear on the screen as per its width but the 4th one remains out of the view and user doesn't know it is there until he accidentally or casually scrolls horizontally. | 4 Card Variant --> Mobile Phones --> SBI Card Presents --> Notice the last tab completely hidden from the screen making the user unknown about it existing | https://www.loom.com/i/cce21e57207040b6b9447bbb1517fbed | - | Arun
PF_114 | 2026-06-22 | All Browsers | - | Mobile Phones | P3 | Bug | SBI Card Presents | Select Tab doesn't change as user scrolls down | As user scrolls down, the selected tab doesn't change and instead remains whatever was clicked. This makes the current card on the screen different then the selected tab | Mobile Phones --> SBI Card Presents --> Select Any Tab --> Scroll down to a different card --> Notice how the selected tab and the card on the screen now mis-match | https://www.loom.com/i/d4f74f4e5f7a4f78971f2c6094c39c9f | - | Sachin
PF_116 | 2026-06-23 | All Browsers | - | All Devices | P3 | Bug | 10% Discount Banner | Choose Cards button needs to have correct aria-lable | Although current dummy content is used for aria-label. However, felt like it shouldn't be something totally different from what the element actually is. It currently annouced "Apply Now" instead of "Choose Cards" | 10% Discount Banner --> Choose Cards Button --> Notice how it annouces "Apply Now" button instead of "Choose Cards" button | https://www.loom.com/i/4211ee20ffa141019e98f9716dcf8712 | - | Satyam | Fixed | 2026-06-23 | Added the correct aria lable : "Choose and compare available credit cards"
PF_117 | 2026-06-23 | All Browsers | - | Touch Devices | P2 | Bug | Key Benefits | Too much gap between Card Name & Joining Fee | In case of Single Card Variant - Mobile & Tablet layout, the card name & the joining fee text below have quite some gap between them. This gap only increases if the font size is reduced. | Key Benefits --> Mobile & Tablet --> Notice the gap between the card name & the joining fee text | https://www.loom.com/i/6edc7e559b7a476fa115642a28dc6398 | - | Satyam
PF_118 | 2026-06-23 | All Browsers | - | Mobile Phones | P2 | Bug | Entire Page | The entire page gets horizontal scroll in 4 card variant mobile layout | Small width mobile devices get horizontal scroll when check using browser tool's device emulation | 4 Card Variant --> Mobile Phones --> Notice how the entire page gets horizontal scroll in case of smalls width mobile devices. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQDu23NecK9ORL4_eEWd7m6gAZMXPrK2jxmsL77-mGkUYrM?e=hREnW9 | - | Satyam
PF_119 | 2026-06-23 | All Browsers | - | Mobile Phones | P2 | Bug | SBI Card Presents | Card Tab sticking container doesn't adjust its position when font increased/decreased | When in mobile phone layout, if the card tab container gets sticky and then user increases the font size, the sticky container goes beneath the header container and if font size is decreased, a gap between the container & the header appears | Mobile Phones --> SBI Card Presents --> Scroll down to get the container to stick --> Increase & decrease the font size --> Notice how the sticky container position doesn't adjust with respect to the header | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBxs4ItZ0i6Q5MqlweYjhifAceFixscXQpAlqzbcM6X3pE?e=mq8U0o | - | Satyam
PF_120 | 2026-06-23 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | The last row container has unwanted border radius at its top right corner | The last row container of the key benefits table doesn't need a rounded border at the top corners as per the design | Desktops --> Key Benefits --> Notice the top right corner radius of the last row container | https://www.loom.com/i/8298530445f54e0ea789c1edde5ebf56 | https://www.loom.com/i/f142234a7b514efc9a3e168505e4e1d5 | Satyam | Fixed | 2026-06-23 | corrected the border radius across the header
PF_121 | 2026-06-23 | All Browsers | - | Desktops | P2 | Bug | Key Benefits | Column header's bottom corners & top row's top corners are not rounded | As per the design, in case of desktop layout, the column header container has all 4 corners rounded including the bottom 2 and the top row's top corners are rounded. But on the webpage, these corners are sharp not rounded | Desktops --> Key Benefits --> Notice the column header containe & top row container corners are not rounded as they are in the design | https://www.loom.com/i/ee7cc87f9b8d410a985f5f55c26027e8 | https://www.loom.com/i/653dde5b0f5244f8ace60f8d07fce3f6 | Satyam | Fixed | 2026-06-23 | corrected the border radius across the header
PF_122 | 2026-06-23 | All Browsers | - | All Devices | P3 | Need Confirmation | 10% Discount Banner | Discount Banner section background color for dark theme | Need confirmation for the background color to be used in case of dark theme for the 10% Discount Banner. Same colour for assistance made simple & discout banner is used on webpage whereas design has different colour | Dark Theme Variant --> 10% Discount Banner --> Notice the section background colour being different | https://www.loom.com/i/47fbc14069db4622a84864a799ea3297 | https://www.loom.com/i/ef87e2f5d28e469bb6921ffa172f7540 | Arun
PF_123 | 2026-06-23 | All Browsers | - | All Devices | P2 | Need Confirmation | Entire Page | Sectional headings - font colour mis-match | As per the design, the dark theme variant has this colour - #4DC6FF for sectional headings and the webpage has the default dark mode font color - #0094D9 | Dark Theme Variant --> Notice the color of all section headings and compare them with the design | https://www.loom.com/i/190ee4ee752f411aa9471f1a302f6261 | https://loom.com/i/5fd3b500f4d644acb3751eadb608b75b | Arun
PF_124 | 2026-06-23 | All Browsers | - | All Devices | P3 | Need Confirmation | Entire Page | Containers remain white filled even in dark theme | In case of product details page, we changed the containers' background fill to dark colour. But in case of Need confirmation whether the containers are okay to remain white even in dark theme for the product family | Dark Theme Variant --> Notice how containers of all sections remain white filled even in dark theme. | https://www.loom.com/i/f909c10635de47c6af9859ed6c71a7ce | - | Arun
PF_125 | 2026-06-23 | All Browsers | - | All Devices | P3 | Need Confirmation | Key Benefits | How should the single variant layout handle more than 4 Key Benefits ? | In case of Single Card Variant - Desktop layout, if more than 4 Key Benefits are to be authored for the card, need confirmation on how would the current layout handle it | Single Card Variant --> Key Benefits --> Desktop Layout --> Notice how the current layout can only handle up to 3 key benefits | https://www.loom.com/i/f598530a03624f87a76c980a132c37f1 | - | Arun
PF_126 | 2026-06-23 | All Browsers | - | All Devices | P3 | Bug | Key Benefits | The bullets of the list items do not remain vertically aligned at the center | Notice how the bullets go slightly downwards vertically in comparison to their sentence when font size is smallest and go slightly up when font size is largest. | Key Benefits --> Increase the font size --> Notice the bullet dot's vertical alignment with the sentence --> Decrease the font size --> Notice the alignment again | small font - https://www.loom.com/i/85d45f2f00c04189a68be4177a63e4d0 large font - https://www.loom.com/i/36ce34f4f9614adcb1942bb56c850daf | - | Satyam
PF_127 | 2026-06-23 | All Browsers | - | All Devices | P3 | Suggestion | Entire Page | Spliting heading tags breaking the heading narration into 2 headings | The section heading is currently split across multiple heading elements to achieve different visual styles. As a result, screen readers announce them as separate headings (e.g., "Heading level 2 – SBI Card Presents" followed by "Heading level 3 – Reliance SBI Card"), due to this the heading does get annouced together in one go. | Entire Page --> Sectional headings --> Notice how the headings get announced separately due to separate HTML tags | https://www.loom.com/i/45c91da0f1cf48ee87d3a731a5ed1c4b | - | Satyam
PF_128 | 2026-06-23 | All Browsers | - | All Devices | P2 | Need Confirmation | Entire Page | Sectional headings fail colour contrast and color mis-match with container headings | As the accessibility checkers cannot determine colour contrast of font that appear directly on image instead of a css background colour, therefore these need to be checked manually on - https://webaim.org/resources/contrastchecker/. The ratio comes around 3:1 instead of 4.5:1. Also, container headings use "#0077AF" to comply with contrast ratio and section headings still use "0094D9 which is different. Need confirmation which color to use. | Entire Page --> Sectional headings --> Notice how the headings color fails the 4.5 colour contrast level and also doesn't match with the container headings that now use "#0077AF" | https://www.loom.com/i/af11d2114fef44aa9de644b9f9273d6f | - | Arun
PF_129 | 2026-06-23 | All Browsers | - | Mobile Phones | P2 | Bug | SBI Card Presents | "Earn Upto" heading has less line height that its description below | In case of Mobile Phones, the "Earn Upto" heading goes in 2 lines. Both the lines appear closer due to 1.1 line height. Whereas the "Earn Upto" description has 1.5 line height which makes it to have more gap between sentences then what it's heading itself has. We can use 1.3 line height for both (in case of mobile phones) | Mobile Phones --> SBI Card Presents --> Notice the line height difference between "Earn Upto" heading & its description | https://www.loom.com/i/46d184fc12ef474780f9dea041e369c4 | https://loom.com/i/5ee64fb2082a42128bd855e2d329cf24 | Satyam