## Sheet1
Defect no | 2026-06-22 | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
Product Family (Default):
1 | 2026-06-17 | Mobile | Edge | md | A white transparent overlay appears above the bottom navigation bar while scrolling the page. | https://ibb.co/qMn8ScqW https://www.loom.com/share/09b9ae288b9847fb80de97c6130fb40f |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; a semi-transparent white layer becomes visible and moves upward during page scroll, affecting the visual appearance of the bottom navigation area.
2 | 2026-06-17 | Mobile | Edge | md | A black overlay layer appears and moves upward while scrolling the page. | https://www.loom.com/share/c596e200436540ab890aa5c4390e3376 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; an unintended black overlay becomes visible during page scroll and shifts upward, affecting the page appearance and user experience.
Product Family – 1 Card Variation:
1 | 2026-06-17 | Mobile | Edge | md | A white transparent overlay appears above the bottom navigation bar while scrolling the page. | https://ibb.co/qMn8ScqW https://www.loom.com/share/09b9ae288b9847fb80de97c6130fb40f |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; a semi-transparent white layer becomes visible and moves upward during page scroll, affecting the visual appearance of the bottom navigation area.
2 | 2026-06-17 | Mobile | Edge | md | A black overlay layer appears and moves upward while scrolling the page. | https://www.loom.com/share/c596e200436540ab890aa5c4390e3376 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; an unintended black overlay becomes visible during page scroll and shifts upward, affecting the page appearance and user experience.
Product Family – 2 Cards Variation:
1 | 2026-06-17 | Desktop | Edge | md | Marquee banner does not span the full available width at 200% zoom in horizontal view. | https://ibb.co/G3T2SFvM |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; gaps appear on the left and right sides of the blue marquee banner at 200% zoom, causing layout inconsistency.
2 | 2026-06-17 | Desktop | Edge | md | Nu HTML Checker reports an invalid ARIA role on the comparison table section. | https://ibb.co/BHN47SYM |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; role="table" is applied to a section element, which is not a valid ARIA role for that element according to HTML validation rules.
3 | 2026-06-17 | Desktop | Edge | md | Invalid ARIA role "table" is used on the section element ".pf-kb-wrapper". | https://ibb.co/qLLRDKCP |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; Accessibility Insights reports that role="table" is not allowed on the section element, resulting in an aria-allowed-role violation.
4 | 2026-06-17 | Desktop | Edge | md | Exclusive Partners carousel is not keyboard accessible because the scrollable region cannot receive keyboard focus. | https://ibb.co/KcMLzXPB |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the scrollable carousel container (.exclusive-partners-logos) is not focusable, preventing keyboard users from accessing and scrolling the content.
5 | 2026-06-17 | Desktop | Edge | md | Multiple text elements have insufficient color contrast and do not meet WCAG AA requirements. | https://ibb.co/NgrThqfy |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; text elements such as the Login label have insufficient contrast against the background and fail WCAG 1.4.3 Contrast (Minimum) requirements.
6 | 2026-06-17 | Desktop | Edge | md | Label-content-name mismatch accessibility issue detected. | https://ibb.co/673M4skS |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the visible label does not match the accessible name announced by assistive technologies, resulting in a WCAG 2.5.3 Label in Name violation.
7 | 2026-06-17 | Desktop | Edge | md | Bottom-left corner border radius is not displayed correctly at 100% browser zoom. | https://ibb.co/WvTYdPD8 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the bottom-left corner appears squared while other corners remain rounded.
8 | 2026-06-17 | Desktop | Edge | md | Bottom-left corner becomes rounded at 150% zoom. | https://www.loom.com/share/eec72d0dd0ce4a5d93d5588c8afdc7e0 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; corner appearance changes at 150% zoom.
9 | 2026-06-17 | Mobile | Edge | md | A white transparent overlay appears above the bottom navigation bar while scrolling the page. | https://ibb.co/qMn8ScqW https://www.loom.com/share/09b9ae288b9847fb80de97c6130fb40f |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; a semi-transparent white layer becomes visible and moves upward during page scroll, affecting the visual appearance of the bottom navigation area.
10 | 2026-06-17 | Mobile | Edge | md | A black overlay layer appears and moves upward while scrolling the page. | https://www.loom.com/share/c596e200436540ab890aa5c4390e3376 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; an unintended black overlay becomes visible during page scroll and shifts upward, affecting the page appearance and user experience.