## Sheet1
Number | Date | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
Product Family (Default):
1 | 2026-06-17 | Desktop | Edge | md | Border is broken at 200% zoom. | https://ibb.co/nshSGc37 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; at 200% zoom, the section border is broken and does not render continuously, resulting in an inconsistent UI appearance.
2 | 2026-06-17 | Desktop | Edge | md | Cards overlap at maximum font size (A+). | https://ibb.co/qHZZMZS |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; when the maximum font size (A+) is applied, the cards overlap with each other, affecting the layout and readability.
3 | 2026-06-17 | Desktop | Edge | md | Exclusive Partners section is not keyboard accessible at 200% zoom. | https://www.loom.com/share/34733cde926c485bad4d0ef6521ce90a |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; at 200% zoom, keyboard focus skips the Exclusive Partners section, preventing users from accessing the carousel using the keyboard.
4 | 2026-06-17 | iPad Mini, iPad Air, Surface Pro 7, | Edge | md | Page does not fit the screen on iPad Mini, iPad Air, Surface Pro 7, | https://ibb.co/3msgg9p5 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; on the iPad Mini, the page does not adapt to the full screen width, causing content to overflow and leaving part of the UI inaccessible on the right side.
Product Family – 1 Card Variation:
1 | 2026-06-17 | Desktop | Edge | md | Button text wraps onto two lines. | https://ibb.co/wNX4SP9J |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the "SEE BENEFITS" button text wraps onto two lines, resulting in an inconsistent button appearance and reduced readability.
2 | 2026-06-17 | Desktop | Edge | md | Table column separator is missing in Dark Mode. | https://ibb.co/C3QGJFpJ |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; in Dark Mode, the vertical separator line between the card details and benefits section is not visible, making the table columns appear merged.
3 | 2026-06-17 | iPad Mini, iPad Air, Surface Pro 7, | Edge | md | Page does not fit the screen on iPad Mini, iPad Air, Surface Pro 7, | https://ibb.co/3msgg9p5 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; on the iPad Mini, the page does not adapt to the full screen width, causing content to overflow and leaving part of the UI inaccessible on the right side.
4 | 2026-06-17 | Desktop | Edge | md | Excessive empty space on the right side of the card section. | https://ibb.co/sJFp0Xf2 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; excessive empty space is displayed on the right side of the card section, resulting in poor space utilization and an unbalanced layout.
5 | 2026-06-17 | Desktop | Edge | md | Image resources failed to load. | https://ibb.co/zVhWXrg0 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; required image resources failed to load due to missing or invalid file paths, resulting in broken images and missing UI elements.
6 | 2026-06-17 | Desktop | Edge | md | Empty link (href) detected. | https://ibb.co/rRjMTKtW |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; one or more links contain an empty href attribute, resulting in non-functional links and poor accessibility.
Product Family – 2 Cards Variation:
1 | 2026-06-17 | Desktop | Edge | md | Image resources failed to load. | https://ibb.co/zVhWXrg0 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; required image resources failed to load due to missing or invalid file paths, resulting in broken images and missing UI elements.
2 | 2026-06-17 | Desktop | Edge | md | Empty link (href) detected. | https://ibb.co/rRjMTKtW |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; one or more links contain an empty href attribute, resulting in non-functional links and poor accessibility.
3 | 2026-06-17 | iPad Mini, iPad Air, Surface Pro 7, | Edge | md | Page does not fit the screen on iPad Mini, iPad Air, Surface Pro 7, | https://ibb.co/3msgg9p5 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; on the iPad Mini, the page does not adapt to the full screen width, causing content to overflow and leaving part of the UI inaccessible on the right side.