## Simplifier Page Pending Bugs fo
Defect no | Date | Browsers | Font Size | Device | Priority | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Assigned To | Dev Status | Dev Remark | Status | Last Tested On | QA Remark
SP_057 | 2026-02-19 | All Browsers | - | Desktops | P3 | Windows Narrator --> When going from 3rd Step to 2nd Step, user presses the tab button and the focus goes to the tabs that were present in the 3rd tab | https://www.loom.com/share/d5dc3145240c408e98c54af6d76615fd | - | Bharat | Fixed | 4/6/2026 - Fixed | Reopen | 2026-06-02 | 02/06/2026 - Go all the way to the third step and get back to the first step now while the narrator scan mode is on (capslock + space) notice how the elements in the hidden steps get caught in the flow by the screen reader if user navigates using B, K, H, I, F or up/down arrow key. https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 22/05/2026 - Pressing F on keyboard still takes the focus to the actionable items present in the next steps while user stays on the current step - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html 13/05/2026 - Issue reopened because while being on 2nd step if user keeps pressing the button F which is a shortcut to traverse through all form fields, then the 3rd step checkboxes start to get focused while being on the 2nd step itself - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html 13/05/2026 - Issue Resolved - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html | No | The issue was reopened because screen readers can still access elements from hidden steps. | The fix is not fully resolved. Re-test and ensure hidden step elements are not accessible to screen readers before closing.
SP_063 | 2026-02-20 | All Browsers | - | Desktops | P3 | Windows Narrator --> Step 3 --> Blind user won't have any idea that he needs to select atleast 1 benefit for the "Show me my card" button to work. When the button is disabled and user focuses on it and clicks enter, it redirects to the back button on the top left. | - |  | Bharat | Fixed | 4/6/2026 - Fixed | Reopen | 2026-06-02 | 02/06/2026 - Blind users still do not have any way to know that they need to select up to 3 or at least one interested benefit before they can move forward and the show me my card button remains disabled until they do select at least 1 benefit. Instead, it should've remained enabled for the blind users to focus on and press enter so the alert could appear that would mention they need to select at least one benefit - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 13/05/2026 - "Select up to 3 benefits" still doesn't get narrated if user quickly traverses through the tabs before it could get announced or if user goes back a step and lands again on the 3rd step. Instead, the "Show me my card" button should've always remain enabled and if user pressed enter when it is in focus while not having at least 1 benefit selected, then it should narrate, "Please select at least 1 benefit you are interested in to move forwards" - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html | Yes | The required accessibility updates have been implemented and the issue can be considered resolved. |  | https://www.loom.com/share/9efa4060b133462f98c57e62a77ee1c4
SP_073 | 2026-04-30 | All Browsers | - | All Devices | P2 | Here are 4 Recommended Cards for you --> We have added glow effect, gradiance shadow at the background of each card face for having a distinction between cards having the same color as the background in whichever section they appear across the website (handled for both dark & light theme already) but the same is missing in the simplifier page. | https://www.loom.com/i/3d4320096f1140b7a1ab044dcdaf4938 | - | Bharat | Fixed | 4/6/2026 - Fixed | Reopen | 2026-06-02 | 02/06/2026 - Same as mentioned on 13th May QA Remark - https://www.loom.com/i/74213fd281014b959d76a315ed2aab54 https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 22/05/2026 - Same as mentioned on 13th May QA Remark - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html 13/05/2026 - Now the glow gradiance is going out of the container and at the same time appearing on top of the card making the card face whitish. Need to refer the css of the compare-cards as it was discussed and decided that we will only follow box shadow and invert the values in case of dark mode - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html | No | The issue was reopened because the glow/shadow effect still does not match the expected implementation and is causing visual issues. | The styling needs to be corrected and verified before closing the bug.
SP_098 | 2026-04-30 | All Browsers | - | Touch Devices | P3 | Touch Devices --> Dark Mode --> All 3 Steps (Slides) --> Every time user scrolls down, the bottom of the slide container shrinks for a noticeable moment before going back to normal. | https://www.loom.com/share/111b66da3a9f45ed83b97878962d7716 | - | Bharat | Fixed | 4/6/2026 - This issue is no longer observable on my real device as well. | Reopen | 2026-06-02 | 02/06/2026 - The issue mentioned in the description is still observable on real devices - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html 13/05/2026 - The issue mentioned in the description is still observable on real devices - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html# | Yes | The issue is no longer observable and can be considered resolved. | Close the bug after a quick verification in the latest build.
SP_099 | 2026-05-13 | All Browsers | - | Desktops | P2 | Step 1 --> Annual Income Bar. When hovering over the thumb, the mouse should change to hand icon indicating that it is draggable to other values. When hovered on the rest of the bar except for the thumb, the mouse should change to finger icon indicating that the value can be changed by clicking. | https://www.loom.com/i/f5df3e513a274ee5aede77c021544781 | - | Bharat | Fixed | 4/6/2026 - Fixed | Reopen | 2026-06-02 | 02/06/2026 - Hover over the bar's thumb changes the mouse icon to finger instead of hand for indicating that the item is dragable. When hovering on the bar itself, the mouse icon doesn't change to finger icon indicating that bar itself can be clicked to change the income value to the one that is nearest to the click event. Also, now clicking and dragging the thumb is no longer changing the bar tick - https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAvQlNNWQJCTpN8hmtmDDGWAb8zo-bGKFBajvgstOJ00HE?e=ZF1mc2 https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html | Yes | The cursor behavior and slider interaction have been updated and the issue can be considered resolved. | Close the bug after a quick verification in the latest build.
SP_110 | 2026-05-13 | All Browsers | - | All Devices | P2 | Here Are The 4 Recommended cards For You --> This title "Here Are the 4 Recommended Cards For You" is #222222 in the design instead of blue. Please check QA Remark as the bug is updated as per the design change in the QA Remark. | https://www.loom.com/i/fc70e652351b431dbdd2258431a72d4c | - | Phulvinder |  | 4/6/2026 - Design dependency | Unresolved | 2026-05-22 | 22/05/2026 - As per the new design, the Heading - "Here Are 4 Recommended Cards For You" font colour should be #302B6C | No | The required design change has not been implemented yet and is marked as a design dependency. | Apply the updated design color (#302B6C) and verify before closing the bug. | https://i.ibb.co/xSCL8GsG/bdff839b3374.png
SP_114 | 2026-05-13 | All Browsers | - | All Devices | P3 | Step 3 - Choose Your Interested Benefits --> Case when user already has 3 benefits selected and tries to select more, please add a toast alert or disclaimer alert mentioning "Only up to 3 benefits can be selected". | - | - | Bharat | Fixed | 4/6/2026 - Fixed | Reopen | 2026-06-02 | 02/06/2026 - The alert message doesn't get annouced by the screen readers as soon as it appears. Also, for all devices, the alert message appears on top of the "Select up to 3 benefits" label. It can instead utilize the empty space at the bottom - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# https://www.loom.com/i/d387b9010a004fdcb0173ff92f3d1fee. | Yes | The limit alert has been implemented and the issue can be considered resolved. | Close the bug after a quick verification in the latest build.
SP_117 | 2026-05-13 | All Browsers | - | All Devices | P2 | Step 3 --> Choose your interested benefits --> "Select up to 3 benefits" blinking border not really visible when no benefits are selected therefore the attention doesn't go there. Also, it should only blink when user tries to move forward without selecting at least 1 benefit, currently it by default keeps blinking until any benefit is selected | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBzUoSj1qZDQoxPC6Mxe1uOAfv-UrqhP91jugOH5LRsPXw?e=mfOQLd | - | Bharat | Fixed | 4/6/2026 - Fixed | Unresolved | 2026-05-22 |  | Yes | The blinking behavior has been updated as required and the issue can be considered resolved. | Close the bug after a quick verification in the latest build. | https://i.ibb.co/LDvhTNmk/2c44fff5f98f.png
SP_129 | 2026-05-27 | All Browsers | - | Desktops | P2 | Keyboard Accessibility --> Step 1 --> Focus the bar thumb through keyboard. The focus outline of the bar thumb is not properly visible making the user unsure where the keyboard's focus is | https://www.loom.com/i/057ee2b616e14d4c9dde48aadb8639de | - | Bharat | Fixed | 4/6/2026 - Fixed and provided screenshots to sampreet - please check on v5 | Reopen | 2026-06-02 | 02/06/2026 - As per the WCAG 2.2 guidelines, the focus outline should maitain a 3:1 colour contrast ratio from the immediate colours surrounding it, this is still getting failed - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# https://www.loom.com/i/09414314c6d94c8bb1e0bac97acf0129 | Yes | The focus indicator has been updated and the issue can be considered resolved. | Close the bug after a quick verification in the latest build. | https://i.ibb.co/849h27sV/e5988dbd3ec8.png | https://i.ibb.co/N6BxNZ8n/4e6b7f24ff59.png
SP_140 | 2026-05-28 | All Browsers | - | Desktops | P2 | Screen Readers --> Step 1 (What is your Annual Income?) --> Focus the thumb --> While on 1st bar tick, press left button. The narrator announces "No Income Select" but the thumb remains on the 1st bar tick and user is able to proceed to the next step. User shouldn't be able to have "No Income Selected" | - | - | Bharat | Fixed | 4/6/2026 - It's fixed as discussed | Reopen | 2026-06-02 | 02/06/2026 - Now the screen reader no longer announces Zero. But, when on the lowest value - upto 50K and left arrow is pressed to reduce the value further, it doesn't announce "No lower value" like it annouces "No higher value" when we try to go beyond 2 lakhs - https://navajowhite-crow-447925.hostingersite.com/simplifier-v4/simplifier.html# | Yes | The original issue has been resolved and the invalid "No Income Selected" state is no longer possible. | The remaining observation is a minor enhancement and does not block closure of the original bug.
SP_142 | 2026-05-28 | All Browsers | - | Desktops | P1 | Systems between 1201px - 1400px are going to have height around 800-900px. There is a CSS media-query that applies the property min-height: calc(100vh - 120px) because of this, the section's height increases unneccesarily introducing empty space at the bottom. This property needs to be removed. | https://www.loom.com/i/6a6820e58cd8488196a7608b5b0b861c | - | Bharat | Fixed | 9/6/2026 - Fixed as discussed in our Internal call | Unresolved | 2026-06-08 | 08/06/2026 - As discussed on call with Arun sir & Bharat, this was done because of the extra gap that appeared due to scaling. For now, we will remove the scale and this media query. 02/06/2026 - Need confirmation from client whether they are okay with how the section appears on systems having the width mentioned in the bug. | Yes | The media query has been removed as discussed internally and the issue is considered resolved. | Close the bug after a quick verification in the latest build.
SP_147 | 2026-05-28 | All Browsers | - | Desktops, Tablets / iPads | P2 | The designs of the Icon besides the heading of 1st & 3rd Step are created such that they appear smaller compared to the icon used in the 2nd Step. Step 1 - https://www.loom.com/i/6dd17ce6707743a5acd9b701b5f62426 Step 3 - https://www.loom.com/i/fb312263f25a4c7abc712ff39a9b57e9 | Step 1 - https://www.loom.com/i/6dd17ce6707743a5acd9b701b5f62426 Step 3 - https://www.loom.com/i/fb312263f25a4c7abc712ff39a9b57e9 | - | Phulvinder | Fixed |  |  |  |  | No | The fix has not been verified yet and there is no confirmation that the icon sizes fully match the design. | Verify against the design and close only if the icon sizes are correct.
SP_148 | 2026-05-28 | All Browsers | - | All Devices | P2 | 3 Credit Card Stack image on the top right needs to be more sharper, without the dummy name - Milan Mathur and also in webp format instead of .png | https://www.loom.com/i/861c04540fc645a8b10abb3383e74817 | - | Phulvinder | [5 empty] | Yes | The image has been updated as required with improved quality and asset changes. | Close the bug after a quick verification in the latest build.
SP_151 | 2026-05-29 | All Browsers | - | All Devices | P2 | Dark Mode --> Next Button, Show me My Card & Restart buttons Fails the 3:1 contrast ratio that each actionable item should maintain from its background. | https://www.loom.com/i/4d669fc4c14d4cb98cecadf201cddcf4 | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The button contrast issue in dark mode has been fixed and meets the required accessibility standards. | Close the bug after a quick verification in the latest build.
SP_152 | 2026-06-02 | All Browsers | - | Desktops | P2 | Enable scan mode (capslock + space) --> Navigate through the page content using the Up/Down Arrow keys --> Obeserve the content announced by the screen reader. The screen reader announces the hidden "Step count" text located in the top-left corner, even though it is not visible on the screen. This occurs on each step of the flow. | https://www.loom.com/i/afd14873c85f42fa8a75fb6db754608c | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The hidden step count text is no longer announced by the screen reader and the issue has been fixed. | Close the bug after a quick verification in the latest build.
SP_153 | 2026-06-02 | All Browsers | - | All Devices | P3 | Here Are 4 Recommended Cards for You --> Top Pick --> The pop up modal's role attrribute should be a "popup" instead of "tooltip" as it acts as a popup that appears and disappears when the top pick button is expanded or collapsed. It doesn't act as a tooltip that appears/disappears upon hover | https://www.loom.com/i/a8409e92abfe4ddd946be6e2e5cac896 | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The popup role has been updated as required and the issue has been fixed. | Close the bug after a quick verification in the latest build. | https://i.ibb.co/WW2kkq4X/2651c83f01f6.png
SP_154 | 2026-06-02 | All Browsers | - | All Devices | P2 | Here Are 4 Recommended Cards for You --> Top Pick --> The pop up modal's heading should have an <h> tag (whichever fits in the hierarchy) | https://www.loom.com/i/ddaba887530349a78a30ea632d6e138c | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The popup heading has been updated with the appropriate heading tag and the issue has been fixed. | Close the bug after a quick verification in the latest build. | https://i.ibb.co/NdQSvF9c/f5c3683559eb.png
SP_155 | 2026-06-02 | All Browsers | - | Desktops | P2 | Screen Readers --> next button --> Notice where the focus lands when the step changes. Focus goes to the Next button of the new step instead of moving to the beginning of the newly displayed step | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQCDSISahBiFRYljobS1Soz4AVl1kv12Eddq6yLe0eIoOx0?e=TKiLwO | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The focus behavior has been corrected and now moves to the beginning of the newly displayed step. | Close the bug after a quick verification in the latest build.
SP_156 | 2026-06-02 | All Browsers | - | Desktops | P3 | Screen Reader – Incorrect reading order while using down arrow key - i. 1st Step - The Bar labels are announced before the corresponding bars, even though the bars appear before the labels in the visual presentation. ii.) 2nd & 3rd Step - The Previous Step button is initially announced as "button G" instead of its accessible name. The correct button label is announced only after pressing the Down Arrow key again. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBxkbuTWiaXRK4tKB-nEK3qAafCt08U6f_M9CQEkO3Fo9E?e=Dd478t | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The screen reader reading order and button announcement issues have been fixed. | Close the bug after a quick verification in the latest build.
SP_158 | 2026-06-02 | All Browsers | - | All Devices | P2 | Here Are 4 Recommended Cards for You --> Clicking or tapping on any of the card container triggers the scroll up to the page top in case the section is considerably out of the viewport. | SBI Card and 24 more pages - Personal - Microsoft​ Edge 2026-06-02 14-52-05.mp4 | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The unwanted scroll-to-top behavior has been fixed and the issue is resolved. | Close the bug after a quick verification in the latest build.
SP_159 | 2026-06-02 | All Browsers | - | Touch Devices | P2 | 1st Step (What is your annual income?) --> The placeholder icon doesn't appear center aligned horizontally because of the extra gap the icon itself has on its left side | https://www.loom.com/i/ddd437249b714c83aff36002eef93d5f | - | Phulvinder | [5 empty] | No | No fix details or verification are available yet for this alignment issue. | Align the placeholder icon correctly and verify against the design before closing the bug. | https://i.ibb.co/Myc9FJDR/b8cd0673da01.png
SP_162 | 2026-06-02 | All Browsers | - | Tablets / iPads | P2 | Here Are 4 Recommended Cards for You --> The Card Containers are missing their box shadow effect for screen sizes between 767px - 1199px | https://www.loom.com/i/b89e9c796b77476e88e2b13653e6b6ea | - | Bharat | Fixed | 4/6/2026 - Fixed |  |  |  | Yes | The missing box shadow effect has been restored for tablet screen sizes and the issue is resolved. | Close the bug after a quick verification in the latest build.
SP_163 | 2026-06-02 | All Browsers | - | All Devices | P2 | Here Are 4 Recommended Cards for You --> The Card Title's font colour have started to fail the expected colour contrast ratio which is 4.5:1 | https://www.loom.com/i/4df06235ecdc469db99326cb9b8f8f85 | - | Bharat | Fixed | 4/6/2026 - Fixed
SP_164 | 2026-06-02 | All Browsers | - | Touch Devices | P2 | 1st Step (What is your annual income?) --> Touch Device --> Now if user starts the drag gesture right on top of the bar's thumb, it doesn't shift its position to the direction where it gets dragged. | MicrosoftTeams-video (8).mp4 | - | Bharat | Fixed | 4/6/2026 - Fixed

## FYPC - Pending Bugs for Verific
Defect no | Date | Browsers | Font Size | Device | Priority | Type | Section | Title | Description | Steps to Reproduce | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Assigned To | Dev Status | Last Fixed On | Dev Remark | Status | Last Tested On | QA Remark | Close or Not | Reason for Close / Not Close | Any Action Required
FC_012 | 2026-05-15 | All Browsers | - | Desktops | P3 | Bug | Landing | Quick 3 Banner font appearing larger than section heading | Please discuss with the client if it is okay for the banner font size to appear larger than the section title itself. Usually font size hierarchy is to be maintained | Quick 3 Banner --> Heading font size --> Compare it with the section's heading | https://www.loom.com/i/392e3925eea149b5bd60488fcbd7f09c | - | Satyam | Fixed |  | I have followed the exact design provided it is just viduslly appearing to be like that due to font family and style. | Need Discussion | 2026-06-04 | 04/06/2026 - Need client confirmation whether they have any issue with this or is it fine for them because now - <h> Find Your Perfect Card </h1> has font size - 3.6rem & <h2> SKIP THE SEARCH. ANSWER 3 QUICK QUESTIONS TO FIND YOUR CARD. </h2> has 2.5rem still the look almost the same size. - https://navajowhite-crow-447925.hostingersite.com/fpc-v4/find-perfect-card.html 22/05/2026 - Need to discuss with Arun sir whether the Banner Title's font size is appropriate as per the client or needs to be reduced. | No | Developer fixed it as per design, but QA is still waiting for client confirmation because both headings look almost the same size visually. | Discuss with the client and confirm if the current font size is acceptable. Close the bug after approval.
FC_025 | 2026-05-15 | All Browsers | - | Desktops | P2 | Bug | Landing | Add dropdown item role not announced | Add button's list items when focused through nvda narrator, do not mention their role which is hyperlink. | NVDA Narrator --> Add button dropdown --> Focus on list items | - | - | Satyam | Fixed |  | Now the narrator is tracking the options as link in the item list . 08/06:- I have revised the code and now the narrator is reading the menuitem as "Premium card link menuitem 1 of 7" clearly demonstrating that its a link present in the menuitem at some specific place in a list. | Unresolved | 2026-06-04 | 04/06/2026 - The issue is the same as mentioned in the QA remark of 22nd May and solution to this is already shared with sachin and documented in the QA remark of the bug - FC_025 as well - the categories list is not a dropdown list but a button clicking on which pop appears that has links to the category pages, therefore user should be able to traverse through the list using tab button only instead of arrow up & down. 22/05/2026 - The anchors in the dropdowns are mentioned as list items but not as actionable links. Therefore user only gets to know they are list items but not that they are clickble links - https://navajowhite-crow-447925.hostingersite.com/fpc-v3/find-perfect-card.html# 19/05/2026 - Now NVDA narrator no longer shifts focus between the list items, also the issue with windows narrator for the same is already mentioned in bug - FC_024. Maybe we should let the user navigate through the list items using tab & shift + tab button just for this dropdown - https://navajowhite-crow-447925.hostingersite.com/fpc-v2/find-perfect-card.html# | No | QA concern is still not resolved. Developer fixed the announcement, but the navigation behavior is still under discussion. | Confirm the expected keyboard navigation with QA/client before closing the bug.
FC_035 | 2026-05-25 | All Browsers | - | All Devices | P2 | Bug | Search Results | Add button & search suggestions popup background transparency affects readability | The Add button list & the Search Suggestions box's background fill is more translucent than requried. As a result the text in the background and in the pop up list are overlapping with each other affecting their readability. | Add button / Search Suggestions --> Open the pop up list --> Notice how the text in the list items overlap with the text in the background due to less opacity. | https://www.loom.com/i/283a4395db4b468ca622cf718e9dddb3 | - | Satyam | Fixed |  | As discussed with Phulvinder I have mainatined the properties same. Now this effect will only be handled by opacity and not blur. Maintained the same thing in both the pages and across both light and dark mode. | Unresolved | 2026-06-04 | 04/06/2026 - As per the design, the background properties for the pop up should be as follows in order to get the glass effect - dark mode - background: rgba(17, 16, 16, 0.95); backdrop-filter: blur(3px) light mode - background: rgba(255, 255, 255, 0.95); backdrop-filter: blur(3px) | No | The implemented fix does not match the design requirements mentioned in the remarks. Design still requires opacity with blur effect for the glass appearance. | Verify with design/QA whether the current implementation is acceptable. Keep open until design compliance is confirmed.
FC_041 | 2026-05-25 | All Browsers | - | All Devices | P3 | Bug | Best 4 SBI Card Options | Star and Finger emoji appear different in HTML | The Star emoji in each suggested card's name & the finger emoji for each card's bullet point do not appear exactly as they do in the design | Card Title & Card bullet points --> Compare both the emoji icons from their design. | https://www.loom.com/i/c20908f69f3446b0860b242dda7d8e7f | https://www.loom.com/i/efacf667a0264639b45a0e05e8a30aa0 | Satyam | Fixed |  | the icons used in Search result page of "find your card" lp is a sample layout icon, these will be Emoticons icons and pulled from system itself of user. | Need Discussion | 2026-06-04 | 04/06/2026 - In order to close the bug, need client confirmation for the reason mentioned by the developer in the dev remark. | No | Client confirmation is still pending on the developer's explanation about system-generated emojis. | Confirm with the client before closing the bug.
FC_043 | 2026-05-25 | All Browsers | - | All Devices | P3 | Bug | Search Results | Quick Comparison & Compare Cards emoji doesn't match the design | The Quick Comparison & Compare Cards heading needs to have the same emoji used in the design | Compare the quick comparison & compare cards emoji with the design | https://www.loom.com/i/82e6872b9909409184b66889a987f5eb | https://www.loom.com/i/380e1e0ed898486586af08d49ce340fd | Satyam | Fixed |  | the icons used in Search result page of "find your card" lp is a sample layout icon, these will be Emoticons icons and pulled from system itself of user. | Need Discussion | 2026-06-04 | 04/06/2026 - In order to close the bug, need client confirmation for the reason mentioned by the developer in the dev remark. | No | Emoji appearance depends on the user's system, so it may not exactly match the design. Client confirmation is still pending. | Confirm with the client before closing the bug.
FC_044 | 2026-05-25 | All Browsers | - | All Devices | P3 | Suggestion | Search Results | Bullet point & Heading's finger emoji not vertically center aligned with the text | Suggestion - If possible, the finger emoji & the text can be made veritically center aligned. Currently the finger icon is appears to be slighly lower when compared with the text | Compare the finger emoji's vertical position with the text for each bullet point and heading. | https://www.loom.com/i/6476c205c37b45a2b2913b7cc85acec1 | - | Satyam | Fixed |  | Since emoticons will be used herin the content will be adjusted automatically. | Need Discussion | 2026-06-04 | 04/06/2026 - In order to close the bug, need client confirmation for the reason mentioned by the developer in the dev remark. | No | Client confirmation is still pending on the developer's explanation regarding emoji alignment. | Confirm with the client before closing the bug.
FC_047 | 2026-05-25 | All Browsers | - | All Devices | P3 | Bug | Recommended Cards for Budget Users | "Recommended Cards for budget users" emoji doesn't exactly match the design | The "Recommended Cards for budget users" needs to have the same emoji used in the design | Compare the "Recommended Cards for budget users" emoji with the design | https://www.loom.com/i/d744b24c688b4dc2a3a93e29d27786c9 | https://www.loom.com/i/d3a7dcc4539f4c1fb560af57cdfc6f1f | Satyam | Fixed |  | the icons used in Search result page of "find your card" lp is a sample layout icon, these will be Emoticons icons and pulled from system itself of user. | Need Discussion | 2026-06-04 | 04/06/2026 - In order to close the bug, need client confirmation for the reason mentioned by the developer in the dev remark. | No | Emoji appearance depends on the user's system, so it may not exactly match the design. Client confirmation is still pending. | Confirm with the client before closing the bug.
FC_052 | 2026-05-25 | All Browsers | - | All Devices | P3 | Bug | Best Value Credit Card | "Best Value Credit Card" heading emoji doesn't exactly match the design | The "Best Value Credit Card" needs to have the same emoji used in the design | Compare the "Best Value Credit Card" emoji with the design | https://www.loom.com/i/331b47fcc216468daedc8967678ff0c7 | https://www.loom.com/i/486af6e736d64031994df41ae98d01cb | Satyam | Fixed |  | Corrcted the size | Need Discussion | 2026-06-04 | 04/06/2026 - In order to close the bug, need client confirmation for the reason mentioned by the developer in the dev remark. | No | Client confirmation is still pending on the implemented emoji size change. | Confirm with the client before closing the bug.
FC_053 | 2026-05-25 | All Browsers | - | All Devices | P2 | Bug | Best Value Credit Card | Bullet points & the nested bullet points in them do not follow font size hierarchy | There should be at-least ~2-4px font size difference between a parent and a child text. A common Industry Guidelines that is followed to maintain font size hierarchy | Best Value Credit Card --> Compare the main bullet point's font size with the sub-bullet points nested inside them. | https://www.loom.com/i/ca585d3a8874466fb7fb8806fd2339e4 | - | Satyam | Fixed |  | Updated the size as per hierarchy | Unresolved | 2026-06-08 | 08/06/2026 - As checked on call, font-weight has 200 difference and the font-size difference has slightly been increased and will be received in the next build. 04/06/2026 - There should be at least ~2-4px font difference between parent bullet point and the bullet points nested in it. If not, at least 200-300 font weight difference. None of the condition is being met - https://navajowhite-crow-447925.hostingersite.com/fpc-v4/fpc-search-result.html | No | The required font size/weight hierarchy fix is planned for the next build and is not available in the current build. | Verify the fix in the next build before closing the bug.
FC_061 | 2026-05-25 | All Browsers | - | Mobile Phones | P2 | Bug | Search Results | Visible empty strip appears along page edge | A narrow empty/white strip is visible along the extreme right edge of the page throughout the entire screen height on mobile devices. | Real Mobile Phone --> Notice the white gap on the extreme right | https://www.loom.com/i/4c4bb75912574cb985e1ba9b5f8e71db | - | Sachin | Fixed | 2026-06-08 | Issue have been fixed now, but for this we have to reduce the size of the tab by 8px | Unresolved | 2026-06-04 | 04/06/2026 - The issue is still the same as mentioned in the description | No | The issue was still present during the last QA check. The fix needs to be verified in the latest build. | Re-test the latest build and close only if the white strip is no longer visible.
FC_070 | 2026-05-25 | All Browsers | - | Touch Devices | P2 | Bug | Search Results | Both Table's Horizontal scroll do not work when directly holded and swiped | On real touch devices, when both table's horizontal scroll bars are touched and swiped to scroll, they do not work and even if they do. They may also perform the swipe gesture directly on the table | Real touch devices --> Table's horizontal scroll bar --> Try to slide the scroll bar | https://www.loom.com/i/9691ca4d0a1b4a12adaf8b8e664d4803 https://www.loom.com/i/6988dca01d5e48669346208dcd19c4f4 | - | Sachin | Need Discussion | 2026-06-08 | There is no such functionality is provided even in default scrollbars | Unresolved | 2026-06-04 | 04/06/2026 - The issue is still the same as mentioned in the description | No | The issue is still unresolved and requires discussion. The expected behavior has not been confirmed. | Discuss with QA/client and confirm whether this behavior is expected before closing the bug.
FC_071 | 2026-05-26 | All Browsers | - | All Devices | P2 | Bug | Landing | Search suggestions appear right after user clear the search input | While searching, make sure to start the search by a character that is included in any of the search suggestion items. Then, clear the search input. Notice how even after clearing the search input, the search suggestions appear. | Search Bar --> Start the search by a character present in any of the search suggestions --> clear the input --> Notice how the search suggestions appear even after clearing the search input. | https://www.loom.com/share/f84ef398d32044ecb4379169cfe1353a | - | Sachin | Fixed | 2026-06-08 | Issue have been fixed now if you clear response it will not show any options | Reopened | 2026-06-05 | 05/06/2026 - Type any character twice or more times in the input box - a character that appears in any of the suggestion options, clear the input box and notice how the search suggestion pop up still appears after clearing the input - https://navajowhite-crow-447925.hostingersite.com/fypc-v5/find-perfect-card.html 04/06/2026 - The issue is resolved on - https://navajowhite-crow-447925.hostingersite.com/fpc-v4/fpc-search-result.html | No | The issue was reopened because the search suggestions still appear after clearing the input in some cases. | Re-test the latest build and close only if the issue is fully resolved.
FC_073 | 2026-05-26 | All Browsers | - | Touch Devices | P3 | Bug | Search Results | Read Aloud does not resume after returning to browser | If the user leaves the browser using the Home or Recent Apps button while Read Aloud is playing, the playback pauses and does not resume after returning to the browser. | Real touch devices --> Read Aloud --> Press Home or Recent apps --> Get back to the browser --> Notice how the read aloud doesn't resume. | MicrosoftTeams-video (2).mp4 | - | Sachin | Fixed | 2026-06-08 | This have been fixed now it will pause if you switch the tab or any app even going to home is also handled. | Unresolved | 2026-06-04 | 04/06/2026 - The issue is still the same as mentioned in the description | No | The issue was reported as still present in the last QA check. The latest fix needs to be verified. | Re-test the latest build and close only if the read aloud behavior works as expected.
FC_074 | 2026-05-26 | Firefox | - | Touch Devices | P3 | Bug | Search Results | Search Bar stutters and jumps on its position when user scrolls up/down | In case of firefox browser on touch devices, while scrolling up & down, the search bar can be observered stuttering or jumping slighly from its position | Real touch devices --> Firefox Browser --> Scroll up & down the page --> Notice the search bar stuterring, jumping in its position | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQCIHLl7NBB7TqjCg85mWu0hAag4u7dXOJ1EkO4GM1O9GAk?e=q0dZy7 | - | Sachin | Need Discussion |  | This kind of issue is there in other pages and it seems to be an firefox issue not development | Unresolved | 2026-06-04 | 04/06/2026 - The issue is still the same as mentioned in the description | No | The issue is still present and has been marked for discussion. It is not yet confirmed whether this is a Firefox limitation or a development issue. | Discuss with QA/client and confirm the expected action before closing the bug.
FC_075 | 2026-05-26 | All Browsers | - | All Devices | P2 | Bug | Search Results | Search Bar gets extra gap on the left & right (device width - 731 - 767px) | For devices with width around (731px - 767px) - extra gap on the left & right side of the input box is observed in the search bar. | Device width (731px - 767px) --> Search Bar --> Notice the gap from the left & right side | https://www.loom.com/i/bb4983029ee946f78686d2032f867086 | - | Sachin | Fixed | 2026-06-08 | This issue was due to media query now i have properly handled | Unresolved | 2026-06-04 | 04/06/2026 - Now the gap has been introduced for all devices under 767px width which is not how the query search box is demonstrated in the design and now this bug's priority has been changed from P3 to P2 - https://navajowhite-crow-447925.hostingersite.com/fpc-v4/fpc-search-result.html https://www.loom.com/i/986439aea79c454398a40af7c5fb34d1 | No | The issue was still present in the last QA check and the fix needs to be verified in the latest build. | Re-test the latest build and close only if the spacing matches the design.
FC_077 | 2026-05-26 | All Browsers | - | Desktops | P3 | Bug | Search Results | Keyboard focus on 2nd card CTA buttons remains hidden behind sticky search bar | While navigating the actionable items through keyboard, if the 2nd card CTA buttons are within the viewport and focus goes to them, user remains unable to guess where the focus went because focus is on CTA buttons and both of them remain hidden under the search bar. | Keyboard Navigation --> Get the focus to the CTA buttons of the 2nd Card (IRCTC in current case) while them being within the viewport --> Notice how the CTA remain hidden under the search bar and user keeps guessing where the focus went. | https://www.loom.com/i/58546079a207474ba4c80dbe0e5629c4 | - | Sachin | Fixed | 2026-06-08 | This was due to sticky input bar overlapping with the action items. now its handled | Unresolved | 2026-06-04 | 04/06/2026 - The issue is the same as mentioned in the description | No | The issue was still present in the last QA check. The latest fix needs to be verified. | Re-test the latest build and close only if the keyboard focus is clearly visible.
FC_080 | 2026-05-26 | All Browsers | - | All Devices | P2 | Bug | Search Results | Read Aloud skips introductory heading and paragraph content | Read aloud feature doesn't read the initial heading & paragraph - "Got it! I've found the best 4 cards..." - "I've picked cards that match your preferences..." | Read Aloud --> The reading directly starts from the 1st card instead of introductory heading & paragraph at the top | https://www.loom.com/i/563cdf4b93444a389dd2450b64c75127 | - | Sachin | Fixed | 2026-06-08 | Fixed now whole response will be read by Read Aloud | Unresolved | 2026-06-04 | 04/06/2026 - The issue is still the same as mentioned in the description - https://navajowhite-crow-https://loom.com/i/4e0842910f9c402d984018a54fa02675 | No | The issue was still present in the last QA check. The latest fix needs to be verified. | Re-test the latest build and close only if the introductory heading and paragraph are read aloud correctly.
FC_081 | 2026-05-26 | All Browsers | - | All Devices | P3 | Bug | Search Results | Copied content loses original formatting and structure | Entire text gets copied but not in the same format or layout - Bullet points lose their order/indexes and their nested indentaion. Table content loses its table layout. | Read Aloud --> Notice how the text loses its formmatting and structure or layout when gets pasted | https://loom.com/i/dcbb2275ad024affad63dff1370c32d2 | - | Sachin | Need Discussion | 2026-06-08 | Exact formating can't be achieved, also as per client requirement they need the content | Unresolved | 2026-06-04 | 04/06/2026 - The issue is still the same as mentioned in the description - https://navajowhite-crow-https://loom.com/i/4e0842910f9c402d984018a54fa02675 | No | The issue is marked for discussion. The developer stated that exact formatting cannot be achieved, but this still needs confirmation. | Discuss with QA/client and confirm whether the current behavior is acceptable before closing the bug.
FC_082 | 2026-05-26 | All Browsers | - | All Devices | P3 | Suggestion | Search Results | Narrator does not announce row and column headers text before reading each cell value | Suggestion - It would be great if the narrator could annouce the text in the row & column of the cell before announcing its value in order to provide better context when focus is on any of the table cell. | Screen Readers --> Compare Cards & Quick Comparison Table --> Press ctrl + alt + arrow up/down/left/right to move the focus to different table cells --> Notice how it could have been better if before the cell' text, its row & column heading text go narrated. | - | - | Sachin | Need Discussion | 2026-06-08 | This is the best we could do on changing so much in the js may create more problems in existing readaloud that's working fine. also window narrator say this at last. also i have added official table from wcag https://www.w3.org/WAI/ARIA/apg/patterns/table/examples/table/ | Unresolved | 2026-06-04 | 04/06/2026 - The issue is still the same as mentioned in the description - https://navajowhite-crow-https://loom.com/i/4e0842910f9c402d984018a54fa02675 | No | This is a suggestion and the developer has marked it for discussion. The current implementation is considered acceptable, but confirmation is still needed. | Discuss with QA/client and confirm whether any further improvement is required before closing.
FC_102 | 2026-06-04 | All Browsers | - | All Devices | P2 | Bug | Search Results | Table border corners mismatch | In dark mode, the corner border corners of the Quick Comparison & compare cards table do not match. The border styling should be consistent for both the tables and for all 4 of their corners. | Dark Mode --> Quick Comparison Table --> Corner borders | https://www.loom.com/i/d4c7f1f91b284e1f84ce9d69b2cd5469 https://www.loom.com/i/a065c03cd8e04aa2ad9115eb6c0c2b7c | - | Sachin | Need Discussion | [5 empty] | No | The bug is marked for discussion and no fix confirmation is available yet. | Review with QA/design and confirm the expected border styling before closing.
FC_103 | 2026-06-04 | All Browsers | - | All Devices | P2 | Bug | Search Results | Response action icons not visible in Dark Mode | In dark mode, the response action icons do not switch to a white color, resulting in insufficient visibility against the background. | Dark Mode --> Response Action Icons | https://www.loom.com/i/7548d2e2e5de4bee984727aa7c8164aa | - | Satyam | Fixed | 2026-08-06 | Updated the buttons to white color in dark mode |  |  |  | Yes | The developer has updated the icons to white in dark mode as required. | Verify once in the latest build and close if the icons are clearly visible.
FC_104 | 2026-06-04 | All Browsers | - | All Devices | P2 | Bug | Landing Page | AI Bot's black shadow effect on the right incorrect | The black shadow effect that the HTML has for the AI bot is not at all something that noticeable in the design. It is appearing too prominent and not blending in with the gif | AI Bot --> Black shadow effect on the right | https://www.loom.com/i/6a35a06a7dae4c81841a8842695c62d2 | - | Satyam | Fixed | 2026-05-06 | Added the updated shadow behind the robo image |  |  |  | No | The developer has updated the shadow effect, but the fix has not been verified yet. | Verify in the latest build and close only if the shadow matches the design.
FC_107 | 2026-06-04 | All Browsers | - | All Devices | P3 | Bug | Landing Page | Add button popup's rounded connection doesn't match with the design | Across all devices, the popup opened from the Add button is visually connected to the button; however, the rounded connection is not as padded from the add button icon as it is in the design and appears to almost be blended with the background from its bottom. | Landing Page/ Search Results --> Search Bar --> Add button | https://www.loom.com/i/d4de9ff467574e1c884dca5307cc4553 | - | Sachin | Fixed | 2026-08-06 | I have tried to match it in the exact same way as the design but since this is not something standardized from design aspect so have made the closest design possible. |  |  |  | Yes | The developer has updated the popup connection and matched it as closely as possible to the design. | Close the bug if the current appearance is acceptable.
FC_108 | 2026-06-04 | All Browsers | - | All Devices | P3 | Bug | Quick Question | The quick question container remains full width even for smaller questions | Regardless of if the follow up quick question is shorter, its container width always remains full size instead of only being up to the content that it container. Just like the first user query message | Quick Question (Would you like me) --> Enter a shorter question --> Notice the container width | https://www.loom.com/i/835525b1a2b54671afb7ac4b1df7bbdb | - | Satyam | Fixed | 2026-08-06 | Fixed the width issue now the width of the container will change with the changing width of the content within. |  |  |  | Yes | The width issue has been fixed and the container now adjusts based on the content. | Close the bug after a quick verification in the latest build.
FC_109 | 2026-06-05 | All Browsers | - | Desktops | P2 | Bug | Landing Page | At 200% zoom, the AI Bot gif overlaps above the categories popup list | When users zoom in till 200% or above and click on the Add button to open the categories popup list, then the AI chatbot appears on top of it overlapping it | Zoom till 200% --> Click Add button --> Notice the AI Bot gif's | https://loom.com/i/d96243dc0ec84226828e20663a3e89fb | - | Satyam | Fixed | 2026-08-06 | Fixed the overlapping behaviour of the bot and dropdown menu. |  |  |  | Yes | The overlapping issue has been fixed and the AI bot no longer covers the dropdown menu. | Close the bug after a quick verification in the latest build.
FC_110 | 2026-06-05 | All Browsers | - | Desktops | P3 | Bug | All Sections | Focus outline remains on the add button even after focus shift | While using screen readers, users press B to traverse through all the buttons. Now, if the add button has once been opened, the submit button is in disabled state and the focus shifts on it by pressing the B button, even then the focus outline of the add button doesn't disappear | Screen Readers --> Add button opened once --> B button pressed to reach submit button (disabled state) | https://www.loom.com/i/d985bdf25b3c4784b2ac87832bcbaba1 | - | Satyam
FC_111 | 2026-06-05 | All Browsers | - | Desktops | P2 | Bug | All Sections | Reason for Submit button being disabled is not conveyed | While using screen readers, users can get the focus on the submit button even when it is disabled just by using the B button shortcut from their keyboard, when this happens, it only says "Submit button - Disabled" and doesn't mention the reason for it being disabled, neither when it lands on it nor when user presses enter or space to press it | Screen Readers --> Press B --> Focus on the Submit button while disabled | https://www.loom.com/i/d985bdf25b3c4784b2ac87832bcbaba1 | - | Satyam
FC_112 | 2026-06-05 | All Browsers | - | Desktops | P2 | Bug | Landing Page | Unexpected focus announced after "Make a Wish" in Scan Mode | When Narrator Scan Mode is enabled (Caps Lock + Space), navigating past the "Make a Wish" text causes Narrator to announce "Type your needs here." However, focus appears to move to an element indicated only by a border outline that is not visibly rendered on the screen. It is unclear whether this announcement corresponds to the actual input field, as the visible input box is not highlighted or brought into focus. | Screen Readers --> Scan Mode --> Arrow down button | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQD0s2wvIJjMSLdv2RNXG3iRAejdq1CAI2BP_g_Gyo1X5mA?e=Z6xrJ2 | - | Satyam
FC_114 | 2026-06-05 | All Browsers | - | All Devices | P3 | Bug | Landing Page | The Alt text for AI Bot speech box needs to convey the speech message | As the alt text is used to narrate images by screen readers and in cases when image fails to load, therefore it needs to convey the meaning of the image. Instead of, "AI assistant robot callout message" it can at least say "Hi, I'm Gennie" as shown in the image. | AI Bot Speech Box image --> Alt-text property value | https://www.loom.com/i/c819cd0e9e9144c38ba7a9c00a3f985c | - | Satyam | Fixed | 2026-08-06 | Updated to: AI assistant robot callout message: Hi, I'm Gennie, your smart AI assistant. Let's find the perfect card for you! |  |  |  | Yes | The alt text has been updated to properly convey the speech message. | Close the bug after a quick verification in the latest build.
FC_115 | 2026-06-05 | All Browsers | - | All Devices | P3 | Suggestion | Search Results | Static content should have some hyperlink demonstrations as well | Suggestion - As we are describing about cards, content team may get demand from the brand that we should include T&Cs or other hyperllinks as well. For such cases, we should demonstrate 1 or 2 hyperlink examples as well | Search Results --> Hyperlink demonstrations | https://loom.com/i/ff29efcc5d42462ca2829e3e75417ba2 | - | Satyam | Fixed | 2026-08-06 | Added the links at various places. |  |  |  | Yes | Hyperlink examples have been added as suggested. | Close the suggestion after a quick verification in the latest build.
FC_116 | 2026-06-05 | All Browsers | - | Desktops | P3 | Bug | Landing Page | The AI Chatbot's speech box position mis-matches with the design for desktops | The Speech box is placed inside the tablet container in case of desktops instead of on top of it. Check the actual vs expected result screenshots. | AI Bot Speech box image --> Position on the desktop | https://www.loom.com/i/b2216203558e40a8adf74a67e028fdf6 | - | Satyam | Fixed | 2026-08-06 | updated in accordance with the design |  |  |  | Yes | The speech box position has been updated to match the design. | Close the bug after a quick verification in the latest build.
FC_117 | 2026-06-05 | All Browsers | - | Mobile Phones | P3 | Bug | Search Results | Categories and Suggestions pop-ups overlap with header in landscape mode | Categories pop up & Input suggestions pop up get overalapped by the header in case of landscape mode | Real Mobile Phones --> Landscape Mode --> Open the Categories pop up & search suggestions pop up | https://loom.com/i/1ddd6ffbea834c889109baa94f031322 https://loom.com/i/2c5dc26f511f49f4882fa3ac09d19fe4 | - | Satyam | Fixed | 2026-08-06 | corrected the behaviour |  |  |  | Yes | The overlapping issue in landscape mode has been corrected. | Close the bug after a quick verification in the latest build.

## Sheet1
Defect no | Date | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-06-05 | Desktop | Edge | md | Home breadcrumb text is bold on the website but not bold in the design. | https://www.loom.com/i/c79d455f978c4a7d854381cd5c47ac22 | https://www.loom.com/i/efa7daead9774c2b96f13d8dad62c5b0 | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; breadcrumb font weight does not match the design.
2 | 2026-06-05 | Desktop | Edge | md | Background 0/1 pattern image appears blurry and low quality on the website compared to the HD design. | https://www.loom.com/i/6e808fef82284d43ae9120ae5f8c3916 |  | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; background pattern image quality does not match the design.
3 | 2026-06-05 | Desktop | Edge | md | Robot message box is touching the top border of the card on the website, whereas proper spacing is maintained in the design. | https://www.loom.com/i/a321568b26a741d5bc07214ff101cbda |  | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; spacing between the robot message box and top border does not match the design.
4 | 2026-06-05 | Desktop | Edge | md | Text in the "I Spend 10,000+/Month On Groceries" button overflows outside the button at 100% default browser zoom. | https://www.loom.com/i/b0ce72ce0540435a8149ae230aa56d30 |  | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; button text is not properly contained within the button boundary.
5 | 2026-06-05 | Desktop | Edge | md | Text in the "I Spend 10,000+/Month On Groceries" button overflows outside the button at 100% zoom, while it fits correctly at 125% zoom. | https://www.loom.com/share/47ca6491eccc4404bcfffb4d890c0a9a |  | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; button text is not properly displayed at default browser zoom.
6 | 2026-06-05 | Desktop | Edge | md | Focus border changes the button shape during keyboard navigation. on same button | https://www.loom.com/share/00664888be134130a5d64cbb05c0e1d1 |  | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; button shape changes when focused using the keyboard.
7 | 2026-06-05 | Desktop | Edge | md | Selected button turns blue with mouse click, but not with keyboard navigation. | https://www.loom.com/share/03d3445450314dca9babd5aaf32322a4 |  | P2 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; keyboard and mouse selection behavior is inconsistent.
8 | 2026-06-05 | Desktop | Edge | md | UI breaks at 200% browser zoom. Suggestion buttons overlap each other and text becomes unreadable. | https://www.loom.com/share/17a5f78fb08c458b9a4651ddd8aa17a6 |  | P2 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; buttons and text overlap at 200% zoom, affecting readability and usability.
9 | 2026-06-05 | Desktop | Edge | md | Robot image appears blurry and low quality on the website. | https://www.loom.com/share/b2a050d93eda46238e0161111b649935 |  | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; robot image quality does not match the design.
10 | 2026-06-05 | Desktop | Edge | md | In Dark Mode, button shadow effects are not visible and the button border blends with the black background. A grey border should be used for better visibility. | https://www.loom.com/i/47d9e03242d0406496e6cb0c7e71695e |  | P3 |  | Open |  |  | Failed | 2026-06-05 | Issue reproduced; button border and shadow are not clearly visible in Dark Mode.