## Sheet1
Number | Date | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-06-17 | Samsung Galaxy S20 Ultra, Pixel 7, Surface Duo, Asus Zenbook Fold, Samsung Galaxy A51/71 | Edge | md | White line visible on the right side of the page. | https://ibb.co/3ygFK73D |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; on supported mobile devices, a white vertical line appears along the right edge of the page, resulting in an inconsistent UI appearance.
2 | 2026-06-17 | Via Browser | Edge | md | UI breaks on the page in Via Browser. | res.cloudinary.com/dnztp5chw/video/upload/v1782971480/video_2026-07-02_11-19-42_c9eevx.mp4 |  | P1 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the page layout breaks when viewed in Via Browser, causing UI elements to render incorrectly and affecting the user experience.
1card
1 | 2026-06-17 | Desktop | Edge | md | Vertical separator line is not visible in Dark Mode. | https://ibb.co/bjD6C83m |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; in Dark Mode, the vertical separator line is not visible, making the sections appear merged and reducing visual clarity.
2 | 2026-06-17 | Samsung Galaxy S20 Ultra, Pixel 7, Surface Duo, Asus Zenbook Fold, Samsung Galaxy A51/71 | Edge | md | White line visible on the right side of the page. | https://ibb.co/3ygFK73D |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; on supported mobile devices, a white vertical line appears along the right edge of the page, resulting in an inconsistent UI appearance.
3 | 2026-06-17 | Desktop | Edge | md | App Store button alignment is inconsistent in the footer.but in default build align downside of socail media platforms and nearby playstore button | https://ibb.co/FbqVDg4m |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the App Store button is not aligned with the social media icons as per the design and appears lower than expected in the footer.
4 | 2026-06-17 | Desktop | Edge | md | Excessive empty space on the right side of the card layout. | https://ibb.co/FLY2CmFN |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; excessive empty space is displayed on the right side of the card layout, resulting in poor space utilization and an unbalanced UI.