## Sheet1
Number | Date | Device | Browser | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-06-17 | Desktop | Edge | md | Multiple image resources failed to load. |  |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; multiple image resources failed to load due to missing or invalid file paths, resulting in broken images and missing UI elements. A total of 20 resource loading failures were detected.
2 | 2026-06-17 | Desktop | Edge | md | Narrator announces '1/7, 2/7, 3//7, 4/ 7, ... Group then says Link"Apply Now" button on top carosal hero section | https://ibb.co/DPN6B9Lj |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; when navigating with Narrator, it announces "2 of 7 group" before reading the "Apply Now" button. The extra group announcement is unnecessary and may confuse screen reader users. The button should be announced directly with its accessible name and role.
3 | 2026-06-17 | Desktop | Edge | md | Narrator announces '1/6, 2/6, 3/6, 4/6, ... Group then says Link"Apply Now" button on Explore Our Cards section | https://ibb.co/KcQ4hBc1 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; when navigating to the "Apply Now" or "See Benefits" buttons on different card tiles, Narrator announces group information such as "1 of 6 group" before the button name. The extra group announcement is unnecessary and may confuse screen reader users. The buttons should be announced directly with their accessible name and role.
4 | 2026-06-17 | Desktop | Edge | md | Narrator announces 'iinput field...' on invisible element after view all cards button | https://ibb.co/SDJWYzbB https://www.loom.com/share/863519e7b3c945c1a2a41e10a53ef1d6 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; while navigating with Narrator, an invisible input field is announced even though it is not visible or interactive on the screen. Hidden elements should not receive keyboard focus or be exposed to screen readers.
5 | 2026-06-17 | Desktop | Edge | md | Narrator announces lot of invisible elements after the "View All Cards" button. | Screen Recording 2026-07-06 202153.mp4 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; after focusing on the "View All Cards" button, Narrator announces hidden/invisible elements that are not displayed on the screen. Invisible elements should not receive focus or be exposed to screen readers.
6 | 2026-06-17 | Desktop | Edge | md | narrator anncoune goto card 1 button, goto card 2 button, goto card 3 button which cards ? blind user will confuse on why sbi card section. | Screen Recording 2026-07-06 202813.mp4 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; Narrator announces carousel controls as "Go to card 1 button", "Go to card 2 button", "Go to card 3 button", etc., without providing the associated card names. These generic labels do not convey meaningful information and may confuse screen reader users. The buttons should include descriptive accessible names, such as "Go to Flipkart SBI Card" or "Go to Tata Neu Infinity SBI Card".
7 | 2026-06-17 | Desktop | Edge | md | Narrator announces "Extra Link" which link? blind user will confuse on Get More with SBI card section | Screen Recording 2026-07-06 203420.mp4 |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; Narrator announces "Extra Link" without indicating its purpose or destination. The link lacks a descriptive accessible name, making it unclear for screen reader users what the link does or where it navigates.
8 | 2026-06-17 | Desktop | Edge | md | Narrator announces 2/3 group, etc on sbi credit cards mobile app section | mobile.mp4 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; while navigating with Narrator, it announces group information such as "2 of 3 group" before interactive elements. This extra announcement is unnecessary and may confuse screen reader users. Interactive elements should be announced directly with their accessible name and role.
9 | 2026-06-17 | Desktop | Edge | md | narrator announce content information footer and footer logo,but it should be announce sbi card homepage link | 1Recording-20260706_204726.webm |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; when the footer logo receives focus, Narrator announces "Content Information", "Footer", and "Footer Logo" instead of a meaningful accessible name such as "SBI Card Home" or "SBI Card Homepage". This makes the purpose of the logo unclear for screen reader users.
10 | 2026-06-17 | Desktop | Edge | md | Navigation icons and menu items have inconsistent alignment and spacing. | https://ibb.co/Lz4b8x4r |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the navigation icons are not of consistent visual size, and the spacing and gaps between the icons and labels are uneven. This results in misaligned menu items and an inconsistent appearance across the navigation bar.
11 | 2026-06-17 | Desktop | Edge | md | Apply Now' button is missing for the Flipkart SBI Card. | https://ibb.co/zWrr1QSK |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the Flipkart SBI Card displays only the "See Benefits" button, while the "Apply Now" button is missing. Other card tiles display both buttons, resulting in an inconsistent user experience.
12 | 2026-06-17 | Desktop | Edge | md | Text cursor remains fixed at the beginning of the input field while Typing or Editing | https://ibb.co/8nmqS0Gt |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; while typing, deleting text, or navigating using the Left/Right arrow keys, the text cursor remains at the beginning (left side) of the input field instead of moving to the current editing position, making text editing difficult.
13 | 2026-06-17 | Desktop | Edge | md | Images are not properly aligned in the "EMI & More" section cards. | https://ibb.co/DHjrhGwG |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the images in the "EMI & More" section are not consistently center-aligned. Their position varies across the cards, resulting in an uneven and inconsistent UI appearance.
14 | 2026-06-17 | Desktop | Edge | md | Content is partially hidden in the "Get More with SBI Card" section. | https://ibb.co/RpYnCK2d https://ibb.co/zW1gQXc8 https://ibb.co/DfwZsHXb |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; in the "Get More with SBI Card" section, the content is partially cut off on multiple options, causing only half of the text to be visible and reducing readability.
15 | 2026-06-17 | Desktop | Edge | md | Explore Our Cards section does not adapt to Dark Mode. | https://ibb.co/My7QDV4n |  | P2 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the "Explore Our Cards" section does not follow the Dark Mode theme, while the "Find Your Perfect Card" section adapts correctly. This results in inconsistent theming and an inconsistent user experience across the page.
16 | 2026-06-17 | Desktop | Edge | md | Excessive spacing between button text and arrow icon. | https://ibb.co/2Ys9Y6H4 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the spacing between the button label ("Apply Now"/"See Benefits") and the arrow icon is excessive, making the button content appear misaligned and visually unbalanced.
17 | 2026-06-17 | Desktop | Edge | md | White vertical strip visible on the right side of the page on Asus Zenbook Fold. | https://ibb.co/93pD6BKP |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; when viewed on the Asus Zenbook Fold device, a white vertical strip appears along the right edge of the page, indicating that the layout does not fully fit the viewport and resulting in an inconsistent UI appearance.
18 | 2026-06-17 | Mobile | Edge | md | Apply Now and "See Benefits" buttons are inconsistently aligned across card carousel items. | video_2026-07-06_13-47-45.mp4 |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the vertical position of the "Apply Now" and "See Benefits" buttons varies between different cards due to inconsistent content height. As a result, the buttons appear at different levels instead of being aligned uniformly across all cards.
19 | 2026-06-17 | Mobile | Edge | md | Background image appears blurred and low quality in the "Why SBI Card?" section. | https://ibb.co/qLvSxd4g |  | P3 |  | Open |  |  | Failed | 2026-06-17 | Issue reproduced; the background image in the "Why SBI Card?" section appears blurry and pixelated on mobile devices, resulting in poor visual quality and an inconsistent user experience.