## Sheet1
Defect no | Date | Device | Browsers (Chrome/firefox/Edge/Safari) | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-05-19 | Desktop | Edge | md | Suggestion dropdown remains visible after clearing the input box; suggestions should disappear when no text is entered | https://www.loom.com/i/0d1fc186731d4d61bdbe7c81f6c4c682 |  | P2 |  | Open |  |  | Failed | 2026-05-19 | Issue reproduced; suggestion popup does not close/reset after input field is cleared
2 | 2026-05-19 | Desktop | Edge | md | Glow/shadow effect around the AI assistant container is missing on site; Figma design shows visible glow effects on edges and corners | https://www.loom.com/share/0d675a2e8a9b4c6599ec7543c577b0e9 |  | P3 |  | Open |  |  | Failed | 2026-05-19 | Issue reproduced; expected glow visual effect from Figma is not implemented on site
3 | 2026-05-19 | Desktop | Edge | md | UI action buttons inside AI assistant section are not working except the "+" icon; clicking other buttons does not perform any action | https://www.loom.com/share/46c872579a1d4e8799e34cef2bd082d3 |  | P1 |  | Open |  |  |  | 2026-05-19
4 | 2026-05-19 | Desktop | Edge | md | Robot illustration outline appears cluttered and rough on site, affecting visual clarity and clean appearance of the AI assistant graphic | https://www.loom.com/share/4c901de7507d45ebb71aac8d0102681b |  | P3 |  | Open |  |  | Failed | 2026-05-19 | Issue reproduced; robot image edges/outlines do not appear smooth and visually polished
5 | 2026-05-19 | Desktop | Edge | md | Content area below the heading has reduced vertical padding on site compared to Figma; design shows more balanced spacing similar to the input box section | https://www.loom.com/i/394642e4e4c74adcbb5cf6ba8bf57bea | https://www.loom.com/i/b82ea1e0b50448e5b9c6e7c95137d51a | P3 |  | Open |  |  | Failed | 2026-05-19 | Issue reproduced; spacing between heading and suggestion buttons does not match design reference
6 | 2026-05-19 | Desktop | Chrome | md | Nu HTML Validator shows HTML/accessibility warnings on webpage | https://www.loom.com/share/d183917c28cc413e8796778f30310977 |  | P3 |  | Open |  |  | Failed | 2026-05-19 | HTML validation warnings found related to accessibility and semantic attributes