## Sheet1
Defect no | Date | Device | Browsers (Chrome/firefox/Edge/Safari) | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-05-22 | Desktop | Chrome | md | Google Lighthouse performance score is low (54) on desktop insights | https://pagespeed.web.dev/analysis/https-navajowhite-crow-447925-hostingersite-com-fpc-v3-find-perfect-card-html/33hc7osphi?form_factor=desktop&category=performance&category=accessibility&category=best-practices&category=seo&hl=en-US&utm_source=lh-chrome-ext |  | P3 |  | Open |  |  | Failed | 2026-05-22 | Lighthouse audit shows low performance score affecting overall page optimization
2 | 2026-05-22 | Desktop | Edge | md | Suggestion dropdown remains visible after clearing the input box; suggestions should disappear when no text is entered | https://www.loom.com/i/0d1fc186731d4d61bdbe7c81f6c4c682 |  | P2 |  | Open |  |  | Failed | 2026-05-22 | Issue reproduced; suggestion popup does not close/reset after input field is cleared
3 | 2026-05-22 | Desktop | Edge | md | Robot illustration outline appears cluttered and rough on site, affecting visual clarity and clean appearance of the AI assistant graphic | https://www.loom.com/share/4c901de7507d45ebb71aac8d0102681b |  | P3 |  | Open |  |  | Failed | 2026-05-22 | Issue reproduced; robot image edges/outlines do not appear smooth and visually polished
4 | 2026-05-22 | Desktop | Edge | md | Content area below the heading has reduced vertical padding on site compared to Figma; design shows more balanced spacing similar to the input box section | https://www.loom.com/i/394642e4e4c74adcbb5cf6ba8bf57bea | https://www.loom.com/i/b82ea1e0b50448e5b9c6e7c95137d51a | P3 |  | Open |  |  | Failed | 2026-05-22 | Issue reproduced; spacing between heading and suggestion buttons does not match design reference
6 | 2026-05-22 | Desktop | Edge | md | Extra spacing is visible between "START NOW" text and arrow icon inside the CTA button compared to Figma design | https://www.loom.com/i/ee572c28b60f4f41b5d31f2bf6057c73 |  | P3 |  | Open |  |  | Failed | 2026-05-22 | Issue reproduced; button text and arrow icon spacing does not match design reference
7 | 2026-05-22 | Desktop | Edge | md | Glow/shadow effect is missing on the new site version but available in Figma design | https://www.loom.com/i/2407924a8a3d48a0891f7aa7d8edc36c |  | P3 |  | Open |  |  | Failed | 2026-05-08 | Issue reproduced; glow/shadow effect not visible on site