## Sheet1
Defect no | Date | Device | Browsers (Chrome/firefox/Edge/Safari) | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-05-28 | Desktop | Edge | md | Extra spacing/gap is visible between the "NEXT" button text and right arrow icon, causing alignment inconsistency | https://www.loom.com/i/5ffdeb190df04dc1ba488abfbfe0438a |  | P3 |  | Open |  |  | Failed | 2026-05-28 | Issue reproduced; button text and arrow icon spacing appears uneven
2 | 2026-05-28 | Desktop | Edge | md | Extra spacing is visible between the "APPLY NOW" button text and arrow icon, causing alignment inconsistency | https://www.loom.com/i/c1f59c144c794c25bce8fe2b46f947ae |  | P3 |  | Open |  |  | Failed | 2026-05-28 | Issue reproduced; button text and arrow icon spacing appears uneven
3 | 2026-05-28 | Desktop | Edge | md | NEXT button allows navigation even when no option/category is selected | https://www.loom.com/share/f0a57eed143449cab5b35c1ba5dc412f |  | P2 |  | Open |  |  | Failed | 2026-05-28 | Issue reproduced; form validation is missing and user can proceed without selecting any option
4 | 2026-05-28 | Desktop | Edge | md | User can proceed to the next page after selecting only one benefit option; minimum required selection count is not enforced | https://www.loom.com/share/ed7cfe46fe2e4e608b6bf85a4ba453df |  | P2 |  | Open |  |  | Failed | 2026-05-28 | Issue reproduced; flow allows navigation without completing the required number of selections
5 | 2026-05-28 | Desktop | Edge | md | SHOW ME MY CARDS button becomes visible after selecting only one option; button should appear only after selecting the required 3 benefits/options | https://www.loom.com/share/ed7cfe46fe2e4e608b6bf85a4ba453df |  | P2 |  | Open |  |  | Failed | 2026-05-28 | Issue reproduced; minimum selection validation is not enforced before enabling CTA button
Accessbility
1 | 2026-05-28 | Desktop | Edge | md | Google Lighthouse Performance score still needs improvement; current desktop performance score is 74 | https://pagespeed.web.dev/analysis/https-navajowhite-crow-447925-hostingersite-com-simplifier-v3-simplifier-html/99bphkbgaq?form_factor=desktop&category=performance&category=accessibility&category=best-practices&category=seo&hl=en-US&utm_source=lh-chrome-ext |  | P3 |  | Open |  |  | Failed | 2026-05-28 | Lighthouse audit indicates performance optimizations are still required
2 | 2026-05-28 | Desktop | Edge | md | Keyboard navigation is working correctly across the page and all interactive elements are accessible using keyboard controls | https://www.loom.com/share/a9060412f95240d194ef5a840ad99370 |  | P3 |  | Closed |  |  | Passed | 2026-05-28 | Verified that keyboard-only navigation works properly for accessibility testing
3 | 2026-05-28 | Desktop | Edge | md | Buttons, inputs, heading structure, and keyboard navigation are working correctly with screen reader accessibility testing |  |  | P3 |  | Closed |  |  | Passed | 2026-05-28 | Verified that core accessibility features work properly with screen readers and keyboard navigation
4 | 2026-05-28 | Desktop | Edge | md | Image Alt Text testing passed for most images, but card images on the final result page cannot be individually accessed or inspected to verify alt text details | https://www.loom.com/share/f05eb162dfae400b96d2c167a51225ea |  | P3 |  | Open |  |  | Failed | 2026-05-28 | Result page card images are not directly selectable/inspectable, preventing proper alt text accessibility verification
5 | 2026-05-28 | Desktop | Edge | md | Main <h1> heading is visually hidden/invisible on the result page, affecting accessibility and heading hierarchy navigation | https://www.loom.com/share/aa5792d14be14b40a25fdd24e868538f |  | P2 |  | Open |  |  | Failed | 2026-05-28 | Issue reproduced; primary H1 heading is not properly visible/accessibly rendered on the result page
6 | 2026-05-28 | Desktop | Edge | md | Nu HTML Checker validation passed successfully with no HTML errors or warnings detected | https://www.loom.com/share/your-link |  | P3 |  | Closed |  |  | Passed | 2026-05-28 | Verified in Nu HTML Checker; document completed with no errors or warnings
7 | 2026-05-28 | Desktop | Edge | md | Visible focus indicator is working correctly during keyboard navigation accessibility testing | https://www.loom.com/share/a9060412f95240d194ef5a840ad99370 |  | P3 |  | Closed |  |  | Passed | 2026-05-28 | Verified that interactive elements show clear visible focus state during keyboard navigation
8 | 2026-05-28 | Desktop | Edge | md | Link accessibility fails in Frequently Asked Questions section due to unclear/generic link text such as "Click Here" and "Extra Link" |  |  | P2 |  | Open |  |  | Failed | 2026-05-28 | Issue reproduced; FAQ links are not descriptive and reduce accessibility/usability for screen reader users

## Sampreets Findings
Defect no | Date | Browsers | Font Size | Device | Priority | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Assigned To | Dev Status | Dev Remark | Status | Last Tested On | QA Remark
SP_016 | 2026-01-07 | All Browsers | - | All Devices | P2 | Here are 4 Recommended Cards for you --> "Our Pick" tag label --> The label font weight needs to be 400 instead of 800 as per the design | https://www.loom.com/i/47097144117042398cba09d0dcdbbfed | https://www.loom.com/i/d29a3495c6174d67a3ff276bf508444f | Bharat | Need Discussion | 12/5/2026 - It's same as in mobile in design you can see it's bold in mobile view | Need Discussion | 2026-05-13 | 13/05/2026 - 700 weight is even more than the card titles & sub titles 30/04/2026 - 700 weight is even more than the card titles & sub titles 19/02/2026 - 700 weight is even more than the card titles & sub titles
SP_057 | 2026-02-19 | All Browsers | - | Desktops | P3 | Windows Narrator --> When going from 3rd Step to 2nd Step, user presses the tab button and the focus goes to the tabs that were present in the 3rd tab | https://www.loom.com/share/d5dc3145240c408e98c54af6d76615fd | - | Bharat | Fixed |  | Reopen | 2026-05-22 | 22/05/2026 - Pressing F on keyboard still takes the focus to the actionable items present in the next steps while user stays on the current step - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html 13/05/2026 - Issue reopened because while being on 2nd step if user keeps pressing the button F which is a shortcut to traverse through all form fields, then the 3rd step checkboxes start to get focused while being on the 2nd step itself - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html 13/05/2026 - Issue Resolved - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html
SP_063 | 2026-02-20 | All Browsers | - | Desktops | P2 | Windows Narrator --> Step 3 --> Blind user won't have any idea that he needs to select atleast 1 benefit for the "Show me my card" button to work. When the button is disabled and user focuses on it and clicks enter, it redirects to the back button on the top left. | - |  | Bharat | Fixed |  | Need Discussion | 2026-05-13 | 13/05/2026 - "Select up to 3 benefits" still doesn't get narrated if user quickly traverses through the tabs before it could get announced or if user goes back a step and lands again on the 3rd step. Instead, the "Show me my card" button should've always remain enabled and if user pressed enter when it is in focus while not having at least 1 benefit selected, then it should narrate, "Please select at least 1 benefit you are interested in to move forwards" - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html
SP_065 | 2026-02-23 | All Browsers | - | All Devices | P3 | Step 1 --> Bar Tick Labels --> In case the text is changed for each bar ticks and it's character length is more or less than the current bar ticks, there is no guarantee whether the bar tick labels will be center aligned with the bar ticks | https://loom.com/i/776ce7dbdbc54832b037c1db11576a84 https://loom.com/i/c78d6330e3eb4ecea605bd783dc88d97 |  | Bharat | Need Discussion | There are no proper solution for this because labels are on absolute position and they are independent from bar | Need Discussion | 2026-05-13
SP_073 | 2026-04-30 | All Browsers | - | All Devices | P2 | Here are 4 Recommended Cards for you --> We have added glow effect, gradiance shadow at the background of each card face for having a distinction between cards having the same color as the background in whichever section they appear across the website (handled for both dark & light theme already) but the same is missing in the simplifier page. | https://www.loom.com/i/3d4320096f1140b7a1ab044dcdaf4938 | - | Bharat | Fixed | 1/5/2026 - Fixed | Reopen | 2026-05-22 | 22/05/2026 - Same as mentioned on 13th May QA Remark - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html 13/05/2026 - Now the glow gradiance is going out of the container and at the same time appearing on top of the card making the card face whitish. Need to refer the css of the compare-cards as it was discussed and decided that we will only follow box shadow and invert the values in case of dark mode - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html
SP_077 | 2026-04-30 | All Browsers | - | All Devices | P3 | Here are 4 Recommended Cards for you --> Shadow image below card faces. Extra gap present between the card face and the shadow image when compared with the design and other pages like compare cards etc. | https://www.loom.com/i/c7cdfffcbc774a6f856574debc72a530 | - | Bharat | Fixed | 13/5/2026 - Please check now | Reopen | 2026-05-22 | 22/05/2026 - The card face images still overlap with the shadow image at the bottom the shadow image doesn't match with shadow image used below the card faces in compare cards - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html https://www.loom.com/i/65664ad075be418bb8d4b13a81a41ca9 13/05/2026 - Now the card face image overlaps with the shadow image at the bottom - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html https://www.loom.com/i/65664ad075be418bb8d4b13a81a41ca9
SP_078 | 2026-04-30 | All Browsers | - | All Devices | P3 | Dark Mode --> 3 Card stack image with the Section Title. In case of white mode, the image has grey shadow effect & gradiance effect at the edges but the same is missing in the dark mode. In case of dark mode, we have have white low shadow & glowing effect | https://www.loom.com/i/0a48c3fdba3c4222a023920d4fb606f9 | - | Bharat | Need Discussion | 11/5/2026 - The shadow is embedded within the image itself. If we need to modify the shadow for dark mode, we would have to use a separate image specifically for dark mode, which would unnecessarily require maintaining two image assets. Since the current appearance is acceptable, we can consider leaving this as is. | Need Discussion | 2026-05-13 | 13/05/2026 - Need to discuss the Dev Remark with Arun sir and keep the bug on hold as discussed with Bharat.
SP_085 | 2026-04-30 | All Browsers | - | All Devices | P2 | 3rd Step --> Show my Cards button --> The button's UI for the disabled state doesn't make the button appear disabled. Instead, the same disabled UI style followed for the compare button in the catalogue page can be followed here - background - #E5E7EA & font - #666666 | https://www.loom.com/i/f2b2a0c13f8e44ffb3f9a8d09f4876f0 | - | Bharat | Fixed |  | Reopen | 2026-05-22 | 22/05/2026 - While in disabled state, the button needs to have some sort of border to distinguish it from its background. Plus the stop hover effect is not required, user should be able to click on it and know the reason of the button being disabled. 13/05/2026 - Even in disabled state, the border colours are still purple instead of #666666 and the mouse icon changing to stop icon while hovering on the button needs to be removed as the button is not actually disabled, it does get clicked and the reason for page not moving forward is highlighted - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html https://loom.com/i/0e1bcb56e7ce4997861119a5e395d789
SP_088 | 2026-04-30 | All Browsers | - | All Devices | P2 | 2nd/3rd Step --> Click on back button --> Notice the animation of how the previous slide appears --> Click on the Next button --> Notice how the next slide appears. The animation for previous slide and the next slide is not the same. | https://www.loom.com/share/789614a012be4c15ab2448fc5951ecc0 | - | Bharat | Need Discussion | 12/5/2026 - The slide animation cannot be the same in both directions because the card visibility state is different during each transition. When the Next button is clicked, the upcoming slide is already partially visible behind the current slide as part of the card stack. But when the Back button is clicked, the previous slide is completely hidden and needs to re-enter from outside the stack. | Need Discussion | 2026-05-13 | 13/05/2026 - Need to discuss the Dev Remark with Arun sir and keep the bug on hold.
SP_094 | 2026-04-30 | All Browsers | - | Desktops | P2 | Here are 4 Recommended Cards for you --> In case of less than 4 cards in the results, the cards should center align in the container. | https://www.loom.com/i/342cefc449e5456d994c234d7c789807 | - | Bharat | Fixed | 13/5/2026 - Please check now | Reopen | 2026-05-22 | 22/05/2026 - Issue still the same as mentioned in 13th May Remark - https://navajowhite-crow-447925.hostingersite.com/simplifier-v3/simplifier.html 13/05/2026 - The layout breaks - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html# The card container doesn't remain center aligned in case only 1 card appears in the results for tablet / iPad breakpoints - https://loom.com/i/70645cb5e10841ce92134019d893fb71 For Desktops between 1201px - 1680px, the layout completes breaks if less than 3 cards appear in the result and the font size is set to smallest - https://loom.com/i/82677eb3a9a540cdaad50eab498b9a52 For 1681px and above, the layout breaks when less than 3 cards and for all font sizes - https://loom.com/i/ab23d73402cf44b584ae74832a87ef46
SP_095 | 2026-04-30 | All Browsers | - | Touch Devices | P2 | Touch Devices --> Dark Mode --> All 3 Steps (Slides) --> Every time user scrolls down, the bottom of the slide container shrinks for a noticeable moment before going back to normal. | https://www.loom.com/share/111b66da3a9f45ed83b97878962d7716 | - | Bharat | Fixed |  | Need Discussion | 2026-05-13 | 13/05/2026 - The issue mentioned in the description is still observable on real devices - https://navajowhite-crow-447925.hostingersite.com/simplifier-v2/simplifier.html#
SP_099 | 2026-05-13 | All Browsers | - | Desktops | P2 | Step 1 --> Annual Income Bar. When hovering over the thumb, the mouse should change to hand icon indicating that it is draggable to other values. When hovered on the rest of the bar except for the thumb, the mouse should change to finger icon indicating that the value can be changed by clicking. | https://www.loom.com/i/f5df3e513a274ee5aede77c021544781 | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_100 | 2026-05-13 | All Browsers | - | All Devices | P2 | Here are 4 Recommended Cards for you --> Our Pick --> The modal should be free to have any content formatting and shouldn't have any default formatting like semibold etc. Also if it is formatted in an ordered list, then the <ol> tag & <li> should be used instead of <span>. It should also be able to have nested bullet points, anchors and strong tags if required. | https://www.loom.com/i/87f0d43372d843588cb06f429ec10b0d | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_101 | 2026-05-13 | All Browsers | - | All Devices | P2 | All 3 Steps --> Headings. The headings do not have <h> tag despite being a heading. Due to this, the slide headings won't get picked by narrators when blind users use the H key shortcut to traverse through all heading. | https://www.loom.com/i/33a3dd524b5d4d4e85483b964d37d734 | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_102 | 2026-05-13 | All Browsers | - | All Devices | P2 | Here are 4 Recommended Cards for you --> Apply Now CTA. The label should be horizontally center aligned instead of having gap between the text and the arrow icon | https://www.loom.com/i/92d840c7968d457495f6c8830099a66f | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_103 | 2026-05-13 | Firefox | Large | Desktops (staring 1351px width) | P3 | Firefox --> Desktops above 1351px width -->When the font size is larges, a slight gap appears below the sub-navigation header container & the breadcrumb below. | https://www.loom.com/i/fcbe2cb7425b4bdc9a7bbed74aebbc0c | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_104 | 2026-05-13 | Firefox | - | Desktops | P3 | Firefox --> Desktops --> Slightly scroll down the page --> Click on Next button or Show me my cards button --> Notice how the section doesn't auto scroll slightly like it does on other browsers to get the slide or section within in the viewport automatically | SBI Card - Google Chrome 2026-05-13 20-06-27.mp4 | - | Bharat | Fixed |  | Unresolved | 2026-05-22 | 22/05/2026 - Apart from the already mentioned bug description, now for all browsers, when user clicks on "Show me my cards" button, it doesn't auto scroll to the top for getting the "Here are Recommended Cards for you" section completely in the view.
SP_105 | 2026-05-13 | Firefox | - | All Devices | P3 | Firefox --> Desktops --> Select values on all the 3 steps --> Refresh the page --> Notice that the previously selected values still appear selected even after the page is refreshed unlike other browsers. | - | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_106 | 2026-05-13 | All Browsers | - | All Devices | P3 | Restart button's line height can be 1.1 instead of 1 to make it more vertically center-aligned. | https://www.loom.com/i/9159f8b001c74cfa892c1293d63bbb9f | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_109 | 2026-05-13 | All Browsers | - | Touch Devices | P2 | Real Touch Devices --> Here are 4 recommended cards for you --> Credit Card face images --> User no longer has the option to long press and get the options related to the image. | - | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_110 | 2026-05-13 | All Browsers | - | All Devices | P2 | Here Are The 4 Recommended cards For You --> This title "Here Are the 4 Recommended Cards For You" is #222222 in the design instead of blue. Please check QA Remark as the bug is updated as per the design change in the QA Remark. | https://www.loom.com/i/fc70e652351b431dbdd2258431a72d4c | - | Bharat | Need Discussion |  | Unresolved | 2026-05-22 | 22/05/2026 - As per the new design, the Heading - "Here Are 4 Recommended Cards For You" font colour should be #302B6C
SP_111 | 2026-05-13 | All Browsers | - | All Devices | P2 | All Steps --> Next & Show Me My Cards Button. The Button label goes uppercase by default. Need to remove the uppercase class from both the buttom element. | https://www.loom.com/i/b560212601694e728c6180f510cc207d https://www.loom.com/i/0335bd08d7c44ad1873daf5e546498d4 | - | Bharat | Need Discussion | 26/5/2026 - As discussed with Namita in internal call we are not removing uppercase class from button on all the pages all buttons should have in uppercase only | Unresolved | 2026-05-22
SP_112 | 2026-05-13 | All Browsers | - | All Devices | P2 | All Steps --> Next Button & Show Me My Cards Button. To much gap between the button label & the arrow icon. Button width can be reduced in order to have a normal gap between the too. | https://www.loom.com/i/59fe0b751b7949d99eeaa7b789ad1462 https://www.loom.com/i/220ddc08c36a44bf81d8abd0e8a1e0db | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_113 | 2026-05-13 | All Browsers | - | All Devices | P3 | Layout breaks at 1201px - https://loom.com/i/5c2299e6bd094288b44098702ee1da7e at 767px - https://loom.com/i/c637fdafa15944f39bb71e9b24a9d4b2 and at 1023px in case of small or large font - https://loom.com/i/ccf51071a1a94f0b968cb60af1fcc1ae | - | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_114 | 2026-05-13 | All Browsers | - | All Devices | P3 | Step 3 - Choose Your Interested Benefits --> Case when user already has 3 benefits selected and tries to select more, please add a toast alert or disclaimer alert mentioning "Only up to 3 benefits can be selected". | - | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_115 | 2026-05-13 | All Browsers | Small | Tablets, iPads | P2 | Tablets, iPads --> Here are 4 Recommended Cards for you --> Case when font size is smallest and the card title concludes within 2 lines then the card face top corner & the bottom shadow image leak out of its container. | https://www.loom.com/i/30f5c8f10c9c4daaba542254da1052e5 | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_116 | 2026-05-13 | All Browsers | - | All Devices | P2 | When blind users move back or forward to any of the steps, the step that he has lands after clicking on the button should also get narrated. Also, when landing on any of the step, should the focus go to the 1st actionable element in that step? | - | - | Bharat | Fixed |  | Unresolved | 2026-05-22
SP_117 | 2026-05-13 | All Browsers | - | All Devices | P2 | Step 3 --> Choose your interested benefits --> "Select up to 3 benefits" blinking border not really visible when no benefits are selected therefore the attention doesn't go there. Also, it should only blink when user tries to move forward without selecting at least 1 benefit, currently it by default keeps blinking until any benefit is selected | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBzUoSj1qZDQoxPC6Mxe1uOAfv-UrqhP91jugOH5LRsPXw?e=mfOQLd | - | Bharat | Need Discussion | 26/5/2026 - Button is in disable state and button is not allowing any cursor action when there is no benefits selected than how user will try to move forword | Unresolved | 2026-05-22
SP_118 | 2026-05-27 | All Browsers | - | Mobile Phones | P1 | Step 1 --> Annual Income Bar --> Select the last option - (Above 2 Lakhs). Notice how the page the page start to have horizontal scroll as soon as 4th income option is selected | MicrosoftTeams-video (3).mp4 | - | Bharat | Fixed
SP_119 | 2026-05-27 | All Browsers | - | Touch Devices | P2 | Step 1 --> Annual Income Bar -->The Rs. symbol and the circular line at its bottom is not visible | https://www.loom.com/i/374898c0fea54db2b8c313e17019436c | https://www.loom.com/i/881d2d3b63274f189ed6c505a7503e62 | Bharat | Fixed
SP_120 | 2026-05-27 | All Browsers | - | All Devices | P2 | Step 1 --> Annual Income Bar --> Selected Bar Tick --> The select bar tick's font color doesn't change to - #007817 as per the design | https://www.loom.com/i/143c6602bcd44c88b74d2b13a922ff45 | https://www.loom.com/i/e0002496b2354afaaf8c4e6b690ff5cf | Bharat | Fixed
SP_121 | 2026-05-27 | All Browsers | - | All Devices | P2 | Step 2 (Where Do You Spend The Most) --> When input box is checked, the background fill colour should be #e0f3f7 as per the design instead of #ebffff | https://www.loom.com/i/1a94cd0b045f4ff4a903e5125d3b105e | https://www.loom.com/i/38489c457ebc43c3b118f5eb73344cff | Bharat | Need Discussion | 28/5/2026 - it's because design color was giving error in accessbilty extension
SP_122 | 2026-05-27 | All Browsers | - | All Devices | P2 | Step 2 (Where Do You Spend The Most) --> When input box is checked, the border colour doesn't change to #8dbcec | https://www.loom.com/i/9c4e9d0f4c9646d9b46598860c90790d | https://www.loom.com/i/dd4e4a1057dd421eb41bdcb7129449ab | Bharat | Fixed
SP_123 | 2026-05-27 | All Browsers | - | All Devices | P2 | Step 2 (Where Do You Spend The Most) --> When input box is checked, it doesn't get the box shadow effect as shown in the design | https://www.loom.com/i/8dd72caa08ce41a68a623447f0db2ce5 | https://loom.com/i/b0b4430361654b4da69d4b77c2ccac4b | Bharat | Fixed
SP_124 | 2026-05-27 | All Browsers | - | All Devices | P2 | Step 2 (Where Do You Spend The Most) --> When input box is checked, the check box heading fails the colour contrast ratio | https://www.loom.com/i/1c9f7eaf93fb4840a5c5d398ff934202 | - | Bharat | Need Discussion | 28/5/2026 - You can close this bug as discussed in our internal call
SP_125 | 2026-05-27 | All Browsers | - | All Devices | P2 | Step 2 (Where Do You Spend The Most) --> When input box is checked, the sub-text font colour fails the colour contrast of 4.55 | https://www.loom.com/i/fce1d5d35be74a778511a02c3e20fbb2 | - | Bharat | Need Discussion | 28/5/2026 - You can close this bug as discussed in our internal call
SP_126 | 2026-05-27 | All Browsers | - | Desktops | P2 | Step 2 (Where Do You Spend The Most) --> The left & right padding of the input boxes' grid container should be 20px instead of 10px as per the design | https://www.loom.com/i/93bd6f456533437288861c9c3dc1ff16 | - | Bharat | Fixed
SP_127 | 2026-05-27 | All Browsers | - | Tablets / iPads | P2 | Step 1 --> Annual Income Bar --> The unselected bar tick's position goes slightly to the bottom instead of staying vertically center aligned | https://www.loom.com/i/f40bb19d0db644de80f0c7be6c4579ea | - | Bharat | Fixed
SP_128 | 2026-05-27 | All Browsers | - | Desktops | P3 | Dark Mode --> Keyboard Accessibility --> Here are 4 Recommended Cards 4 you --> Apply Now & See Benefits CTA. When the keyboard focus is on the See Benefits CTA, the focus outline blends with the UI due to which the button doesn't appear to be in focus. | https://www.loom.com/i/4229dd320db844d3991b7d6749c90618 | - | Bharat | Fixed
SP_129 | 2026-05-27 | All Browsers | - | Desktops | P2 | Keyboard Accessibility --> Step 1 --> Focus the bar thumb through keyboard. The focus outline of the bar thumb is not properly visible making the user unsure where the keyboard's focus is | https://www.loom.com/i/057ee2b616e14d4c9dde48aadb8639de | - | Bharat | Fixed
SP_120 | 2026-05-27 | All Browsers | - | Mobile Phones / Tablets, iPads | P3 | Step 1 --> Annual Income Bar --> The white border line across the bar is present in case of desktops but missing for mobile & tablets, check the actual vs expected screenshots. | https://www.loom.com/i/fe36908c3f5f4e15b2047aecdfb8ffed | https://www.loom.com/i/3339f44d240e4aa797b48894bce46d78 | Bharat | Fixed
SP_131 | 2026-05-27 | All Browsers | - | All Devices | P2 | Dark Mode --> Step 1 --> Annnual Income Bar --> The selected Bar tick's speech box keeps its white background and missing its shadow effect in dark mode. It should change to dark background and the dark shadow effect should be inverted to bright shadow in case of dark mode | https://www.loom.com/i/613a43dd662c4519b937f34dc64b886d | - | Bharat | Fixed
SP_132 | 2026-05-27 | All Browsers | - | All Devices | P2 | Dark Mode --> Step 1 --> Annual Income Bar --> The Bar's gradiance, Rs. icons and other details still remain bright themed when in dark mode. | https://www.loom.com/i/b45dafa37383412aa108ad5bebcbccbb | - | Bharat | Need Discussion
SP_133 | 2026-05-27 | All Browsers | - | Desktops | P3 | Dark Mode --> Step 2 (Where Do You Spend The Most) --> Hover on a selected check box. The Check boxs' heading's font colour fails the colour contrast when hovered on the checkbox | https://www.loom.com/i/daaa9e2672f3414eb21b91b9a18364e5 | - | Bharat | Fixed
SP_134 | 2026-05-27 | All Browsers | - | Desktops | P3 | All 3 Steps --> Hover over Next & Show me my cards button --> The buttons are missing their hover effect where the arrow moves in its position. Please refer the hover effect of the CTAs on already delivered pages. | https://www.loom.com/i/eabf47c2789d4413b219bd3694ec41b8 | - | Bharat | Fixed
SP_135 | 2026-05-27 | All Browsers | - | Desktops | P3 | Dark Mode --> Step 3 (Choose Your Interested Benefits) --> Hover on a selected tab. The tabs label font colour fails the colour contrast when hovered on it. | https://www.loom.com/i/9a9c3d8a0697465ea5740c89b43ab629 | - | Bharat | Fixed
SP_136 | 2026-05-27 | All Browsers | - | Desktops | P3 | Step 2 (Where Do You Spend The Most) --> In this new changed layout, in case when the Checkbox heading is lengthier, it has a chance of breaking the UI in case of mobile phones & tablets | https://www.loom.com/i/8060920167ac46d7ab333e89448a53e9 https://www.loom.com/i/6b887632daad4e8ca47d786e06cceacb | - | Bharat | Fixed
SP_137 | 2026-05-27 | All Browsers | - | All Devices | P3 | Step 2 (Where Do You Spend The Most) --> The check box's size and the tick mark when checked doesn't exactly match with the design | https://www.loom.com/i/894758d9381544c7a98645ca98191879 | - | Bharat | Need Discussion | 28/5/2026 - Checbox size is reduced to maintain in one fold
SP_138 | 2026-05-27 | All Browsers | - | Desktops | P1 | All 3 Steps --> For Desktops, the entire section has been scaled down to 75% in order to fit it in the viewport of all desktop screens but due to this, the readability of the content & icons in the steps have gotten affected, their unsual scaled down view looks odd and inconsistent with the final result - "Here are 4 Recommended Cards for You" | https://loom.com/i/a3367075f36043a3846b21777706e9e1 | - | Bharat | Need Discussion
SP_139 | 2026-05-28 | All Browsers | - | Desktops | P2 | Here Are 4 Recommended Cards for You --> The gap between the card containers is less than required when compared with the design. Also, the grid container has more than neccessary left & right margin from the design. Due to this, the card container shadow effects are overlapping on top of each other. Please check the actual vs expected result to fix the issue. | https://www.loom.com/i/e34e0438735d4a32b033827442611bec | https://loom.com/i/bc71c64d717e4194bd458c534a7985ba | Bharat | Need Discussion
SP_140 | 2026-05-28 | All Browsers | - | Desktops | P2 | Screen Readers --> Step 1 (What is your Annual Income?) --> Focus the thumb --> While on 1st bar tick, press left button. The narrator announces "No Income Select" but the thumb remains on the 1st bar tick and user is able to proceed to the next step. User shouldn't be able to have "No Income Selected" | - | - | Bharat | Fixed
SP_141 | 2026-05-28 | All Browsers | - | All Devices | P3 | Here Are 4 Recommended Cards for You --> Card Face Alt Text --> Although related to content, we can still keep the alt-texts updated according to the actual card's image instead of static "SimplySave" for all cards. | https://www.loom.com/i/0a662fcf031b4adab4fe1d5f113908db | - | Bharat | Fixed
SP_142 | 2026-05-28 | All Browsers | - | Desktops | P1 | Systems between 1201px - 1280px are going to have height around 800-900px. There is a CSS media-query that applies the property min-height: calc(100vh - 120px) because of this, the section's height increases unneccesarily introducing empty space at the bottom. This property needs to be removed. | https://www.loom.com/i/6a6820e58cd8488196a7608b5b0b861c | - | Bharat | Fixed | 29/5/2026 - This property can't be removed because there are systems available where the approximate height is around 700px, so height-based media queries can't be reliably written. Now the section has been vertically center aligned, so this issue should no longer occur.
SP_143 | 2026-05-28 | All Browsers | Small | Desktops | P2 | Step 1 (What is Your Annual Income?) --> Small font --> Notice how the step's container doesn't have any padding at the bottom as a result, either UI breaks or no gap is visible at the bottom breaking the visual balance | https://www.loom.com/i/674a94a759014859bba53bc915f1e5e4 | - | Bharat | Fixed
SP_144 | 2026-05-28 | All Browsers | Default / Large | Tablets / iPads | P2 | For Tablets & iPads, extra gap/empty space observed in case of default & large font for each of the 3 steps on Tablets & iPads. Step 1 - https://www.loom.com/i/105a9893db374f85b4f97f9611ac7b66 Step 2 - https://www.loom.com/i/4511fc684d6b441e99c3fa1b0190078c Step 3 - https://www.loom.com/i/4a7c97941db84c4fa7f5b3e19ec8b8d6 | Step 1 - https://www.loom.com/i/105a9893db374f85b4f97f9611ac7b66 Step 2 - https://www.loom.com/i/4511fc684d6b441e99c3fa1b0190078c Step 3 - https://www.loom.com/i/4a7c97941db84c4fa7f5b3e19ec8b8d6 | - | Bharat | Need Discussion
SP_145 | 2026-05-28 | All Browsers | Default / Small | Mobile Phones | P2 | For Mobile Phones, extra gap/empty space observed in case of default & small font size for each of the 3 steps. Step 1 - https://www.loom.com/i/6b04d7799d2e4efcb413428f70aaa17f Step 2 - https://www.loom.com/i/c1e54d9a42504b2e8a1294c465bbbae2 Step 3 - https://www.loom.com/i/a0f12dba2d5143acb55d91dfcd12c22f | Step 1 - https://www.loom.com/i/6b04d7799d2e4efcb413428f70aaa17f Step 2 - https://www.loom.com/i/c1e54d9a42504b2e8a1294c465bbbae2 Step 3 - https://www.loom.com/i/a0f12dba2d5143acb55d91dfcd12c22f | - | Bharat | Need Discussion
SP_146 | 2026-05-28 | All Browsers | - | All Devices | P2 | Following Text are not selectable through mouse/touchpad or touch screen - 1. Section Heading & Sub-Heading - Find The Perfect Credit Card - Answer 3 quick questions to find your best cards - https://www.loom.com/i/d0c8e581cb11440aa3ec28d4f40e207f 2. Step 1(What is Your Annual Income?) --> Bar Tick Labels - https://www.loom.com/i/1fea1efeefc046ddba35febcadd4d604 3. Top Pick Tooltip heading & bullet points in the Here are 4 recommended cards for you - https://www.loom.com/i/637682b0470c493aa5bdfea94f40aa65 | https://www.loom.com/i/d0c8e581cb11440aa3ec28d4f40e207f https://www.loom.com/i/1fea1efeefc046ddba35febcadd4d604 https://www.loom.com/i/637682b0470c493aa5bdfea94f40aa65 | - | Bharat | Fixed
SP_147 | 2026-05-28 | All Browsers | - | Desktops, Tablets / iPads | P2 | The designs of the Icon besides the heading of 1st & 3rd Step are created such that they appear smaller compared to the icon used in the 2nd Step. Step 1 - https://www.loom.com/i/6dd17ce6707743a5acd9b701b5f62426 Step 3 - https://www.loom.com/i/fb312263f25a4c7abc712ff39a9b57e9 | Step 1 - https://www.loom.com/i/6dd17ce6707743a5acd9b701b5f62426 Step 3 - https://www.loom.com/i/fb312263f25a4c7abc712ff39a9b57e9 | - | Phulvinder
SP_148 | 2026-05-28 | All Browsers | - | All Devices | P2 | 3 Credit Card Stack image on the top right needs to be more sharper, without the dummy name - Milan Mathur and also in webp format instead of .png | https://www.loom.com/i/861c04540fc645a8b10abb3383e74817 | - | Phulvinder
SP_149 | 2026-05-28 | All Browsers | - | Touch Devices | P2 | 1st Step (What is your annual income?) --> While performing scroll or pinch gesture, if the initial touch is on any of the bar ticks, it gets selected even though user didn't intend to. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQAsci_7iHl1TIwKgxnsAfk1Af0V1LrOPzxdNsSQ6tf8eAQ?e=AmWmr9 | - | Bharat
SP_150 | 2026-05-28 | Firefox | - | Touch Devices | P3 | FireFox --> Here Are 4 Recommended Cards for You --> The Restart button container at the bottom stutters or jumps in its position when user scrolls up & down the page in case of touch devices on firefox. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQDO_IEy9NJYTaHAYr-oumu5AcmydZn3xdrkodHiU25jNAA?e=MfTSe3 | - | Bharat