## Sheet1
Defect no | Date | Device | Browsers (Chrome/firefox/Edge/Safari) | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark | URL
1 | 2026-05-04 | Desktop | Edge | md | Extra Link bold text is showing on Compare Cards page; this looks like wrong/placeholder text and should not be visible | https://www.loom.com/i/4ca5da2ff59c48afb5c8e829e5466bc3 | https://www.figma.com/design/TLF9L6filn2IlqNqohuVrW/SBI-CARD-MOBILE-latest?node-id=19847-2983&t=4rRDlNUEuGsQ55gE-1 | P2 |  | Open |  |  | Failed | 2026-05-04 | Issue seen again; wrong text is visible and not matching design | SBI Card
2 | 2026-05-04 | Desktop | Edge | md | Close (X) icon is not matching design; Figma shows simple "X" but site shows "X inside a circle" | https://www.loom.com/i/ba648689a94146b29b2a8e7430992318 | https://www.figma.com/design/TLF9L6filn2IlqNqohuVrW/SBI-CARD-MOBILE-latest?node-id=19847-2716&t=Y6WWyRmEgg6y0gtt-1 | P3 |  | Open |  |  | Failed | 2026-05-04 | Issue seen again; icon style is different from design | SBI Card
3 | 2026-05-04 | Desktop | Edge | md | Message "*These are just the key feature highlights..." should appear only after at least 1 card is added to comparison | https://www.loom.com/i/6dfec0c47e284408879c9ebfe5d8c937 | https://www.figma.com/design/TLF9L6filn2IlqNqohuVrW/SBI-CARD-MOBILE-latest?node-id=19847-3105&t=Y6WWyRmEgg6y0gtt-1 | P4 |  | Open |  |  | Suggestion | 2026-05-04 | UI improvement suggested; message visibility can be condition-based | SBI Card
4 | 2026-05-04 | Desktop | Edge | md | Tick icon is not matching design; Figma shows tick inside a circle but site shows only tick icon | https://www.loom.com/i/c140198bb389425fa92f4c9f25585b79 | https://www.loom.com/i/11b8cd4e4f704060b4a47d6010ceeb01 | P3 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; icon style is different from design reference | SBI Card
5 | 2026-05-04 | Desktop | Edge | md | Cross icon is not matching design; Figma shows cross inside a circle but site shows only cross icon. there should be a red cross icon | https://www.loom.com/i/de20ac222e334798817936e8fe7b5cc8 | https://www.loom.com/i/047eb6f5969d4e229730c7ddf54feff2 | P3 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; icon style is different from design reference | SBI Card
6 | 2026-05-04 | Desktop | Edge | md | Card name layout is not matching design; Figma shows card name in two lines on desktop but site shows it differently (two lines only in portrait or mobile screen) | https://www.loom.com/share/84f15a120e60403690e6b68e6132be04 | https://www.figma.com/design/TLF9L6filn2IlqNqohuVrW/SBI-CARD-MOBILE-latest?node-id=19847-2696&t=xqNin7qGHB4oMwQI-1 | P2 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; text wrapping behavior is inconsistent with design on desktop view | SBI Card
7 | 2026-05-04 | Desktop | Edge | md | Section headings spacing is not matching design; Figma shows left spacing for headings but site has no left space (content is too close to border) | https://www.loom.com/i/811d58db08d045e6b5a388e2b76747fd | https://www.loom.com/i/5f885cb881d34e0ba37cec991b64676b | P2 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; left padding/margin missing causing misalignment with design | SBI Card
8 | 2026-05-04 | Desktop | Edge | md | Content inside benefits box is not aligned as per design; Figma shows all 3 points properly fitted within box but site shows content at top with extra empty space at bottom | https://www.loom.com/i/7f92489db6f14dce8d08d7871d0117cc | https://www.loom.com/i/74cd593fbde442c684f0af1d70113872 | P2 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; vertical spacing is unbalanced with extra space at bottom causing UI inconsistency | SBI Card
9 | 2026-05-04 | Desktop | Edge | md | Button color is not matching design; Figma shows blue color for "Apply Now" button but site shows blue color on "See Benefits" button instead | https://www.loom.com/i/2afedc91bb5a453aa769e96c7a6a4f46 | https://www.loom.com/i/c63a034799b542cb849b8f0f84bb7bba | P2 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; button color styling is swapped compared to design | SBI Card
10 | 2026-05-04 | Desktop | Edge | md | Background image is not matching design; Figma shows different background style but site displays a different background image | https://www.loom.com/i/af0526c0366c422f92025685ee081497 | https://www.figma.com/design/TLF9L6filn2IlqNqohuVrW/SBI-CARD-MOBILE-latest?node-id=19851-2032&t=xqNin7qGHB4oMwQI-1 | P2 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; background design does not match Figma reference | SBI Card
11 | 2026-05-04 | Desktop | Edge | md | Featured and Lifestyle cards are not visible in Select Card popup; no data is displayed and shows "No Cards To Show" | https://www.loom.com/share/c6afcc1c5276459297c870e4396b5b37 |  | P1 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; expected card data is not loading in popup | SBI Card
12 | 2026-05-04 | Desktop | Edge | md | Select Card list shows same card multiple times and does not display all available cards; data duplication issue | https://www.loom.com/i/378037d499ad4dd2adab45d2d750bd89 |  | P1 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; duplicate entries visible and expected card list is not fully loaded | SBI Card
13 | 2026-05-04 | Desktop | Edge | md | Search functionality in Select Card popup is not working; entering text does not filter or update the card list | https://www.loom.com/i/e2acf72121a342beb546d9ed31647b51 |  | P1 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; search input does not return filtered results | SBI Card
14 | 2026-05-04 | Desktop | Edge | md | See Benefits CTA style is not matching design; Figma shows it as plain text link but site displays it in rounded/circular button style | https://www.loom.com/i/ef1db18cb25540cf8634cba068b4d42c | https://www.figma.com/design/TLF9L6filn2IlqNqohuVrW/SBI-CARD-MOBILE-latest?node-id=19786-2670&t=xqNin7qGHB4oMwQI-1 | P2 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; CTA styling differs from design reference | SBI Card
17 | 2026-05-04 | Desktop | Edge | md | Same card can be added multiple times in Compare section; duplicate card selection is allowed instead of restricting unique cards only | https://www.loom.com/share/229efd1167984e49ae744feb2bf23591 |  | P1 |  | Open |  |  | Failed | 2026-05-04 | Issue reproduced; duplicate cards are allowed in comparison causing incorrect compare behavior | SBI Card

## Sampreets Findings
Defect no | Date | Browsers | Priority | Font Size | Device | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Dev Status | Dev Remark | Status | Last Tested On | QA Remark
CC_062 | 2026-01-08 | Firefox | P2 |  | Touch Devices | Firefox Browsers --> Flickering issues is noticed. Top sticky section - "You are comparing" flickers when user scrolls down. Each row accordion flickers and clips the content inside it from the bottom when opened. | https://www.loom.com/share/75d94fe6acec40aeba5f12e2b9af5869 | - | Fixed |  | Reopened | 2026-05-04 | 04/05/2026 - The flickering issue still persists. 09/04/2026 - The "You are comparing" container flickers in firefox when user scrolls through the page slowly and the accordions auto expand in case the user starts the swipe gesture on top of the accordion but with the intention to scroll. 13/01/2026 - The accordion flickering issue is solved everywhere. The "You are comparing" flickering issue is resolved on all browsers except for "Firefox"
CC_067 | 2026-02-10 | Edge/Chrome/Firefox | P2 |  | All Devices | You Are Comparing --> Dark Mode --> Even when user switches to dark mode, the section and the table below it keeps following the light theme. | https://www.loom.com/i/8c73b698ffb24624b062130574539dcf | - | Fixed |  | On Hold | 2026-04-09 | 09/04/2026 - As discussed with Arun sir, need to first discuss this with Namita ma'am whether it is required to enhance dark mode or not.
CC_085 | 2026-04-03 | All Browsers | P2 |  | All Devices | Nu HTML Validator --> 14 errors found | https://loom.com/i/b0e61bbb0d9f4f2fbc0c70d223380a9e | - | Fixed | Only one error is coming which is in assistance section fix will be given with catalog fixes | Reopened | 2026-05-04 | 04/05/2026 - 5 new errors have now occurred in the nu html validator - https://loom.com/i/6adb6cfb32d341d3a1fd67dc784a994d 06/04/2026 - All the errors are resolved - https://loom.com/i/0e77d75da99c4df18f2587db5be80f3b
CC_092 | 2026-04-03 | All Browsers | P2 |  | Desktops | Turn on Windows Narrator --> Click on Add Card. Narrator focuses on an invisble element and narrates click here to download the SBI Card | https://www.loom.com/share/869f1ec8a4fd4b6b91c47a28280f8e9a | - | Fixed |  | Reopened | 2026-05-04 | 04/05/2026 - Reopening this issue because in the latest build, it annouces "Skip to main content" twice when the select card drawer opens - https://navajowhite-crow-447925.hostingersite.com/compare-cards-v1/compare-cards.html# 09/04/2026 - Check on call on both Sachin & Arun sir's system, the issue is not occuring therefore closing this issue. 09/04/2026 - It still focuses on an invisible element that may actually be breadcrumb as it says "Home/Credit Card/Comare Cards"
CC_093 | 2026-04-06 | All Browsers | P3 |  | All Devices | When user scrolls down, the "You are Comparing" container height gets reduced but the position of the table below remains the same. As a result a gap appears between the container & the table. The gap is noticeable and doesn't get covered until user scrolls down further. | https://www.loom.com/share/050792cb6b544d5a89a349ce2d6e3601 | - | Fixed |  | Reopened | 2026-05-04 | 04/05/2026 - While at the top of the section, if user scrolls down ever so slightly such that the "You Are Comparing" section contracts but the header sub-navigation menu remains, then the comparison table doesn't adjust its position and a gap appears between the top section and the table. Similar thing happens in case of touch devices and it also happens sometimes while user is zooming in & out using the pinch gesture - https://navajowhite-crow-447925.hostingersite.com/compare-cards-v1/compare-cards.html# https://www.loom.com/i/03696b3303a34ef785723da0bebe29b8 09/04/2026 - The issue is resolved on - https://navajowhite-crow-447925.hostingersite.com/compare-cards-final/compare-cards.html# 09/04/2026 - Now this issue occurs in case of all devices.
CC_095 | 2026-04-06 | All Browsers | P2 |  | All Devices | Run the lighthouse test using the broser inspect tools --> Check the performance score in the report. The performance score is not acceptable both for desktops & for mobile phones. | - | - | Need Discussion |  | On Hold | 2026-05-04 | 04/05/2026 - As dicussed, Arun sir has already acknowledged the performance issue and informed that this will be taken care of later as we currently need to deliver the page on priority. Therefore, need to keep the bug on hold.
CC_103 | 2026-04-09 | All Browsers | P2 |  | All Devices | Currently there is no main content in the HTML therefore clicking on the skip to main content in the header doesn't shift the focus to any element and simply starts from the header itself. | https://www.loom.com/i/c0ac2c65c4684128af62327c707e4bdc | - | Fixed | Breadcrumb have been added now rest issue need to be fixed in entire website | Reopened | 2026-05-04 | 04/05/2026 - In case of touch devices, clicking on skip to main content doesn't shift the focus to the main section. (It should've focused on the breadcrumb like it does in case of desktop but the breacrumb is missing in case of touch devices for now - https://navajowhite-crow-447925.hostingersite.com/compare-cards-v1/compare-cards.html
CC_105 | 2026-04-09 | All Browsers | P3 |  | Desktops | Select Card Drawer --> Windows Narrator --> When Cross button is in focus, it narrates it as "cross" buton at the add also mentions "scan". In case when no card is available in the drawer, the tab focus goes out of the drawer while it remains open. When user closes the drawer using cross button, the narrator focus doesn't land back on the add cards button. | - | - | Fixed | As per various searches i have done, tell scan to any element is not a bug. | Reopened | 2026-05-04 | 04/05/2026 - As per the dev remark, scan is not an issue. However, the narrator able to focus on the FAQ question while the drawer remaining open is still an issue 09/04/2026 - i.) The narrator still annouces "scan" but not only on cross button but on search & drop down as well. ii.) User when inside the "Select Card" drawer and no cards available in the list, moving through the drawer, narrator annouces "What is a credit card" which is the first question of the FAQ section. It does it while drawer already open. iii.) When user selects a card to add, the tab focus doesn't land on the next "Add Card" button or the card CTA, instead lands on the "Extra Link" in the table or the FAQ.
CC_113 | 2026-04-21 | All Browsers | P2 |  | All Devices | Remove All Cards --> Notice the Table disclaimer still remains visible even when there are no cards added | https://loom.com/i/681c2d36e90848f3b26c15cd327fda90 | - | Need Discussion
CC_114 | 2026-05-04 | All Browsers | P2 |  | All Devices | Skip to main content --> Click on skip to main content hides the header container but the "You Are Comparing" container doesn't adjust its position and a gap appears above it | https://www.loom.com/i/ccbef90702dd496293540747e5c1172b | -
CC_115 | 2026-05-04 | All Browsers | P1 |  | Touch Devices | "You Are Comparing" section --> Breadcrumbs are missing in case of touch devices | https://www.loom.com/i/6baebdd895e04b5ca892124685911058 | -
CC_116 | 2026-05-04 | All Browsers | P2 |  | All Devices | "Select Card" Drawer --> Select Category Dropdown --> The scroller of the dropdown is out of its container and its UI could've been the same as the scroller used in the exclusive privileges section's tooltip container | https://www.loom.com/i/152d4d3108d343928eb2b6473cc386c2 | -
CC_117 | 2026-05-04 | All Browsers | P3 |  | All Devices | "Select Card" Drawer --> Select Category Dropdown --> The Dropdown doesn't give an impression that it has more options that user can access apart from the 6 that are visible. | https://www.loom.com/i/152d4d3108d343928eb2b6473cc386c2 | -
CC_118 | 2026-05-04 | All Browsers | P2 |  | Touch Devices | Touch Devices --> Comparison Table --> Accordions --> When only 1 or 2 cards are added, the bordor on the extreme right of the accordion container is not required. It is especially visible in case of dark mode. | https://www.loom.com/i/e5a6e4175b734fcb8c932554e6e540fb https://www.loom.com/i/0a4c64a3c8634ecc8053c8a847ea49ce | -
CC_119 | 2026-05-04 | All Browsers | P2 |  | Touch Devices | Dark Mode --> Touch Devices --> Comparision Table --> Accordions --> The arrow icons of the accordions need to change their colour to a ligher one in case of dark mode. | https://www.loom.com/i/47b7258d829b4c3ebf7c777aa42a226e | -
CC_120 | 2026-05-04 | All Browsers | P2 |  | All Devices | Dark Mode --> Select Card Drawer remains light themed even in case of dark mode. | https://loom.com/i/701fde0abc9f45cf9ab6644e1d28c92d | -
CC_121 | 2026-05-04 | All Browsers | P2 |  | All Devices | Dark Mode --> All Devices --> The background fill color for the containers is lighter when compared with the - #111010 color used in simplifier & 404 page. | https://www.loom.com/i/46244edbc3e1416cbd52e0f2d653c9ad | -
CC_122 | 2026-05-04 | All Browsers | P2 |  | All Devices | Dark Mode --> All Devices --> Comparision Table -->The gridline colours appear too bright getting even more emphasized in dark mode then they do in light mode. Need to darken them a bit in case of dark mode. | https://www.loom.com/i/70aa541532884b948854f0f27b8c7f63 | -
CC_123 | 2026-05-04 | All Browsers | P2 |  | Touch Devices | Dark Mode --> 1 Card Slot Empty --> Add Card button. The add card button should have a lighter UI in order to be visible in case of dark mode | https://www.loom.com/i/9bebd2f0a4214d0f8aa53f817ebcc32d | -
CC_124 | 2026-05-04 | All Browsers | P2 |  | All Devices | Dark Mode --> You Are Comparing section --> The section container, The card slot container & the card face should have a light colour glow or shadow effect, CTAs should have dark mode UI and the background-colour of the containers should be dark, we can have light border if they still blend in too much with their parent container's dark background. | https://www.loom.com/i/a17d221ed9f34d2d92017cadf418f5fe | -
CC_125 | 2026-05-04 | All Browsers | P3 |  | All Devices | Dark Mode --> Remove all cards from the slots --> Check the background circle of the no-data.svg image. The circle's colour is a little too bright. Same colour recommended for the container background fill can be used for this as well - #111010 | https://www.loom.com/i/2be7ef79409a4f58a8e6c3a1a6b6fdfd
CC_126 | 2026-05-04 | All Browsers | P2 |  | Desktops | The comparision table container has bottom border but not the left, right & top border. Either the bottom border should be removed as it is in the design and if purposefully added then it should be for all 4 sides. This is especially evident in case of dark mode | https://www.loom.com/i/f4f406188cd0496eb64cbc0d037d71e6 | -
CC_127 | 2026-05-04 | All Browsers | P2 |  | Desktops | Breadcrumbs --> There is no underline under the hyperlinks of the compare cards breadcrumb but we have it in the bread-crumbs of other pages. | https://www.loom.com/i/3da8e4a16e114069a44046cd1935b43b | https://www.loom.com/i/97604c6df3c94fd2b3810e4a4c350cba
CC_128 | 2026-05-04 | All Browsers | P2 |  | Desktops | Breadcrumbs --> The last hyperlink of the breadcrumb is the page itself and that too is clickable in compare cards but that is not the case in other pages. | https://www.loom.com/i/3da8e4a16e114069a44046cd1935b43b | https://www.loom.com/i/97604c6df3c94fd2b3810e4a4c350cba
CC_129 | 2026-05-04 | All Browsers | P2 |  | Desktops | Breadcrumbs --> Font size of the breadcrumbs on Product Details & Catalogue page is smaller and the forward slashes do not match as well | https://www.loom.com/i/3da8e4a16e114069a44046cd1935b43b | https://www.loom.com/i/97604c6df3c94fd2b3810e4a4c350cba
CC_130 | 2026-05-04 | All Browsers | P2 |  | Desktops | Breadcrumbs --> On other pages, the breadcrumb is situated in its own separate container that has a gradiance (black to white fade out) effect as well. The same is not followed in the compare-cards page | https://www.loom.com/i/3da8e4a16e114069a44046cd1935b43b | https://www.loom.com/i/97604c6df3c94fd2b3810e4a4c350cba
CC_131 | 2026-05-04 | All Browsers | P2 |  | All Devices | Accessibility Checker --> The checker highlights 7 instead fails for aria-hidden-focus which stats hidden elements should not be focusable | https://loom.com/i/5f55ac7ffd834818a69d6488d1362879 | -
CC_132 | 2026-05-04 | All Browsers | P2 |  | All Devices | Accessibility Checker --> Select Card Drawer. The selected category in the dropdown list fails the colour contrast level and the tick mark image doesn't have an alt-text | https://www.loom.com/i/61aebc015db344b4a5d0654f88ee2676 | -
CC_133 | 2026-05-04 | All Browsers | P2 |  | All Devices | You Are Comparing --> Section Title, Card Titles & Tag background fill --> Instead of #0094D9, the new blue colour that meets the contrast level - #0077af should be used to maintain consistency and to pass WCAG 2.1 AA standards for colour contrast | https://www.loom.com/i/3b8429d795744207ad1cb3fc399b0f04 | -
CC_134 | 2026-05-04 | All Browsers | P2 |  | All Devices | You Are Comparing --> Keep 1 or 2 card slots empty --> Scroll down the page for triggering the "You Are Comparing" section to get contracted while aking sure the comparison table remains inside the viewport --> Click on Add Card --> Without adding any card, click close the drawer --> Notice how some of the rows go beneath the "You Are Comparing" section and are not accessible. User has to scroll down once in order to resolve the issue. Same issue occurs when card slots are empty, section is contracted and user adds his first card for comparison | https://www.loom.com/share/6c3d09c5026846dfbcf44bde39ead4d0 | -
CC_135 | 2026-05-04 | All Browsers | P2 |  | All Devices | Comparision Table --> Instead of bullet points, special characters are now appearing for the sentences - For ex: check the "Welcome Benefits" row | https://www.loom.com/i/221a02de1e8f4493aac2f2a8028f0580 | https://loom.com/i/ce32c05b57634e29b4228fe1780fa760
CC_136 | 2026-05-04 | All Browsers | P2 |  | All Devices | Reduce the font size to smallest --> Make sure some cards added in the slot --> Scoll down till the comparison table remains in the viewport --> Notice the slight gap just above the "You are comparing" section right after it gets contracted. Through this gap, the table contents are visible while scrolling - This is more evident in dark mode. This starts to happen as soon as the section gets contracted | https://www.loom.com/i/21396414ec4441ae8874f64c1e6b3987 | -
CC_137 | 2026-05-04 | All Browsers | P2 |  | Touch Devices | Real Touch Devices --> Comparison Table --> Case when tick or cross icons are present along with the content inside any cell of the comparison table, instead of being present on the top of the content, they go extremely small and besides the text content. For ex: Fuel Surchage Waiver row --> 2nd & 3rd cell. Check out the screenshot for better understanding. | https://www.loom.com/i/ed09761410614928a6b00cf41a9c87e1 | -
CC_138 | 2026-05-04 | All Browsers | P2 |  | Mobile Phones (Landscape Mode) | Real Touch Devices (Landscape Mode) --> Select Card Drawer --> Select Category dropdown. The dropdown goes out of the view port and some of its options present later in the list are go unaccessible. | https://www.loom.com/i/7d8a3d19c5974fc69365196dccfea6c7 | -
CC_139 | 2026-05-04 | All Browers | P2 |  | All Devices | Dark Mode --> Case when no content present in the cell the hyphen symbol is used "-" this hypen symbol doesn't change its colour in case of dark mode | https://www.loom.com/i/2057c33211994fca9ce5bd5dc798a8ee | -
CC_140 | 2026-05-04 | All Browsers | P3 |  | Touch Devices | Scroll down more than half the comparistion table and make the header containers disappear and "You Are Comparing" section contracts --> Scroll up until the header containers appear back. While the header containers appear back, notice how the "You Are Comparing" section takes its new position even before the header containers have appear completely as a result for a slight moment table content beneath are visible in the space above the "You are Comparing" section. This could be prevented if the "You Are Comparing" section adjusted its position at the same time and in the similar manner like the header containers do (like sliding back in) | https://www.loom.com/share/111b66da3a9f45ed83b97878962d7716 | -
CC_141 | 2026-05-04 | All Browsers | P3 |  | Mobile Phones (Landscape Mode) | Mobile Phones with Height above 767px --> Get to the top of the viewport --> Rotate to Landscape mode -->Notice the gap that appears above the "You Are Comparing" section | https://www.loom.com/i/1466f09d06394a7686a20e5eca382d5f | -
CC_142 | 2026-05-04 | Firefox | P3 |  | Desktops | Select Drawer --> Drawer Scroll bar & the Select Category dropdown scrollbar --> The Scroll bar UI needs to be the same as it is on other browsers | https://www.loom.com/i/8504464eabcc426691185fdb078936ec | -
CC_143 | 2026-05-04 | All Browsers | P2 | Large/Default | Desktops (1024px - 1200px) | "You Are Comparing" section --> Sub-heading --> The sub-heading gets truncated when the screen-size within the mentioned range (in case of default or large font) | https://www.loom.com/i/db73e6e1145e45e69d6501ce536af2c1 | -
CC_144 | 2026-05-04 | All Browsers | P3 |  | Desktops | Keyboard Accessibility --> Select Drawer --> When tab focus is on the drawer's cross button, clicking on shift + tab doesn't shift the focus to previous element | https://www.loom.com/i/74789e3828c643549cf23d4894d8bc07 | -
CC_145 | 2026-05-05 | All Browsers | P2 |  | Touch Devices | Comparison Table --> The accordion heading & the cell content are not horizontally aligned with each other now. They should follow the same margin gap | https://www.loom.com/i/06904d00aa0d462aa4c627c17a3c45f7 | -
CC_146 | 2026-05-05 | All Browsers | P2 |  | Touch Devices | No Matter how many cards added in the slot --> Reduce the font size --> Close and open the top accordion --> Increase the font size --> Notice how the content gets cropped because the accordion adjusts its size incorrectly (not enough to show the entire content) | https://www.loom.com/share/2a8a7d477030461ea6006231fc6a7e4c | -
CC_147 | 2026-05-05 | All Browsers | P2 |  | All Devices | Screen Reader --> For blind users, the narrator only reads the content each cell in the container table without any context about which benefit row it belongs to or for which card making it impossible for the user to get the context of the point being narrated | - | -
CC_148 | 2026-05-05 | All Browsers | P1 |  | All Devices | Frequent Layout shifts are causing the page to stutter and if not, are surely affecting user's focus. On real devices we have Header bars disappearing, You are comparing section getting to its sticking position, then getting contracted or expanded even with a slightest scroll, not to mention the address bar appearance and disappearance with scroll on real devices - Too many items are causing too many frequent layout shifts. | - | -