## Sheet1
Defect no | Date | Device | Browsers (Chrome/firefox/Edge/Safari) | fontsize- lg/md/sm | Description | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Bug Priority | Assigned To (Developer Name) | Dev Status | Last Fixed On | Dev Remark | QA Status | Last Tested On | QA Remark
1 | 2026-05-15 | Desktop | Edge | md | Glow/shadow effect around the AI assistant container is missing on site; Figma design shows visible glow effects on edges and corners | https://www.loom.com/share/0d675a2e8a9b4c6599ec7543c577b0e9 |  | P3 |  | Open |  |  | Failed | 2026-05-15 | Issue reproduced; expected glow visual effect from Figma is not implemented on site
2 | 2026-05-15 | Desktop | Edge | md | Send message arrow button appears larger on site, while Figma design shows a smaller and more compact circular button | https://www.loom.com/share/59ea21f911de4a7ea2f7afadeca5129b |  | P3 |  | Open |  |  | Failed | 2026-05-15 | Issue reproduced; send button size and spacing do not match Figma design reference
3 | 2026-05-15 | Desktop | Edge | md | UI action buttons inside AI assistant section are not working except the "+" icon; clicking other buttons does not perform any action | https://www.loom.com/share/46c872579a1d4e8799e34cef2bd082d3 |  | P1 |  | Open |  |  | Failed | 2026-05-15 | Issue reproduced; multiple interactive buttons are non-functional in AI assistant interface
4 | 2026-05-15 | Desktop | Edge | md | AI assistant container does not fully adapt to dark mode; inner container and input area remain in light theme causing inconsistent dark mode experience | https://www.loom.com/i/853eecc3eaa44f0eadddcfb155a31736 |  | P2 |  | Open |  |  | Failed | 2026-05-15 | Issue reproduced; dark mode styling is partially applied and does not match overall page theme
5 | 2026-05-15 | Desktop | Edge | md | Robot illustration outline appears cluttered and rough on site, affecting visual clarity and clean appearance of the AI assistant graphic | https://www.loom.com/share/4c901de7507d45ebb71aac8d0102681b |  | P3 |  | Open |  |  | Failed | 2026-05-15 | Issue reproduced; robot image edges/outlines do not appear smooth and visually polished
6 | 2026-05-15 | Desktop | Edge | md | Content area below the heading has reduced vertical padding on site compared to Figma; design shows more balanced spacing similar to the input box section | https://www.loom.com/i/394642e4e4c74adcbb5cf6ba8bf57bea | https://www.loom.com/i/b82ea1e0b50448e5b9c6e7c95137d51a | P3 |  | Open |  |  | Failed | 2026-05-15 | Issue reproduced; spacing between heading and suggestion buttons does not match design reference
7 | 2026-05-15 | Mobile | Edge | sm | ASK ILA floating widget overlaps the send button/input area at 320px screen width, affecting usability and visibility | https://www.loom.com/share/756a257e80b64ee69395ce3454a44735 |  | P2 |  | Open |  |  | Failed | 2026-05-15 | Issue reproduced; floating widget overlaps interactive input controls on small screen devices

## Sampreets Findings
Date | Browsers | Font Size | Device | Priority | Title | Description | Steps to Reproduce | Issue Screenshot/Recording | Design Screenshot/Screen Recording | Dev Status | Last Fixed On | Dev Remark | Status | Last Tested On | QA Remark
2026-05-14 | All Browsers | - | All Devices | P2 | HTML Errors Found on Webpage via Nu HTML Validator | The webpage contains 3 HTML validation errors identified using the Nu HTML Checker - https://validator.nu/ - 1. Attribute inert not allowed on element div at this point. (2) 2. Bad value for attribute aria-activedescendant on element input: An ID must not be the empty string. | Copy the Page URL --> Go to - https://validator.nu/ --> Paste the URL and click on Validate --> Click on Message filtering to segregate errors & warnings. | https://loom.com/i/6e181a2f65774551b72ea54ecf5f0aaf | - | Fixed |  | All the issues and warnings are resolved.
2026-05-14 | All Browsers | - | Desktops | P2 | Search suggestion item doesn't get filled in the input box | If user chooses an option from the search suggestions list, they expect it to get filled in the input box for them to proceed and search for it. | Enter any characters in the input box --> Select an option from the search suggestions list --> Notice how the selected option doesn't get filled in the input box. | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQA9LBljihMVRL_WrX9p3ZN2AeVk53kTyCRQZnnF6esNS3U?e=EgAY2d | - | Fixed |  | Autocomplete is optimised such that when user clicks on some search suggestion it gets filled in the input
2026-05-14 | All Browsers | - | Desktops | P2 | Quick Search option tabs do not have any hover state | As informed by the designer, the 5 quick search options (I love shopping, etc.) have their hover state created in the design but not implemented in the HTML | Hover over any of the 5 quick search buttons --> Notice how they are missing their hover state UI | https://www.loom.com/i/544af147f60048d3b93703953e02f8c1 | - | Fixed |  | This was not provided by Phulvinder previously. Just now got it applying now.
2026-05-14 | All Browsers | - | All Devices | P3 | Add button's item list its glassmorphism effect | In the design, the add button item list's background is translucent making the background elements blurrily visible. | Click on Add button --> Notice the item list's background. | https://www.loom.com/i/5117c946ae6446e1a9419d066da442ba | https://www.loom.com/i/d986e48f6421406390a4bdd6db4e22c9 | Fixed |  | Now there is an opacity od 85% applied along with backdrop blur of 5 px as per discussion and agreement with Phulvinder.
2026-05-14 | All Browsers | - | All Devices | P3 | Search Suggestions List missing its glassmorphism effect | In the design, the search suggestion list background is translucent making the background elements blurrily visible. | Search anything in the Search Input box --> Notice the search suggestion list background. | https://www.loom.com/i/674616ba3f0b4a11a78594bc95761c3b | https://www.loom.com/i/2753eda2f14b453490ea7539b545fb10 | Fixed |  | Now there is an opacity od 85% applied along with backdrop blur of 5 px as per discussion and agreement with Phulvinder.
2026-05-14 | All Browsers | - | All Devices | P3 | Start Now button's arrow icon vertically unaligned | The button's label "Start Now" & the arrow icon besides it do not appear vertically center aligned. | Start Now button --> Notice the arrow icon's vertical alignment | https://www.loom.com/i/ea1502010bc849089a690800b8d40c5a | - | Fixed |  | The icon is properly aligned.
2026-05-14 | All Browsers | - | Desktops | P3 | Tablet container missing glow effect | In the design, the tablet container has glow effects on its top right & bottom left corner in case of desktops | Tablet container --> Notice the top right & bottom left corner | https://www.loom.com/i/73fb47f21a8c4cca81d7087e81de5175 | https://www.loom.com/i/4b15a54fdd164e57954f24df6ef28251
2026-05-14 | All Browsers | - | All Devices | P3 | Tablet container's inner border gradiance missing | In the design, the tablet container's inner border has a linear gradiance from left to right. Check the expected result screenshot. | Tablet container --> Notice the dark inner border | https://www.loom.com/i/c3073c02a65049b89442dcaac613cc90 | https://www.loom.com/i/3e68a0f229124fcba698c42bcd97baa6 | Fixed |  | Gradiant applied for the inner tablet border
2026-05-14 | All Browsers | Large | Desktops (>=1350px width) | P1 | Quick Search options tab UI breaks in case of lengthy label | If a button label gets wrapped to 3rd line then it will break the button's UI. For ex: "I Spend 10,000+/Month On Groceries" | Desktops (above 1350px width) --> Increase the font size --> Notice how the "I Spend 10,000+/Month On Groceries" tab label gets word wrapped to 3rd line breaking the UI | https://www.loom.com/i/c56b2037bd244548bbba4e2c1195b672 | - | Need Discussion
2026-05-14 | All Browsers | - | Desktops | P3 | Search Input Box's outer border missing | In the design, the Search Input box also has an outer 1px white border around its container apart from the grey border. | Search Input Box --> Notice the 1px white outer border present in the design is missing. | https://www.loom.com/i/c093e470fd524d77942ecce428f82faf | https://www.loom.com/i/363e8f793c134fbcbbedb815694b5a49 | Fixed |  | Already had a discussion on thi with Philvinder, this outer border is just a design created mistakenly and not to be taken in account while devlopment. | Resolved | 2026-05-15 | 15/05/2026 - As per the dev remark and confirmation from Phulvinder ji, closing this issue as it was a design mistake.
2026-05-14 | All Browsers | - | All Devices | P2 | <h> tag for contextual headings not being followed. | Blind users use H key shortcut for the screen-reader to narrate all the headings & sub-headings present on the page. Section's subheading, tablet container's heading & banner heading all provide contextual information and therefore are important to get narrated but they won't be identified if <h> tag not used for them. | Inspect section's sub-heading, tablet container heading & banner title --> Notice how all 3 headings provide contexual information to the user but are not in <h> tag | https://www.loom.com/i/c35a12250abc4b178ce37614cb36b038 | - | Fixed |  | Subheadings chnaged to h2
2026-05-15 | All Browsers | - | Desktops | P3 | Quick 3 Banner font appearing larger than section heading | Please discuss with the client if it is okay for the banner font size to appear larger than the section title itself. Usually font size hierarchy is to be maintained | Quick 3 Banner --> Heading font size --> Compare it with the section's heading | https://www.loom.com/i/392e3925eea149b5bd60488fcbd7f09c | - | Need Discussion
2026-05-15 | All Browsers | - | All Devices | P2 | Section Background image goes blurry & lack sharpness | The Find perfect card background image lacks sharpness on all devices. Also, it should have 3 different images for 3 breakpoints - Mobile, Tablet & Desktops | Find perfect card background image --> Notice how the 0s & 1s in the binary code streaks appear blurry and lack sharpness. | https://www.loom.com/i/39a7c098f3d64f74a4983f6b6171abcc | https://loom.com/i/9e149d584e7b43f9bb4c29cd970afede | Fixed |  | A refined image will be provided by Phulvinder.
2026-05-15 | Chrome | - | All Devices | P3 | Font weight & color rendering on chrome doesn't match | The font weight even though is same across the browsers but the fonts still appear slightly less bolder when compared with edge & firefox browser. Also, Font colour on chrome appears lighter when compared with other browsers | Chrome Browser --> Compare the font weight & colour rendering on chrome with other browsers and notice the difference | https://loom.com/i/f6fc910d653347a981aa06836475591f | https://loom.com/i/c57e9a5ed5d14a13908d76cfd3a489c9
2026-05-15 | All Browsers | - | All Devices | P2 | Quick 3's "Start Now" Arrow not consistent with other CTAs | All across the pages, wherever the arrow icon is used with a CTA, it is used as an svg instead of a plain text symbol. Also, when hovered up on, the arrow slightly moves. This svg icon & hover effect needs to be followed for Start Now CTA as well | Quick 3 Banner --> Start Now --> Compare the arrow and its hover state with other arrows present on other page CTAs | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBh7KXGQcA9SI8Ob5YIrmO7AcDQXlrX9jsPaV3ApJl0kYs?e=A8is2G | - | Fixed |  | Added the svg and the complete content is now aligned well
2026-05-15 | All Browsers | - | Mobile Phones | P3 | Tablet heading has less margin space from its container | Please discuss with the client if it the current width of the heading inside the tablet needs to be reduced to have more left & right margin space for the container border | Mobile Phones --> Tablet Heading --> Notice the left & right margin space of the heading from its container. | https://www.loom.com/i/e5c009a9f3b7442296a4384347883967 | -
2026-05-15 | All Browsers | - | Mobile Phones | P3 | Scaling down button sizes in Search Bar for mobile phones | Please discuss with the client if they wish to get the Add & submit button size more reduced for mobile phones in order for their size to be appropriately scaled according to the device size and also to have more input box length. If it is fine as it is, will close the issue. | Mobile Phones --> Search Bar --> Add button & Submit button size | https://www.loom.com/i/d3cd88332b0146f1960ba78bf9f24ef0 | -
2026-05-15 | All Browsers | - | Tablets / iPads | P2 | Quick 3's "Start Now" label gets wrapped to next line | The client may not want the "Start Now" CTA label to get wrapped to the next line in turn increasing the height of the CTA affecting the UI look of it. This happens in case of Tablets/ iPads and may happen for desktops if the Quick 3 Banner title is lenthier and the font size is increased to large instead of default | Tablets, iPads --> Quick 3 --> Start Now CTA --> Notice how the CTA label goes to 2 lines instead of being in a single line. | https://www.loom.com/i/8f7b444f28374114845ba44a61ff657e | -
2026-05-15 | All Browsers | - | All Devices | P2 | Quick 3's "Start Now" CTA has button tag instead of Anchor | If clicking on something will redirect us to a new page, we should use <a> anchor tag for it instead of button. Buttons only if some action is to be performed on the same page. As we will be redirecting the user to Simplifier page with this CTA therefore it should have <a> tag | Quick 3 Banner --> Start Now --> Inspect and notice how it has <button> tag instead of <a> tag | https://www.loom.com/i/0b90fe14c72b4b959dacb32465df04a2 | -
2026-05-15 | All Browsers | - | Desktops | P3 | Search suggestions dropdown opens without available suggestions | If any keyword that doesn't have any search suggestions is entered in the input box and down arrow key on the keyboard is pressed, empty search suggestions dialog box appears. | Input box --> Enter random characters --> click the down arrow button on the keyboard --> Notice how the search suggestions list box opens even when there are no suggestions. | https://www.loom.com/i/381ad38b80f3468c951fe30d0e88a59d | - | Fixed |  | Corrected the behaviour. If there are no suggestions then the combobox will not get open on pressing the arrow keys.
2026-05-15 | All Browsers | - | Desktops | P3 | Tab key collapses dropdown but retains focus on add button | When dropdown is open: Pressing Tab should usually close the dropdown and move to the next tabbable element. | Expand the Add button's list --> Arrow up & down key to shift focus between list items --> Press tab. Notice how the list collapses but the focus remains on the Add button instead of moving to the next focusable item. | SBI Card and 14 more pages - Personal - Microsoft​ Edge 2026-05-15 14-36-13.mp4 | -
2026-05-15 | All Browsers | - | Desktops | P3 | Search suggestion should not auto-fill on Tab or Shift+Tab | If enter or space bar is not pressed while the search suggestion item is in focus and simply tab or shift + tab is pressed, the list item should not get selected and filled in the input box. | Input box --> Search Suggestions list --> focus on any list item --> instead of enter, press tab --> Notice how focus shifts to next focusable element but the list item also gets filled in the input box | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQCL8iL6SxnZT7JoMUaXqzJIAX4ykdokKdqhDDLyF60hfVE?e=xhV2Pa | - | Fixed |  | Fixed the autocomplete keyboard interaction behavior. Previously, pressing Tab or Shift + Tab while a search suggestion was highlighted automatically selected and populated the value in the input field. Updated the interaction logic so that suggestions are now selected only through explicit actions such as Enter, Space, or mouse click. Tab navigation now correctly closes the suggestion popup and moves focus naturally without altering the input value.
2026-05-15 | All Browsers | - | Touch Devices | P1 | UI Colors Render Incorrectly on Real Mobile Devices | Tablet background colour, quick suggestion tab colour, Search bar border colour, AI Bot shadow effect render differently on real mobile devices and do not match the design but they render fine on real desktops. | Real Mobile Devices --> Noticehow all the colours render for each UI element in the section | https://ikokas.sharepoint.com/:v:/s/SBICreditCardWebsiteRevamp/IQBF4PQ3Qmo1S6MSKWM4QdIuAXkRUMGrTZ3WA0x0ZCCB2rk?e=34h8AS | -
2026-05-15 | All Browsers | - | Desktops | P3 | Window narrator list items focus does not shift by arrow keys | If using windows narrator, user remains unable to shfit the focus between list items using up & down arrow keys. It just narrates the list item label instead of shifting the focus to the next actionable list item. | Windows Narrator --> Add button dropdown --> Press up & down arrow key --> Notice how the focus doesn't shift | - | -
2026-05-15 | All Browsers | - | Desktops | P2 | Add dropdown item role not announced | Add button's list items when focused through nvda narrator, do not mention their role which is hyperlink. | NVDA Narrator --> Add button dropdown --> Focus on list items | - | -